|  |  | Back to Office Report Submitted by: Marco CHIU Title: UN-REDD Regional Technical Advisor Date submitted: August 28th 2015 |  |
| --- | --- | --- | --- |
| 1. Practice area: BPPS / UN-REDD |  |  |  |
| 2. Mission period (incl. of travel days) From: July 12th to: July 18th, 2015 |  |  |  |
| 3. Type of mission: Support Argentina´s UN-REDD NP inception workshop and first Steering Committee meeting |  | 4. Clients Secretariat of Environment and Sustainable Development (SAyDS) |  |
| 5. Purpose of mission - Work with SAyDS in the preparation of the AWP and revisions of the NP´s results framework - Support the delivery of the NP´s inception workshop - Support SAyDS and agencies COs on the delivery of the first NP Steering Committee meeting |  | 6. Documents, materials, resources - Agenda of the workshop and Steering Committee meeting - Argentina´s NP inception workshop report (including Participants list) |  |
| 7. Mission members Daniel TOMASINI, Matias MOTTET, Alejandra García, and Marco CHIU (UNDP); Juan FERRANDO (UNEP); and Serena Fortuna, Angel Parra, and Francisco Yofre (FAO). |  | 8. Costs UN-REDD Global Programme |  |
| 9. Brief summary of the mission Argentina, a partner country of the UN-REDD Programme since 2010, was invited by the Policy Board to present a submission for a National Programme at PB 11 or PB 12 (December 2013 or June 2014 respectively). The country got approval at PB12 for the implementation of its NP for US $ 3,591,000. The project document is in an advanced stage of completion at the moment, starting the circuit for getting the appropriate clearances and proceed to signatures. Argentina has an R-PP developed and assessed by the Forest Carbon Partership Facility in 2010, but has not yet completed its grant agreement. In the context of developing the FCPF grant agreement and the UN-REDD inception phase, a conceptual framework to integrate SESA and ESMF as part of the broader SE process, and as part of the development of Argentina´s REDD+ NS/AP, has been defined by SAyDS with support from UN-REDD and FCPF. Following signatures of Argentina´s UN-REDD NP Project Document in March 2015, the inception phase took place until July 2015. In this context this inter-agency mission was carried out to support the PMU on the development of the inception workshop and the first Project Board Meeting. These two events were preceded by a capacity building day on REDD+ delivered by the regional UN-REDD team to recently hired PMU staff members. 9.a Findings - The inception workshop took place as planned. It was developed at Argentina´s Foreign Affairs Ministry with attendance of more than 80 participants representing IPs, national and provincial government entities, academia, NGOs, and some SAyDS authorities. - The agenda of the workshop included: (1) presentations on REDD+; (2) the readiness status in Argentina; (3) the UN-REDD Programme; and (4) a general look at Argentina´s NP. Group-work followed these presentations, aimed at collecting views from participants on the results framework of Argentina´s NP. - A number of recommendations for the UN-REDD team in Argentina were presented at the plenary, summarizing views discussed on working groups organized by NP component. Some of those recommendations apply to the NP design and some others to the implementation phase. They are to be consolidated in the workshop report (at the time of finalizing this BTOR the report was made available on the web; it can be reached here). - Some of the main recommendations from participants include: - On participatory platforms and stakeholder engagement - Consolidate the REDD+ Advisory Council (CAR). It was requested to ensure participation of IPs, also takin into account that IPs already have a proposal of a consultation protocol. - Organize the CAR by creating thematic working groups dedicated to address different issues. - For communications it was requested to work with stakeholders with proven capacity to disseminate information effectively. It was recommended to use participatory assemblys as a platform, as well as audiovisual and printed materials in Spanish and native languages. - Think about stakeholders like family-farming organizations, protected areas extensionists, and others in the rural sector. - For the development of the REDD+ NS/AP - Revise the stakeholder engagement approach in order to assess whether it needs to be broaden to cover all types of forest-related stakeholders. - Include gender as a transversal topic - Include ecosystem restoration activities using native species (increasing carbon stocks) - Strengthen the application of the relevant current legal framework - IPs suggested to engage the judiciary system in the process - Include in the analysis the data and models run by the 3rd NC, in which emission reductions were simulated, using different scenarios of forest protection (taking as a basis the forestry law zoning). - On FREL and forest monitoring systems - It was stressed the need to differentiate between monitoring systems and surveillance/control systems. - Engage IPs actively and ensure technical capacity development. The “forest wardens” experience was mentioned as a good example to replicate. - Discuss means to disseminate information, other than the web, to foster forest-nodal inter-link at the provincial level. - Consider real-time early warning systems. - On safeguards - Strengthen the consultation processes in the country, taking into account specific protocols for IPs and with respect to IPs vision, as well as IP networks engaged in the REDD+ readiness process. - Create a specific safeguards roundtable dedicated to IPs, promoting dialogues at the national and provincial levels. - IPs suggest to develop a dialogue in which there is respect to the rights of IPs, as well as a common understanding of territory, communal property, and the concept of good living. - Ensure the engagement of provincial authorities. - Link Argentina´s NP to SAyDS Social Observatory on Forestry and on Biodiversity. - Ensure the inclusion of the other forest ecosystem services in the discussion. - In addition to the inception workshop, the PMU worked with the UN-REDD team to prepare the documents for the first Project Board Meeting. During the preparation of these documents, the UN-REDD team suggested to adjust the language on the results framework to better reflect further refinements in the rational of some activities. SAyDS originally accepted but then decided not to present to the Project Board such suggested changes. If those editions are determined relevant after starting the NP implementation, then another opportunity to revise the result framework will be envisioned. - The first Project Board Meeting took place on Friday July 17th with participation of delegates from SAyDS, Ministry of Agriculture, Foreign Affairs, UN-REDD Agencies, and IPs and civil society representatives as observers. The meeting was co-chaired by the UN RR and the Head of the SAyDS Advisory team. - The Project Board received a proposal of AWP that goes from July 2015 to June 2016, which marked the beginning of the NP implementation. SAyDS willingness to show results towards the end of 2015 compromise the ability to secure a technically sound programming (i.e. performing a legal and institutional gap assessment for safeguards before defining the “Country Approach to Safeguards”; or assessing REDD+ risk and benefits before defining a first set of REDD+ PaMs). As a result, it was agreed to discuss further, at the technical level, between SAyDS and UN-REDD ways to address this issue and then submit a revised AWP for consideration of the Board. - The Board also agreed to consider developing future meetings at the sub-national level, on sites were activities are being implemented. 9.b Results achieved (key outputs) - Inception workshop delivered: The event provided the opportunity to create momentum among different stakeholders engaged in the REDD+ readiness process in Argentina to reinforce their commitment to collaborate with the process. Expectations were inevitably created, at least from civil society there was a clear demand to be infirmed and engaged in the process. SAyDS committed to define the means to support this. - AWP reviewed and process for approval defined: The Project board had the opportunity to revise the results, products, and targets for the first year of implementation. The process for approving the AWP was agreed too. - UN-REDD NP Project Document content shared with SAyDS technical staff: The training on REDD+ delivered to the PMU, although short, provided the chance to offer the sources of information available to access documents and tools on REDD+, both on the UNFCCC and the UN-REDD Programme. 9.c Expected outcomes and impacts As a result of this mission and related follow up, it is expected that: - Argentina will successfully start the implementation of the NP. - The PMU organize all the documentation to formalize the beginning of the implementation. - SAyDS will be able to motivate key stakeholders to continue engaged during the implementation of the UN-REDD NP. |  |  |  |
| 10. Key counterparts Secretariat of Environment and Sustainable Development (SAyDS). |  |  |  |
| 11. Follow up action matrix |  |  |  |
| Action to be taken | By whom |  | Expected completion date |
| - Produce the Inception Workshop Report | PMU supported by UN-REDD team |  | Mid August 2015 |
| - Manage signatures on the First Project Board Meeting minutes | PMU supported by UNDP-CO |  | End July 2015 |
| - Follow up on the development of roadmaps towards key results of the AWP. | PMU supported by UN-REDD team |  | September |
| 12. Distribution list Tim, Josep, Arturo, Clea, Mirey, Fernando, Daniel, Matias, Dina, PY, Bruno, Matilde, Jen, Kim, Hellen, |  |  |  |

Annex I: Inception Workshop Agenda

Taller de Lanzamiento del Programa Nacional ONU-REDD

Ciudad de Buenos Aires 14 y 15 de Julio

Antecedentes

El Programa de Naciones Unidas ONU REDD es una iniciativa de colaboración para reducir las emisiones de la deforestación de bosques (REDD) en los países en desarrollo. El programa lanzó en 2008 y cuenta con el apoyo y experiencia de la Organización de las Naciones Unidas para la Agricultura y la Alimentación (FAO), el Programa de Naciones Unidas para el Medio Ambiente (PNUMA) y el Programa de Naciones Unidas para el Desarrollo (PNUD). El Programa apoya los procesos de preparación para la futura implementación de REDD+ llevados en cada país y promueve la participación activa e informada de todos los actores interesados, incluyendo los pueblos indígenas y otras comunidades que dependen de los bosques en la implementación de REDD+ a nivel nacional e internacional.

Los Acuerdos de Cancún (2010) alcanzado durante la COP16 identificaron cuatro elementos claves que los países interesados en implementar REDD+ están llamados a completar (Decisión 1/CP 16). Entre tales elementos se encuentra el desarrollo de planes de acción o estrategias nacionales REDD+.

La propuesta de Programa Nacional (PN) ONU REDD se basa en el análisis de los lineamientos establecidos en el R-PP de Argentina y en los diálogos con varios actores relevantes llevados a cabo durante, y en seguimiento, a las misiones al país de las agencias de Naciones Unidas encargadas de apoyar la implementación del programa en el país. Para la preparación de R-PP y el PN hubieron varias instancias de consulta dentro del gobierno y hacia afuera, iniciadas en 2008 y cubriendo distintas regiones del país con el fin de priorizar necesidades.

El Programa ONU - REDD ha considerado relevante promover la creación de un espacio para el aprendizaje y el intercambio de experiencias entre los países sobre el desarrollo de sus planes de acción o estrategias nacionales REDD+. Algunos aspectos que los países están considerando incluyen la evaluación de los recursos forestales nacionales, como la cobertura boscosa y su distribución geográfica; los arreglos legales e institucionales necesarios; la creación de espacios de participación de la sociedad civil; la identificación de los impulsores de deforestación y degradación de bosques, así como las actividades para combatirlas y la identificación de áreas geográficas prioritarias; el desarrollo de análisis económicos y espaciales para la toma de decisiones informadas; la definición de una estructura y planes de sostenibilidad financiera; el establecimiento de lineamientos para la implementación de REDD+; así como la articulación con las prioridades y políticas existentes en cada país, entre otros. El plan de acción o estrategia nacional REDD+ debe guardar consistencia con la forma en la que los países estén abordando los otros tres elementos claves establecidos en los Acuerdos de Cancún (un nivel nacional de referencia de las emisiones forestales y/o un nivel nacional de referencia forestal; un sistema nacional de vigilancia forestal; un sistema de información sobre salvaguardas).

Objetivos:

- Proporcionar una visión general sobre ONU REDD

- Presentar el Programa Nacional (PN) ONU REDD en Argentina

- Conformar un espacio de consensos acerca de aquellos aspectos claves referentes al inicio y ejecución del PN, el marco de resultados y los planes operativos.

- Clarificar conceptos claves, definir roles y responsabilidades y difundir y potenciar próximas actividades.

- Asegurar la participación plena de los distintos asociados previamente identificados en los procesos de consulta a las partes interesadas, como así también recoger, intercambiar y discutir toda la información que fuera de utilidad para realizar ajustes necesarios en la estrategia de implementación.

AGENDA

| Día 1 (Lunes 13 de Julio) Trabajo interno: Capacitación Unidad Operativa | Actividades | Facilitadores/as | Participantes |
| --- | --- | --- | --- |
| 9.30 a 12.00 hs | Reunión de coordinación y repaso de agenda |  | UOP/FACILITADOR |
| 12.00 a 17.00 (con corte para almuerzo) | Capacitación Unidad Operativa (UOP) - Bosques y cambio climático - Generalidades sobre la preparación para REDD+ en Argentina - El Programa ONU REDD - Enfoque de género de programa ONU REDD - REDD+ bajo la CMUCCC y los cuatro pilares de REDD+ nacional o plan de acción REDD+ - Nivel de Referencia de Emisiones Forestales - Sistema Nacional de Monitoreo de Bosques - Sistema de Información sobre Salvaguardas | A definir por las agencias | UOP/ FACILITADOR |
| 14.00 a 17.00 hs | Reunión paralela con pueblos originarios | Esp. en pueblos originarios | Pueblos originarios |
| 14.00 a 17.00 hs | Reunión paralela CAR |  | OSCs |

| Día 2 (Martes 14 de Julio) Presentación de Programa ONU – REDD Argentina | Actividades | Facilitadores/as | Participantes |
| --- | --- | --- | --- |
| 9.00 a 9.30 | Recepción Participantes. | FACILITADOR/ UOP | OSCs, PO, SAyDS y Otros ministerios, Instituciones academicas, Sector privado |
| 9.30 a 10.00 | Bosques y Cambio Climático en Argentina Políticas Públicas forestales y su articulación con REDD. | Coordinador Nacional |  |
| 10.00 a 10.30 | Presentación ONU REDD | EQUIPO REGIONAL PNUD |  |
| 10.30 a 11.15 | Presentación ONU-REDD en Argentina Presentación cuatro pilares de REDD+. Objetivos. Componentes. Estructura. | Coordinador Nacional Coordinador Técnico |  |
| 11.15 a 11.30 | Receso. |  |  |
| 11.30 a 12.00 | Presentación de Resultados | Coordinador Nacional |  |
| 12.00 a 12.30 | Presentación de lineamientos del Plan Operativo Anual (POA) | Coordinador Técnico |  |
| 12.30 | Receso. Almuerzo. |  |  |
| 14.30 a 17.00 | Grupos de Trabajo. Contenidos: - Acciones estratégicas para evitar la deforestación y degradación del Construcción - Nivel de Referencia Nacional de Emisiones Forestales. - Fortalecimiento del Sistema Nacional de Monitoreo de Bosques (SNMB) - Desarrollo del Sistema de Información sobre Salvaguardas (SIS) e involucramiento de actores Productos deseados: - Marco lógico actualizado para cada uno de los componentes del Programa. - Planes operativos anuales ajustados para cada uno de los componentes con un enfoque en los resultados esperados para diciembre 2015. - Esquema y pautas de seguimiento y monitoreo del Programa con proyección para el primer año de trabajo | FACILITADOR/UOP | Grupos de Trabajo con OSCs, PO, SAyDS y Otros ministerios, Instituciones academicas, Sector privado |
| 17.00 a 18.00 | Resumen del día y cierre. |  |  |

| Día 3 (Miércoles 15 de Julio) Taller de presentación ONU – REDD Argentina | Actividades | Facilitadores/as | Participantes |
| --- | --- | --- | --- |
| 9.00 A 9.30 | Recepción Participantes. | FACILITADOR/UOP | OSCs, PO, SAyDS y Otros ministerios, Instituciones academicas, Sector privado |
| 9.30 a 11.30 | Plenario. Grupos de Trabajo. Resumen de los principales productos y acciones que llevará a cabo componente. | FACILITADOR/UOP |  |
| 11.30 a 12.00 | Presentación de protocolo de consulta de pueblos originarios | Representante de pueblos originarios |  |
| 12.00 a 12.30 | Presentación CAR | Marisa Young |  |
| 12.30 a 13.30 | Receso almuerzo |  |  |
| 13.30 a 16.30 | Plenario. Acuerdos Generales. | Presentación de resultados de cada grupo por un informante designado |  |
| 16.30 a 18.00 | Resumen general y cierre. |  |  |

| Día 3 (jueves 16 de julio) | Actividades | Facilitador | Participantes |
| --- | --- | --- | --- |
| 10.00 a 13.30 hs | Revisión de insumos para la reunión de la Junta |  | UOP y agencias |
| 13.30 a 14.30 hs | Receso almuerzo |  |  |
| 14.30 a 16.15 | Reunión de trabajo interagencial |  | UOP y Agencias |
| 16.15 a 19.00 Sesiones paralelas | Capacitaciones especificas Operativa Nivel de referencia INDCs | FAO | SAyDS (área de bosques, cambio climático, cancillería, etc) |
|  | Reunión con entidades que realizarán estudios de costo de oportunidad y escenarios espaciales futuros: | PNUMA Coordinador Nacional Coordinador Técnico | Entidades realizadoras de estudios de costo de oportunidad y escenarios espaciales futuros |

| Día 5 (Viernes 17 de Julio) | Actividades 1era Junta de Proyecto ONU -REDD Argentina | Participantes |
| --- | --- | --- |
| 10 hs | Recepción |  |
| 11hs | Presentación del proceso REDD+ en Argentina y la visión de país; El Programa ONU – REDD en Argentina. Descripción de roles, funciones y responsabilidades de la Junta de Proyecto Presentación y aprobación del Plan Operativo Anual Recomendaciones de la Junta de Proyecto hacia la implementación del Programa ONU –REDD Argentina Cierre de la reunión | Secretaria de Ambiente, agencias, cancillería, coordinador residente SNU Agricultura, sociedad civil, banco mundial, Cofema, otros observadores |

Décimo Sexta Conferencia de las Partes de la Convención Marco de Naciones Unidas sobre Cambio Climático.