22 June, 2012

NPWG CALL- Action points only

- Tracking tool for NPs.

- The following feedback was provided to the Secretariat regarding the tracking tool:

  - Add a formula to calculate % Duration automatically

  - Add a column for delivery based on the total amount approved and not only on the amount transferred

  - Put the columns of delivery and duration together

  - Replace Start date with transfer of funds

  - Add a column for targeted support to be cross-checked with Thais and Helena

  - Record Co-financing information from the Annual Reports (in numbers, not ticks)

  - Double check the financial information extracted from the MPTF-O

  - Extract existing HACT Macro Assessments from the UNDG website and rate the column

- In terms of  timing and roles and responsibilities:

  - Financial information shall be updated on a quarterly basis, UNDP’s info accessed directly from the Secretariat via Atlas, FAO and UNEP information to be provided by the financial focal points (FAO and UNEP will confirm by the next call whom)

  - Achievement of outcomes shall be updated every six months by the Secretariat based on the semi-annual reports

  - Columns M-O to be provided by UNDP by next call

  - Tracking tool to be updated via share docs

- Bolivia.

- Wait for the document that the Government will send to the Mission

- Receive comments from mission members

- The mission leader will compile the comments, and prepare a new draft

- When drafting the recommendations will consult with the Secretariat for consistency with procedures, and the mandate given by the PB

- Vietnam

- Yemi will request that the comments sent by Mme Thoa are incorporated as track changes in the draft Chapter 4.

- Applying principles for NP delivery

- Yemi will send the principles to the RTAs, requesting their application for all new National Programmes and  to the extent that is appropriate for existing National Programmes. For existing National Programmes (except those finalizing) the Lead Agency shall be designated.

- It was clarified that is important that in line with the principles, the implementation modalities are to beagreed between the three agencies, and the National counterpart.

- Targeted support (Helena or Thais to join)

- To avoid additional steps, Helena or Thais will join future discussion on targeted support and registered the decisions taken by the NPWG

- Upcoming FCPF and REDD+ partnership meetings.

This item was not discussed due to lack of time