[image: image1.jpg]UN-REDD

PROGRAMME



                     [image: image2.jpg]


       [image: image3.png]Z|a



       [image: image4.jpg]



Annual Joint Programme Progress Report
	Country/Global
	Bolivia

	Title:
	Bolivian UN-REDD National Programme

	Reporting Period
	January 1st, 2010  -  December 31st, 2010

	Date of Submission
	January 20th, 2011

	Submitted by/contact information
	Pierre-Yves GUEDEZ, 
Regional Technical Advisor, UNDP/UN-REDD LAC

pierre-yves.guedez@undp.org


I.  PURPOSE

Programme main outcome:
Bolivia’s readiness for implementing a REDD+ National Programme for reducing emissions from deforestation and forest degradation within the framework of the National Forest and Climate Change Strategy by 2013.

Outcomes:

1. Improving capacity among national government institutions for implementing REDD+ activities, and monitoring and assessing carbon stock in forests.

2. Improving civil society’s capacity for implementing REDD+ activities.
3. Generating REDD+-related experience at a local level, with the participation of territorial bodies and the civil society.
UNDAF related outcome:
Strengthening the institutional and organizational capacity for productive development and job creation through the sustainable management of natural resources and the environment.
Main implementing partners:
Policy Committee: ministries, vice-ministries (according to relevance) and social organizations.
Technical Committee: permanent members - technical teams of vice-ministries, prefectures, municipalities, public universities, research institutes, technical teams of social organizations - and temporary members - NGOs, private universities, institutes and research centers -.
Political Focal Point: Vice-Ministry of Environment, Biodiversity, Climate Changes and Forest Development and Management.
Technical Focal Point: Climate Change National Programme.

II.  RESOURCES

	Contributor
	Amount in  US$
	Title and description of programme/activities

	MDTF - UNREDD
	2,787,350
	Outcome 1. Improving capacity among national government institutions for implementing REDD+ activities, and monitoring and assessing carbon stock in forests.

	MDTF - UNREDD
	743,650 
	Outcome 2. Improving civil society’s capacity for implementing REDD+ activities.

	MDTF - UNREDD
	1,177,000
	Outcome 3. Generating REDD+-related experience at a local level, with the participation of territorial bodies and the civil society.

	KfW (Germany)
	€ 2,000,000 (in process)
€ 8,000,000 (in process)
	Technical Cooperation for Institutional strengthening 

Implementation of pilot projects.

	FCPF
	3,600,000 (under discussion)
	The RPP document has been prepared in 2010, but will be modified to reflect the results of the Conference of People on Climate Change and of the international negotiations on climate change before being submitted to the FCPF. 


The allocations of the funds from Germany and from FCPF have been discussed during the elaboration of the NJP document, by a team of government staff and consultants working together on a unique log-frame in order to ensure perfect synergy and coordination during the implementation of each initiative. They shall have the same steering committee and interlocutors.  
III.  RESULTS

The resources for 2011 were transferred to the UN agencies in December 2010. Implementation will begin effectively in 2011.

IV.  FUTURE WORK PLAN

Priority actions planned:

Improving capacity among national government institutions for implementing REDD+ activities, and monitoring and assessing carbon stock in forests: Design of the forest and land-use monitoring system, the national forest inventory and programming the inventory for priority areas; development of a new methodology for the inventory of carbon contents according to the IPCC; qualifying government institutions and other relevant stakeholders to work with methodologies, forest and land-use assessment tools and forest inventory; generating a deforestation and emission prognoses and scenarios; design of a system for transferring and distributing REDD+ resources; development of a collaborative analyzing and adjusting legal, political and institutional issues regarding REDD+; support to the implementation of the Climate Change National Programme; preparing a first version of Action Plan for Reducing Emissions from DD (REDD+ Plan) in basis of the causes analysis of deforestation and forest degradation and macroeconomic and social impacts of reducing deforestation and a prognosis of such impacts.
Improving civil society’s capacity for implementing REDD+ activities: Systematizing lessons learned at a REDD+ level; design of a communication and training strategy; developing a participation plan for stakeholders to design REDD+ activities; preparing communication material and training for different types of stakeholders; preparing a national REDD+ communication and training campaign addressed to decision makers, local stakeholders and general public; identifying needs at the university system for fostering research on REDD+; and promoting the creation of an accessible data and results bank from research on REDD+.
Generating REDD+-related experience at a local level, with the participation of territorial bodies and the civil society: Preparing a standard methodological framework for implementing pilot projects; designing a monitoring and assessment system on the impacts of pilot projects; selection of pilot REDD+ programmes and projects to be supported and design of technical cooperation for these pilot projects; and qualifying local stakeholders for planning, implementing, monitoring and assessment of REDD+ pilot projects.
Estimated budget required (2011 IN US$):
	Outcome
	TOTAL 
	FAO
	UNDP
	UNEP (through UNDP)

	1. Improving capacity among national government institutions for implementing REDD+ activities, and monitoring and assessing carbon stock in forests.
	831,500
	429,500
	186,500
	215,500

	2. Improving civil society’s capacity for implementing REDD+ activities.
	182,000
	-
	182,000
	-

	3. Generating REDD+ - related experience at a local level, with the participation of territorial bodies and the civil society.
	123,000
	52,000
	71,000
	-

	IC (7%)
	79,555
	33,705
	45,850
	

	Total:
	1,216,055
	515,205
	700,850
	


V.  FINANCIAL IMPLEMENTATION

	Participating UN Org.
	Total Transferred  Up to 31 December 2010
	Cumulative
Up to 31 December 2010
ACTUALS

	
	 
	Commitments *
	Disbursements **

	FAO
	US$ 515,205
	0-
	0-

	UNDP
	US$ 700,850 (including US$215.000 under UNEP supervision)
	0-
	0-

	UNEP
	UNEP has pooled its funds with those of UNDP, UNEP funds have been transferred directly from MDTF to UNDP 
	0-
	0-

	Total
	US$ 1,216,055
	0-
	0-


The funds listed in this table have been transferred at the end of 2010. They will be executed in 2011.
