## Sheet1
Task | Actions | PIC | Duration | June | July | August | September | October | November
Objective: Conduct UN-REDD NJP Indonesia Central Sulawesi inception workshop
1. Revise Indonesia UN-REDD FPIC Guideline document | * Check whole document for sensitive words such as "Indigenous Peoples" * Revise structure | Tom | 03Jun
2. Pak Yuyu to clear, or acknowledge FPIC document | * Send revised FPIC doc to Pak Yuyu * Pak Yuyu or staff to review | Tom/Pak Yuyu | 03-10Jun
3. Present FPIC document in Hanoi, receive inputs, consolidate | * Prepare presentation * Gain initial approval from UN-REDD at the global level for the Indonesia FPIC strategy * Need to obtain clarity and confirmation on the principles which need to be followed - the ground rules of FPIC * Develop (if possible) UN-REDD FPIC global principles | Tom/Lisa/Pak Yuyu | 16-18Jun
4. Develop participant list for inception workshop | * Major CSOs and local Government from each district should be present in the inception workshop * CSOs and local Government should both be consulted and agree on the final participant list * Can start with Provincial government (DINAS Kehutan), AMAN, JKPP, Huma, Karsa, etc. * Also ask LEAD local office in Palu * Pak Yuyu to approve * Send invitations, DSA, travel etc etc. | Silje/Rogier | 10-30Jun
5. Hire Pak Hegar as FPIC coordinator for Central Sulawesi | * Develop TOR * SSA contract, 5 months based in Central Sulawesi * Start obtaining feedback on FPIC Guidelines and strategy for Central Sulawesi | Pak Machfudh/Silje | 03-12Jun
6. Clarify FPIC tools for inception workshop | * FPIC tools are intended for local stakeholders to understand what kind of support/methods are available for use in each district for FPIC * Awareness raising - this should be carried out in all districts. * Participatory mapping- costs about 3,500-5,000USD/location. BRWA/AMAN can be consulted for package level information and to present in the inception workshop * Workshops at district and village level - PA should develop simple guidelines and standard fees, what can and can't be supported by UN-REDD etc. | Tom | 10-15Jun
7. Clarify UN-REDD support modality and budget level for FPIC | * Clarify which Output can be used for which FPIC tool, and also the budget: - awareness raising (radio, pamphlets, tv, factsheets etc.) - participatory mapping - consultations - district and village level workshops | Alex/Rogier/Hanna | 10-20Jun
8. Develop FPIC presentation for inception workshop | *Should include the following: -UN-REDD FPIC principles (ground rules) as confirmed in Hanoi - DRAFT concept of a CSO Body in Palu - DRAFT awareness raising strategy for whole Province - DRAFT FPIC tool budget allocation | Tom | 25-30Jun
9. Conduct Palu inception workshop | * As per AMAN request, CSOs/local communities should be invited one day before the workshop so they can socialize and obtain common ground amongst themselves. This is a CSO only event, Gov/UN should not attend unless requested. * Pak Hegar (head of the DKN Adat Chamber) should moderate the FPIC sessions * Achieve clarity on a CSO Body to be based in Palu * Clarity on activities and pilot districts * Decision on FPIC support budget distribution at district level * Some clarity on district specific FPIC institutional arrangements * Identify any FPIC principles in addition to the UN-REDD global FPIC principles, and develop Central Sulawesi FPIC principles | UN-REDD/ local Government/ LEAD | 1st week July
Task | Actions | PIC | Duration | June | July | August | September | October | November
Objective: Establish FPIC framework in Central Sulawesi
1. Establish CSO Body in Palu | * The structure, staffing and institutional arrangement of the CSO Body should be determined in the inception workshop. Maybe under UN-REDD Palu coordination office, maybe more independent. * Functions of the CSO Body would include: - Conduct REDD+/UN-REDD awareness raising for all districts - Assist and coordinate district level FPIC processes - Act as a focal point for grievances and complaints - Coordinate with BRWA, LEAD, Government and other key stakeholders - Open door policy | Pak Hegar, UN-REDD, local Government
2. District CSO/Government consortiums develop FPIC plans for each pilot district | * Develop work plan, including FPIC tools and other UN-REDD support mechanisms * Districts to coordinate with CSO Body and UN-REDD to ensure FPIC principles are met. Key FPIC principles may include gender, household level consultations and participatory mapping | District CSO/Gov consortium, CSO Body
3. CSO Body reports to UN-REDD on district FPIC plans | * Report to UN-REDD HQ (Mina Setra, Charles McNeil) and other related global level meetings to ensure Central Sulawesi district level FPIC plans are in line with UN-REDD standards | CSO Body, UN-REDD
Task | Actions | PIC | Duration | June | July | August | September | October | November
Objective: Conduct FPIC and M&E
1. Provincial level REDD+ awareness raising | * CSO Body coordinates and supports Provincial and district level awareness raising, including the development of flyers, radio script etc. * First 3 months intensive awarenss raising, afterwards changing to REDD+/CC related updates and events | CSO Body/UN-REDD, province, all districts | 2nd wk July-
2. Districts conduct FPIC | * Additional awareness raising, if CSO Body coordinated province-wide awareness raising is insufficient * consultations, meetings at district/village level * participatory mapping in several areas according to available budget * Process should be documented and communicated by CSO Body/UN-REDD Provincial office communications expert * CSO Body/UN-REDD provincial office to support procurement and related costs as agreed in inception workshop | Districts, CSO Body
3.. Monitoring and Evaluation of FPIC at districts | * CSO Body should ensure reports are produced and shared * CSO Body engages in spot checks and ensures whether the process is in line with agreed Provincial level FPIC principles * UN-REDD to backstop M&E | CSO Body/UN-REDD
4. Independent M&E | * This could potentially be RECOFTC, to independently evaluate the district level FPIC processes | RECOFTC(?)
No.4 納品
No.5 納品
No.6 納品
FPIC Indonesia Guidelines
Inception work shop 1st wk July
Participant list
Support and coordination