REVISED STANDARD JOINT PROGRAMME DOCUMENT

Budget revision

1. Cover Page

Global

Programme Title: UN-REDD Programme – International Support Functions

Budget Revision (June 2009)

______________________________________________________________________

Joint Programme Outcome(s): This budget revision adds a new output under the existing Outcome 4, to provide funds for the establishment and operation of the UN-REDD Programme Secretariat.

Outcome 4: Increased knowledge management, communication and coordination

New Output 4.4: Establishment and operation of the UN-REDD Programme Secretariat

Programme Duration: 12 months

Anticipated start/end dates: 1 July 2009 / 30 June 2010

Fund Management Option(s): Pass-Through

Managing or Administrative Agent: UNDP

(if/as applicable)

Total estimated budget revision*:						2,888,415 US$

Out of which:

1. Funded Budget:		2,888,415 US$

2. Unfunded budget:		 	_____

* Total estimated budget includes both programme costs and indirect support costs

Budget allocations approved by the 1st UN-REDD Programme Policy Board, 10 March 2009:

6,673,590 US$

Total new budget:		9,562,005 US$

Sources of funded budget:

- Donor: UN-REDD Fund	2,888,415 US$

- Distribution of Funds

FAO 	   810,973 US$

UNDP 	   921,959 US$

UNEP 	1,155,483 US$

Names and signatures of participating UN organizations

| UN organizations | National Coordinating Authorities |
| --- | --- |
| Name of Representative: Peter Holmgren Director, Environment Climate Change and Bioenergy Division Signature Name of Organization: Food and Agriculture Organization of the United Nations Date & Seal | Not Applicable |
| Name of Representative: Veerle Vandeweerd Director, Environment and Energy Group Signature Name of Organization: United Nations Development Programme Date & Seal | Not applicable |
| Name of Representative: Tim Kasten Deputy Director, Division of Environmental Policy Signature Name of Organization: United Nations Environment Programme Date& Seal | Not applicable |

2. Executive Summary

At its first meeting (9-10 March 2009, Panama), the UN-REDD Policy Board approved the budget allocations for the Global Joint Programme, amounting to US$ 6,673,590.

The activities of the Global Joint Programme aim to support the country actions and provide the international community with confidence and understanding of the technical and social aspects of a post 2012 REDD mechanism.  The programme design draws from the respective strengths of the partner agencies in line with One-UN objectives and provides technical and scientific support as well as knowledge management.

With this budget revision, the overall formulation of the programme remains the same as per the first Global Joint Programme document signed by FAO, UNDP and UNEP and presented at the first Policy Board Meeting of the UN-REDD Programme (9-10 March 2009, Panama).

The budget is revised to incorporate the establishment and operation of the Programme Secretariat and include funds for regional technical support.

The present revision also takes into account the Policy Board recommendation to amend the title of Outcome 4. It also aligns the title of Outcome 1 with the UNFCCC process terminology, and uses “multiple” benefits instead of co-benefits in outcome 3 to emphasize the importance of ecosystem services, livelihoods and other socio-economic and environmental benefits that forests provide.

As stated in the original Global Joint Programme document, the programme outcomes aim to increase international confidence and understanding about the feasibility and options for including a REDD mechanism in a Post-Kyoto regime.  Specifically, by June 2010 the following outcomes will be achieved:

Outcome 1: Improved guidance on Measurement, Reporting and Verification (MRV) approaches (led by FAO)

Outcome 2: Increased engagement of stakeholders in the REDD agenda (led by UNEP)

Outcome 3: Improved analytical and technical framework of multiple benefits for REDD decision-makers (led by UNDP and UNEP)

Outcome 4: Increased knowledge management, coordination and communication (co-led by the three agencies) (title revised as recommended by the 1st Policy Board meeting)

3. Results Framework (for output 4.4)

### 3.1  Budget Revision at the Output Level

A revision is made at the output level under Outcome 4, with one additional output:

“UN-REDD Programme Secretariat established and operating.” The total amount of the revision for year 2009 is USD 2,888,415, including the portion for regional support. (See Table 2: Results Framework and Resource Allocation.)

### 3.2. Description of the Additional Output and Summary of Activities

As described in the Programme Framework Document of 20 June 2008, the UN-REDD Programme Secretariat serves the Policy Board, using the capacities of the participating UN organizations, research institutions and recognized experts. It seeks to ensure that strategies and operational guidance decided by the Policy Board are implemented and adhered to. The secretariat will manage the National Joint Programme review process. It will also manage the UN-REDD Programme’s overall monitoring and evaluation function which includes inter alia monitoring allocations to and delivery by the international support functions and country joint programmes, and tracking Programme-wide progress and ensuring that monitoring mechanisms are applied.

In addition, the Secretariat is the practical manifestation of the UN-REDD Programme – the entity with which other relevant initiatives and organizations can interact and work with.

### 3.3. Summary of Secretariat Activities

The Secretariat’s Terms of Reference were shared for information with the Policy Board at its first meeting. The Secretariat activities can be summarized as follows:

- Policy Board support

- Partnerships and external relations

- Quality assurance and oversight of national joint programmes

- Quality assurance and oversight of the International Support Functions described in the Global Joint Programme.

The Secretariat, coordinated by the participating UN Organizations Coordination Group, will work as an integrated inter-agency team, developing its own work plan and internal distribution of tasks.

Tables 1, 2 and 3 below describe the budget allocations, workplan and monitoring framework for the additional output 4.4 “UN-REDD Programme Secretariat established and operating”:

- Table 1: Results Framework and Resource Allocation, 2009

- Table 2: UN-REDD Programme – Global Programme - Work Plan for the additional Output 4.4.

- Table 3: Joint Programming Monitoring Framework (JPMF)

Table 1: Results Framework and Resource Allocation

| Outcome 4. Increased knowledge management, communication and coordination |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Additional Output | Participating UN organization-specific Outputs | Participating UN organization | Participating UN organization corporate priority | Implementing Partner | Indicative activities for each Output | Resource allocation and indicative time frame* |  |  |
|  |  |  |  |  |  | Category | Y1 | Total |
| 4.4 UN-REDD Programme Secretariat established and operating |  | FAO | Same as mentioned above against output 1.1 of the original document |  | Policy Board support Partnerships and external relations Quality assurance and oversight of national joint programmes Quality assurance and oversight of the International Support Functions described in the Global Joint Programme Monitoring and knowledge management | Personnel (Global support ) | Staff 389,400 | 550,467 |
|  |  |  |  |  |  |  | Consultants 62,067 |  |
|  |  |  |  |  |  |  | Travel 99,000 |  |
|  |  |  |  |  |  | Personnel (Regional Support) | 207,452 | 207,452 |
|  |  |  |  |  |  | Contracts |  |  |
|  |  |  |  |  |  | Training of Counterparts |  |  |
|  |  |  |  |  |  | Supplies |  |  |
|  |  |  |  |  |  | Other direct costs (misc) |  |  |
|  |  |  |  |  |  | Total programme cost | 757,919 | 757,919 |
|  |  |  |  |  |  | Indirect support cost | 53,054 | 53,054 |
|  |  |  |  |  |  | Total FAO | 810,973 | 810,973 |
|  |  | UNDP | Same as mentioned above against output 1.1 of the original document |  |  | Personnel (Global support ) | Staff 389,400 | 550,467 |
|  |  |  |  |  |  |  | Consultants 62,067 |  |
|  |  |  |  |  |  |  | Travel 99,000 |  |
|  |  |  |  |  |  | Personnel (Regional Support) | 311,177 | 311,177 |
|  |  |  |  |  |  | Contracts |  |  |
|  |  |  |  |  |  | Training of Counterparts |  |  |
|  |  |  |  |  |  | Supplies |  |  |
|  |  |  |  |  |  | Other direct costs (misc) |  |  |
|  |  |  |  |  |  | Total programme cost | 861,644 | 861,644 |
|  |  |  |  |  |  | Indirect support cost | 60,315 | 60,315 |
|  |  |  |  |  |  | Total UNDP | 921,959 | 921,959 |
|  |  | UNEP | Same as mentioned above against output 1.1 of the original document |  |  | Personnel (Global support ) | Staff 488,400 | 649,467 |
|  |  |  |  |  |  |  | Consultants 62,067 |  |
|  |  |  |  |  |  |  | Travel 99,000 |  |
|  |  |  |  |  |  | Personnel (Regional Support) | 103,724 | 103,724 |
|  |  |  |  |  |  | Contracts | 148,500 | 148,500 |
|  |  |  |  |  |  | Training of Counterparts |  |  |
|  |  |  |  |  |  | Supplies | 50,000 | 50,000 |
|  |  |  |  |  |  | Other direct costs (misc) | 128,200 | 128,200 |
|  |  |  |  |  |  | Total programme cost | 1,079,891 | 1,079,891 |
|  |  |  |  |  |  | Indirect support cost | 75,592 | 75,592 |
|  |  |  |  |  |  | Total UNEP | 1,155,483 | 1,155,483 |
|  | Grand Total |  |  | Programme cost |  |  |  | 2,699,454 |
|  |  |  |  | Indirect support cost |  |  |  | 188,961 |
|  |  |  |  | Total |  |  |  | 2,888,415 |

4. Work plans and budgets

The work plan and budget (table 3) of this Programme has been developed jointly by the three participating UN organizations. It details the activities of the new output 4.4. to be carried out within the UN-REDD programme, timeframes and planned inputs from the participating UN organizations as well as expected outcomes and outputs. A revised work plan and budget will be produced subsequent to the decisions of the annual/regular reviews.

Table 2. WORK PLAN for new Output 4.4. (UN-REDD Programme Secretariat and regional technical support)

| Outcome 4: By mid 2010, improved knowledge management, communication and coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | UN Org. |  | TIME FRAME |  |  |  |  |  | UN Org. | Resource and time frame* (US $) |  |  |  |  |  |
| JP Outputs |  | Indicative activities |  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 |  | Category |  | Y1 |  | Y2 | Total |
| New output 4.4 (a) UN-REDD Establishment and operation of the UN-REDD Programme Secretariat; (b) Regional technical support | (a1) Policy Board support |  | FAO |  | X | X |  | X |  |  | FAO | Personnel |  | 507,805 |  | 250,113 | 757,918 |
|  |  |  | UNDP |  | X | X |  | X |  |  |  | Contracts |  |  |  |  |  |
|  |  |  | UNEP |  | X | X |  | X |  |  |  | Training of Counterparts |  |  |  |  |  |
|  | (a2) Partnerships and external relations |  | FAO |  |  |  | X | X | X | X |  | Supplies |  |  |  |  |  |
|  |  |  | UNDP |  |  |  | X | X | X | X |  | Other direct costs (misc) |  |  |  |  |  |
|  |  |  | UNEP |  |  |  | X | X | X | X |  | Total |  | 507,805 |  | 250,113 | 757,918 |
|  | (a3) Quality assurance and oversight of national joint programmes |  | FAO |  |  | X | X | X | X | X | UNDP | Personnel |  | 577,301 |  | 284,342 | 861,644 |
|  |  |  | UNDP |  |  | X | X | X | X | X |  | Contracts |  |  |  |  |  |
|  |  |  | UNEP |  |  | X | X | X | X | X |  | Training of Counterparts |  |  |  |  |  |
|  | (a4) Quality assurance and oversight of the International Support Functions described in the Global Joint Programme |  | FAO |  |  | X | X | X | X | X |  | Supplies |  |  |  |  |  |
|  |  |  | UNDP |  |  | X | X | X | X | X |  | Other direct costs (misc) |  |  |  |  |  |
|  |  |  | UNEP |  |  | X | X | X | X | X |  | Total |  | 577,301 |  | 284,342 | 861,644 |
|  | (a5) Monitoring and knowledge management |  | FAO |  |  |  | X | X | X | X | UNEP | Personnel |  | 504,638 |  | 248,553 | 753,191 |
|  |  |  | UNDP |  |  |  | X | X | X | X |  | Contracts |  | 99,495 |  | 49,005 | 148,500 |
|  |  |  | UNEP |  |  |  | X | X | X | X |  | Training of Counterparts |  |  |  |  |  |
|  | (b1) Regional technical support provided (staff) |  | FAO |  |  |  |  | X | X | X |  | Supplies |  | 33,500 |  | 16,500 | 50,000 |
|  |  |  | UNDP |  |  | X | X | X | X | X |  | Other direct costs (misc) |  | 85,894 |  | 42,306 | 128,200 |
|  |  |  | UNEP |  |  |  | X | X | X | X |  | Total |  | 723,527 |  | 356,364 | 1,079,891 |
| Summary of Costs (US $) Output 4.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FAO |  |  |  | Programme Cost |  |  |  |  |  |  |  |  | 507,805 |  | 250,113 |  | 757,918 |
|  |  |  |  | Indirect Support Cost |  |  |  |  |  |  |  |  | 35,546 |  | 17,508 |  | 53,054 |
| UNDP |  |  |  | Programme Cost |  |  |  |  |  |  |  |  | 577,301 |  | 284,342 |  | 861,644 |
|  |  |  |  | Indirect Support Cost |  |  |  |  |  |  |  |  | 40,411 |  | 19,904 |  | 60,315 |
| UNEP |  |  |  | Programme Cost |  |  |  |  |  |  |  |  | 723,527 |  | 356,364 |  | 1,079,891 |
|  |  |  |  | Indirect Support Cost |  |  |  |  |  |  |  |  | 50,647 |  | 24,945 |  | 75,592 |
| Total |  |  |  | Programme Cost |  |  |  |  |  |  |  |  | 1,808,634 |  | 890,820 |  | 2,699,454 |
|  |  |  |  | Indirect Support Cost |  |  |  |  |  |  |  |  | 126,604 |  | 62,357 |  | 188,961 |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  | 1,935,238 |  | 953,177 |  | 2,888,415 |

Table 3. Joint Programming Monitoring Framework (JPMF)

| International Support Functions |  | Indicators | Means of Verification | Collection Method | Responsibilities (Lead Agency) | Risk and Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Expected Outcomes | Expected Outputs |  |  |  |  |  |
| 4. Increased knowledge management, communication and coordination |  |  |  |  | FAO, UNDP, UNEP |  |
|  | 4.4 Establishment and operation of the UN-REDD Programme Secretariat | - Successful Policy Board meetings - Effective support to the UNFCCC process - Effective oversight of the national and global programmes | - Website - Policy Board reports - Programme outputs | - Website hits and feedback - Reports - Programme products and services | UNEP, FAO and UNDP | Timely staffing of the secretariat and its timely outputs |

Note that all sections of the original signed Joint Programme Document apply to this budget revision.