STANDARD JOINT PROGRAMME DOCUMENT

Country: Indonesia

# 1. Cover Page

UNDAF Outcome(s):		OUTCOME 1:	Strengthening Human Development to Achieve the MDGs

OUTCOME 3:	Protecting the Vulnerable and Reducing Vulnerability

Programme Duration: 20 Months

Anticipated start/end dates: August 2009 – March 2011

Fund Management Option(s): pass-through

Managing or Administrative Agent: UNDP

Total estimated budget*:	USD 5,644,250

Out of which:

1. Funded Budget:		USD 5,644,250

2. Unfunded budget:		 	_____

* Total estimated budget includes both programme costs and indirect support costs

Sources of funded budget:

- Government	 	_________

- UN Org….		_________

- UN Org…		_________

- Norway (UN-REDD) 	USD 5,644,250

- Donor …		_________

- NGO…		 	_________

Names and signatures of national counterparts and participating UN Agencies

| UN Agencies | National Partners |
| --- | --- |
| …………. Signature FAO Date, Seal | ……… Signature Ministry of Forestry Date, Seal |
| …………. Signature UNDP Date, Seal |  |
| ……….. Signature UNEP Date, Seal |  |

# ACRONYMS

| AA | Administrative Agency |
| --- | --- |
| ADB AMAN | Asian Development Bank Aliansi Masyarakat Adat Nusantara (Indigenous People Alliance of the Archipelago) |
| BAPLAN | Badan Planologi (Division of Forest Planning) |
| BAPPENAS BD | Badan Perencanaan Pembangunan Nasional (National Development Planning Agency) Biodiversity |
| BLU | Badan Layanan Umum (Public Service Agency) |
| BMK | German Federal Ministry of Economic Cooperation and Development |
| BMKG | Indonesian Institute for Meteorology, Climatology and Geophysics |
| BMZ | German Ministry for International Cooperation |
| C | Carbon |
| CCB | Climate, Community & Biodiversity Standards |
| CDM CI CIFOR | Clean Development Mechanism Conservation International Center for International Forestry Research |
| CIMTROP | Centre for International Management of Tropical Peatlands |
| CKPP | Central Kalimantan Peatlands Project |
| CO2 | Carbon dioxide |
| CoP CSOs | Conference of the Parties Civil Society Organizations |
| DG | Directorate General |
| DGPLAN | Direktorat Jendral Planologi Kehutanan (Directorate General for Forest Planning) |
| DKN | Dewan Kehutanan Nasional (National Council on Forestry) |
| DNPI | Dewan Nasional Perubahan Iklim (National Council on Climate Change) |
| EU | European Union |
| FAO | Food and Agriculture Organization of the United Nations |
| FCPF FFI FKKM | Forest Carbon Partnership Facility Flora and Fauna International Forum Komunikasi Kehutanan Masyarakat (Communication Forum on Community Forestry). |
| FLEGT | Forest Law Enforcement, Governance and Trade |
| FMU | Forest Management Unit |
| FORDA | Forest Research and Development Agency |
| FRA | Forest Resources Assessment |
| FRIS FWI | Forest Resources Information System Forest Watch Indonesia |
| GEF | Global Environment Facility |
| GER | Global Eco-Rescue |
| GIS | Geographical Information System |
| GoI | Government of Indonesia |
| GoJ | Government of Japan |
| GoN | Government of Norway |
| GTZ HACT HKm HK HL HR HTR | German Technical Cooperation Agency UN Harmonized Advance Cash Transfer Hutan Kemasyarakatan (one of Indonesia’s community based forest management programmes) Hutan Konservasi (Conservation Forest) Hutan Lindung (Protected Forest) Hutan Rakyat (one of Indonesia’s community based forest management programmes) Hutan Tanaman Rakyat (one of Indonesia’s community based forest management programmes) |
| HPA | Hutan Produksi Alam (Natural Production Forest) |
| HPT | Hutan Produksi Terbatas (Limited Production Forest) |
| HTI HUMA ICEL | Hutan Tanaman Industri (Industrial Plantation Forest) Perkumpulan untuk Pembaharuan Hukum berbasis Masyarakat dan Ekologi (Community and Ecology Based Legal Reform Organization) Indonesian Center for Environmental Law |
| ICRAF | World Agroforestry Centre |
| IFCA IPs | Indonesian Forest Climate Alliance Indigenous Peoples |
| IPCC | Inter-Governmental Panel on Climate Change |
| ITC | International Training Centre |
| JICA | Japan International Cooperation Agency |
| JKPP JPD KARSA KDP-PNPM | Jaringan Kerja Pemetaan Partisipatif (Participatory Mapping Working Network) Joint Programming Document Lingkar Pembaharuan Pedesaan dan Agraria (Village and Agrarian Reforms Institute. Kecamatan Development Programme/Program Nasional Pemberdayaan Masyarakat |
| KfW | German Development Bank |
| KLH | Kementerian Lingkungan Hidup (Ministry of Environment) |
| KpSHK KPA KPH KSA LULUCF MoM | Kelompok Sistim Hutan Kerakyatan (Consortium for Supporting Community Based Forest System Management) Kawasan Pelestarian Alam (Nature Conservation Zone) Kesatuan Pemangkuan Hutan (Forest Management Unit) Kawasan Suaka Alam (Nature Reserve Zone) Land Use, Land Use Change and Forestry Minutes of Meeting |
| MRV | Measurement Assessment Reporting and Verification |
| MDG MDTF | Millennium Development Goal Multi-Donor Trust Fund |
| MoA MoE | Ministry of Agriculture Ministry of Environment |
| MoF | Ministry of Finance |
| MoFor | Ministry of Forestry |
| MoHA | Ministry of Home Affairs |
| MoTC | Ministry of Trade and Commerce |
| MOU | Memorandum of Understanding |
| MT | Megatonnes |
| NCAS NCASI | National Carbon Accounting System National Carbon Accounting System Indonesia |
| NFI NGOs NJP NPB | National Forest Inventory Non-governmental Organizations National Joint Programme National Project Board |
| NPD | National Project Director |
| NPM | National Project Manager |
| PEB | Project Executive Board |
| PES PHBM PHKA PMU PP | Payment for Ecosystem Services Pengelolaan Hutan Berbasis Masyarakat (Community Based Forest Management)- (one of Indonesia’s community based forest management programmes Perlindungan Hutan dan Konservasi Alam (Forest Protection and Nature Conservation) Programme Management Unit Peraturan Pemerintah (Government Regulations) |
| PSP | Permanent Sample Plot |
| PU | Departemen Pekerjaan Umum (Ministry of Public works) |
| REDD | Reducing Emissions from Deforestation and Forest Degradation |
| REL RLPS | Reference Emissions Level Rehabilitasi Lahan dan Perhutanan Sosial (Land Rehabilitation and Social Forestry) |
| RMU | PT Rimba Makmur Utama |
| R-PIN | REDD Project Idea Note |
| R-PLAN RTRWP | REDD Plan Rencana Tata Ruang Wilayah Propinsi (Provincial Level Spatial Planning) |
| RS RUPES | Remote Sensing Rewarding Upland Poor for Environmental Services |
| SFM | Sustainable Forest Management |
| STORMA SSA | Stabilization of Tropical Rainforest Margins project Special Service Agreement |
| TA TB | Technical Assistance Taman Buru (Game Reserve Park)) |
| TGHK ToR | Tata Guna Hutan Kesepakatan (Consulted Forest Planning) Term of Reference |
| TNC | The Nature Conservancy |
| UN UNDAF UNDG Excom | United Nations United Nations Development Assistant Framework United Nations Development Group Executive Committee |
| UNDP UNDP CO | United Nations Development Programme United Nations Development Programme Country Office |
| UNEP | United Nations Environment Programme |
| UNFCCC UNRC | United Nations Framework Convention on Climate Change United Nations Resident Coordinator |
| UN-REDD | United Nations Collaborative Programme on Reducing Emissions from Deforestation and Forest Degradation in Developing Countries |
| USD | US dollars |
| WB | World Bank |
| WRI WWF | World Resources Institute World Wildlife Fund |

# Table of Contents

1. Cover Page	1

ACRONYMS	2

Table of Contents	5

2. Executive Summary	6

3. Situation Analysis	8

4. Strategies including lessons learned and the proposed Joint Programme	12

5. Results Framework	17

6. Management and Coordination Arrangements	37

UNREDD NJP Programme Structure	40

7.  Execution modality and Fund Management Arrangements	41

8. Monitoring, Evaluation and Reporting	42

9. Legal Context or Basis of Relationship	48

11. Harmonized Annual Work Plan 2009	50

Annex 1 – Response to the UNREDD Secretariat Note	60

Annex 2 – CSO Consultation	61

Annex 3 – Legal Context UNDP	67

Annex 4 – Supplemental Provisions	68

# 2. Executive Summary

In September 2008, the global United Nations Collaborative Programme on Reducing Emissions from Deforestation and Forest Degradation in Developing Countries  (UN-REDD Programme) was launched aiming to assist tropical forest countries in establishing a fair, equitable and transparent REDD regime. Indonesia is one of the nine pilot countries for the initial phase. This will be funded by the Government of Norway as part of Norway’s International Climate and Forest Initiative which was announced during the UNFCCC conference at Bali in 2007.

The proposed National Joint Programme (NJP) aims to support the Government of Indonesia (GoI) to timely develop a REDD architecture that will allow a fair, equitable and transparent REDD implementation significantly contributing to a sustainable reduction of forestry related greenhouse gas emissions

Multi-stakeholder participation in REDD is of critical importance to REDD readiness. Recognizing the importance to do so, the government initially has been working through the IFCA multi-stakeholder alliance. IFCA organized and streamlined stakeholder input. Amongst others, this resulted in an initial outline of what was called a REDD supply chain. Furthermore, subject matter related analyses were conducted which fed into a final consolidation report that has formed the foundation for Indonesia’s National REDD strategy. Recently, the Ministry of Forestry has issued a Ministerial Decrees No. 30/2009 and No. 36/2009 on REDD regulation. The Decrees were issued after various in-depth multi-stakeholder consultations on REDD regulations.

The multi-stakeholder consultation process also includes people and local communities potentially affected by REDD, and UN-REDD is keenly aware of the concerns raised by local communities and Civil Society Organizations (CSOs) of an emerging REDD scheme in Indonesia. On 20 May 2009, an in-depth stakeholder consultation with Indigenous Peoples (IPs) representatives and CSOs was conducted as part of the development of the UN-REDD Programme. Inputs from the consultations have been used to refine the proposal and will guide later implementation.

Provincial and district governments are developing policies and have shown interest in developing REDD as an effort to strengthen forest development in their area. While these initiatives need support, better communication between district, province and central government is essential to make REDD successful in the longer term.

The Objective of the UN-REDD Indonesia Programme is “to support the GoI in attaining REDD-Readiness”. In order to secure this Objective, three Outcomes with subsequent outputs and activities will be pursued:

Outcome 1: Strengthened multi-stakeholder participation and consensus at national level

Output 1.1 (UNDP):	Consensus on key issues for national REDD policy development

Output 1.2 (UNDP):	REDD lessons learned

Output 1.3 (UNEP):	Communications Programme

Outcome 2 Successful demonstration of establishing a REL, MRV and fair payment systems based on the national REDD architecture

Output 2.1 (FAO):	Improved capacity and methodology design for forest carbon inventory within a Measurement, Reporting and Verification System (MRV), including sub-national pilot implementation

Output 2.2 (FAO):	Reference Emissions Level (REL)

Output 2.3 (UNDP):	Harmonized fair and equitable payment mechanism at provincial level

Output 2.4 (UNEP):	Toolkit for priority setting towards maximizing potential Carbon-benefits and incorporating co-benefits, such as biodiversity conservation and poverty alleviation under MDG

Outcome 3: Capacity established to implement REDD at decentralized levels

Output 3.1 (UNDP):	Capacity for spatial socio-economic planning incorporating REDD at the district level

Output 3.2 (UNDP):	Empowered local stakeholders are able to benefit from REDD

Output 3.3 (UNDP):	Multi-stakeholder-endorsed District plans for REDD implementation

# 3. Situation Analysis

- Background

Forest resources in many developing countries play important roles in national economic development as well as source of income and other customary uses for local people. In the context of global climate change, forests play an integral role in mitigating climate change. Not only are they one of the most important carbon sinks, storing more carbon than both the atmosphere and the world's oil reserves, but they also constantly remove carbon from the atmosphere through photosynthesis, which converts atmospheric carbon to organic matter. While forests are working diligently to clean up the carbon, people have emitted carbon to the atmosphere through burning fossil fuels, pumping carbon right back into the atmosphere through deforestation. According to IPCC, deforestation and forest degradation in developing countries account for about 20% of global carbon emission. Significant emission reduction could be made, however, if appropriate compensation mechanisms can be created.

Indonesia is a country with forest land about 60 % of the country area, the third largest forest area under tropical rainforest in the world. Indonesia’s forest is important not only for national economy development and livelihood of local people, but also for global environment. Indonesia is the home of mega diversity and one of the custodians of the world tropical peat land.

Indonesia put a high interest on the issue of climate change including REDD since Indonesia is an island country. The combination of high population density and high levels of biodiversity, together with a staggering 80,000 kilometers of coastline and 17,500 islands, makes Indonesia one of the most vulnerable countries to the impacts of climate change. The devastating impact of global warming is already evident in Indonesia and the effects will be felt more acutely by the poorest people, who are living in the most marginal areas or surrounding forest that are vulnerable to drought, for example, or to floods and landslide. Developed countries are responsible for the majority of greenhouse gas emissions which cause global warming

Indonesia is currently facing the challenge of deforestation and forest degradation. Most recent estimates based on satellite Landsat 7 ETM+ imageries issued by GoI indicated that between 2003 and 2006, deforestation was around 1.17 million ha per year.  Accurate estimates of the magnitude of forest degradation do not exist.

Indonesia has developed measures to tackle illegal logging and initiated a program to rehabilitate degraded areas. Other efforts on sustainable forest management, rehabilitation of degraded forest and non-forest land, and protected area management, campaigning one million planting trees, one man one tree are examples of several efforts to show the seriousness of the government to tackle climate change related issues. The Indonesian Forest Carbon Alliance (IFCA) team, under the leadership of the Ministry of Forestry, sought to build on these foundations to create a credible system to generate REDD revenue by reducing Indonesia’s deforestation rate. Developing REDD Readiness and demonstration activities will provide this proof-of-concept work to support a viable market in carbon credits for avoided deforestation in the post 2012. Regulation on implementation of REDD mechanism has been developed to support these initiatives.

All of these could contribute positively in reducing global emission and restoration of other global environmental function. But, with the wide forest coverage and its complex problems, under this business as usual activities, Indonesia is hard to achieve the REDD Readiness by 2012. While progress is being made, it needs to be emphasized that most of these initiatives are still in their early stages of development. It is strongly recommended by forest communities that Indonesia has to make more efforts to enhance the current forestry business to be REDD Ready.

B. REDD Indonesia Institutional setting

Indonesia has a range of policies and programs that are of direct relevance to the REDD. First, it is important to acknowledge that Indonesia has ratified: the Ramsar Convention; the UN Convention on Biological Diversity; the UNFCCC; and the Kyoto Protocol. The Ministry of Environment (MoE) is the key agency in developing environmental policies in Indonesia, including policies related to climate change. The DNPI leads Indonesia’s negotiations in the UNFCCC (MoE was a focal point for the climate change negotiation in Indonesia). Second, the Ministry of Forestry (MoFor) has so far pro-actively driven REDD process in Indonesia, starting with the establishment of the IFCA in 2007 to conduct initial steps in REDD Readiness. Since 2008, The Ministry of Forestry has issued four National Regulations on Reducing Emissions from Deforestation and Degradation in order to guide implementation of national REDD policy. Some programs related to REDD preparation are ongoing such as developing Indonesia NCAS and FRIS program.  FRIS will be the basis for monitoring, assessment and reporting for REDD and GHG. It will also include a REDD registry to list REDD related operations and for serving payment mechanism.  Other programs to support REDD indirectly, particularly to carbon measurement are developed in the MoFor through various projects. For examples, collaboration between the MoFor (PHKA, RLPS, FORDA) and ICRAF under a Rewarding the Upland Poor for Environmental Services (RUPES) project, REDD ALERT project, and other activities under KPH system development and Timber Legality Assurance System (TLAS).

Since COP13, the increased complexity and significant anticipated benefits and economic changes initiated by REDD triggered increased involvement of other institutions, including BAPPENAS, Ministry of Finance, Ministry of Environment, Ministry of Public Works, Ministry of Home Affair, Ministry of Agriculture, The Coordinating Ministry of Economic Affairs, and Provincial and District Government. The National Council on Climate Change is the umbrella institution to coordinate the institutions. The national institutions responsible to develop REDD related policies and program based on their sectoral mandates whereas some provincial and district governments are in the process of initiating demonstration activities.   Indonesia has adopted an approach to REDD implementation characterized as a “national approach with sub-national implementation”.

Through the IFCA process, a multi-stakeholder alliance, established and managed by the Forestry Research and Development Agency (FORDA) and supported by the World Bank, has conducted a series of important studies on different aspects of REDD organized through working groups. By the time of COP 13 in December 2007 each of the working groups had developed technical papers which were supported by a structured program of consultations with principal stakeholders from the Ministry of Forestry (MoFor), national and international NGO’s and forest industry groups.

The Ministry of Forestry (MoFor) has the responsibility to manage the nation’s forest which is currently in the order of 120.35 million ha or 64.08% of the land surface.  To guide implementation of national REDD policy, the Ministry of Forestry has recently initiated the following four decisions:

- Ministerial Regulation P.68/Menhut-II/2008 which provides an umbrella for voluntary REDD initiatives and demonstration pilot projects currently under implementation or being developed. (December 2008)

- Ministerial Decision SK. 13/Menhut-II/2009 which establishes a Climate Change Working Group within the Ministry of Forestry (MoFor) (January 2009). The Climate Change Working Group aims to develop initiatives to deal with issues related to climate change including REDD. The group comprises all Directorat Generals (DG)s within the Ministry.

- Ministerial Regulation P. 30/Menhut-II/2009 which provides mechanisms to reduce carbon emissions from deforestation and forest degradation  (May 1, 2009)

- Ministerial Regulation P. 36/Menhut-II/2009 which provides a framework for issuing licenses for carbon utilization in production and protection forests (May 22, 2009).

Within MoFor, Directorat General of Forest Plan (DGPlan) is responsible for the Forest Resource Inventory System (FRIS) which is integrated into the National Carbon Accounting System (NCAS). NCAS, which monitors all terrestrial carbon, is an integrated effort to measure all green house gas emissions related to terrestrial carbon. NCAS is a fully integrated Carbon Accounting Model (CAM) for estimating and predicting all, wall to wall, biomass, litter and soil carbon pools in forests and agricultural systems. In addition to this, it accounts for changes in other major greenhouse gasses such as nitrogen oxides through monitoring of the nitrogen cycle and human-induced land use practices. FRIS will be the basis for monitoring, assessment and reporting for REDD and Green House Gas (GHG), as far as these concern the forests managed by the ministry of forestry. It will also include a REDD registry to list REDD related operations and for serving payment mechanisms.

Other programs indirectly related to support REDD, particularly to carbon measurement are developed in the MoFor through various projects. For examples, collaboration between the MoFor (PHKA, RLPS, FORDA) and ICRAF under a Rewarding the Upland Poor for Environmental Services (RUPES) project, REDD ALERT project, and other activities under KPH system development and Timber Legality Assurance System (TLAS).

Furthermore, the MoFor, with financial and technical support from Australia, Germany, the UK, and the World Bank is currently developing demonstration activities for testing and triggering a global REDD mechanism. In June 2008, Indonesia and Australia agreed to develop a Roadmap for Access to International Carbon Market.

Since COP13, the increased complexity and significant anticipated benefits and economic changes initiated by REDD triggered increased involvement of other institutions, including:

- The National Development Planning Agency (Badan Perencanaan Pembangunan Nasional- BAPPENAS): BAPPENAS is responsible for overall development coordination which includes the management of financial/technical assistance from Development Partners. BAPPENAS coordinates the implementation of bilateral and multilateral aid projects which includes cooperation projects with Australia and Germany. BAPPENAS contributes  through the following initiatives:

  - BAPPENAS is working on the establishment of a climate change multi donor trust fund intended to support climate change related initiatives. This could potentially include REDD.

  - BAPPENAS has initiated project ideas, presented in the national development response to climate change, also known as the Yellow Book.

  - The possible development and management of a mechanism through which REDD credits are being traded is seen as a potential responsibility of BAPPENAS in collaboration with the Ministry of Finance.

- The Ministry of Environment (Kementerian Lingkungan Hidup- KLH), until the establishment of the National Council on Climate Change (Dewan Nasional Perubahan Iklim-DNPI), served as the focal point for the United Nations Framework Convention on Climate Change (UNFCCC). KLH is responsible for developing and overseeing national policies on environmental management issues.

- Ministry of Finance (MoF): MoF is responsible for the design and implementation of payment mechanisms, including sharing of REDD generated revenues. One of the possible options to manage REDD finances is the establishment of a Public Service Agency (BLU). MoF is instrumental in the establishment and management of these institutions which will report to the Minister. Furthermore, MoF has established a task force for developing fiscal policies relevant to climate change.

- The National Council on Climate Change (DNPI): The DNPI was established in 2008 through a Presidential Decree, meaning that the DNPI reports its activity directly to the President. It has been given significant authority to advise and oversee implementation of both climate change adaptation and mitigation policies. DNPI has become the UNFCCC focal point. The DNPI comprises of six working groups to deal with issues of adaptation, mitigation, technology transfer, finance, forestry and post-Kyoto mechanisms.

- Ministry of Public works (Pekerjaan Umum- PU): Its Directorate General for Spatial Planning is responsible for spatial planning and oversees the implementation of law 26/2007, a spatial planning law.

- Ministry of Home Affairs (MoHA) is responsible for overseeing decentralization and provides overall guidance to the districts with regards to the spatial – and economic development planning. Engagement with MoHA on REDD is thus of significant importance, but still very limited.

- Ministry of Agriculture is responsible in managing estate crops (such as rubber, palm oil, and other estate crops) and forested land outside of state owned forests.

- The Coordinating Ministry of Economic Affairs develops and oversees economic development. It is responsible for mainstreaming climate change into general development policies. The ministry has been instructed by the president through Presidential Instruction 5/2008, which also instructs MoFor and KLH, to issue timely REDD regulations.

- Provincial and District Government:

Based on Forestry Law No. 41/1999 and its revise Law No. 19/2004, forest and forest  related issues are the responsibility of the Ministry of Forestry, but with significant management responsibilities at the local level except management of forest for conservation purposes. Management of conservation forest is under the responsibility of the central government.  According to the Laws, the minimum forest cover that should be maintained of the total area of a watershed is 30%. The Law also mentioned that islands, provinces, districts or watersheds should have a minimum forest cover of 30% of the total land area and the forest area. The forest area is defined by the government based on biophysical conditions, climate, population and socio-economic conditions of the community within the region it is residing. This has been supported by Law 26/2007 on Spatial Planning which gives mandate to each district to be responsible for their district spatial plans. The law  mentions that at least 30% of each district area should be vegetated by trees.

Tata Guna Hutan Kesepakatan -TGHK (consulted forest planning) of a region represents implementation of the forest law No. 41/1999. Some problems often occure in the implementation of the TGHK on the field.  Spatial plans issued by local government and TGHK are often conflicting. In some of the most forested provinces, such as Central Kalimantan, these conflicts are significant. To solve this issue, there is a process to align which is called Paduserasi and has proven to be challenging.

In some cases, conflict of spatial planning and TGHK can provide significant opportunities for REDD development in forested areas outside the forest area managed by MoFor. For example, Law 26/2007 covers spatial planning of coastal zones, which provides to the possibility of REDD incentives to avoid the clearing of mangrove forests (relatively carbon intensive). As such, a robust policy framework could be put in place to integrate REDD into spatial planning at national and local levels for forested areas outside the forest area. Furthermore, the development of cross-cutting policies on climate adaptation in spatial plans can integrate climate adaptation into the development of sectoral policies and make the policies climate change resilient.

While waiting for a guideline of national REDD mechanism, some provinces are in the process of establishing REDD working groups. In Aceh this is facilitated through Green Aceh. In Papua, the government is actively pursuing REDD and is in the process of developing a REDD policy which is well embedded and linked into a national programme. Outside Aceh and Papua, commitment on REDD has been shown by some districts such as Berau District, Malinau District, both in the East Kalimantan Province. The Berau district collaborates with MoFor and TNC on developing large scale REDD demonstration activities. Some REDD working groups have been also established in Central and East Kalimantan. For an example, Kemitraan, a national NGO, is working at district level in Siak, Riau Province. However, so far these REDD working groups have not been officially enacted.

# 4. Strategies including lessons learned and the proposed Joint Programme

- REDD related initiatives

IFCA: As mentioned above, in July 2007, Indonesia formed the IFCA, a forum for stakeholder communication, coordination, and consultation on REDD related issues, including progress and outputs of the studies on REDD methodologies, strategy, financial/market analysis and incentive distributions. The IFCA studies undertaken in 2007 resulted in the following recommendations: (1) build on the initial framework designed by IFCA, (2) continue consultations and technical analysis, (3) test and implement pilot/demonstration activities with heterogeneous conditions, (4) conduct capacity building at all levels, (5) create a credible national framework for verifiable emission reductions, and (6) deliver real reductions in GHG emissions. In order to follow up on the outcomes of the IFCA studies in 2007, the COP-13 Decision and implement the REDDI Road Map, the REDDI Framework was set up. Recently, this has been elaborated and resulted in the National REDD Strategy as summarized in table 1.

Minister of Forestry’s Regulations and Decisions: In 2008, the Minister of Forestry issued a regulation on the implementation of REDD demonstration activities (PERMENHUT No. P. 68/Menhut-II/2008). The aim of the implementation of demonstration activities is to test and develop methodologies, technology and institution of sustainable forest management that endeavor to reduce carbon emissions by addressing deforestation and forest degradation and also as an umbrella regulation for some REDD demonstration activities that are currently initiated by some institutions. In 2009, a Decree on establishing the Ministry of Forestry Working Group on Climate Change/WG-FCC (SK.13/Menhut-II/2009) was issued. The working group is responsible to provide inputs to the Ministry of Forestry on policies and issues that have to be solved related to climate change including REDD. In March 2009, the Ministry of Forestry issued two other regulations on REDD implementation (PERMENHUT No. P30/Menhut-II/2009 and PERMENHUT No. P36/Menhut-II/2009). These Permenhuts provide guidance on implementation of both for fund and voluntary based REDD Indonesia programs.

Bilateral Cooperation: The Government of Indonesia and German Government (BMZ, implemented by KfW/GTZ): This project tentatively aims to support “The implementation of strategies for forest conservation and sustainable forest management resulting in reduced GHG emissions from the forest sector and improved living conditions of the rural population”. The project will be working in 2 to 4 districts in Kalimantan, mostly located in what is called the “Heart of Borneo” which encompasses the provinces of East and West Kalimantan. The project focuses on a district implementation model.

The Government of Indonesia and AusAID: AusAID has initiated the “International Forest and Climate Partnership”. The partnership encompasses the following key areas:

  - Policy development and capacity building to support participation in relevant international negotiations and future carbon markets;

  - Technical support for Indonesia to develop its national forest carbon accounting and monitoring system; and

  - Development of large-scale project based demonstration activities, and the provision of related enabling assistance, to trial approaches to REDD. This includes the Kalimantan forest and carbon partnership and a second demonstration project in early development.

Multilateral Cooperation: The Government of Indonesia and World Bank (WB): the WB support is moving from technical assistance towards financing. Together with FORDA, the Bank played a key role in coordinating IFCA which was perceived as successful. Indonesia participates in the Forest and Carbon Partnership Facility (FCPF) and therefore is eligible for readiness support. Beyond the readiness process, the WB foresees that the Forest Investment Program (FIP) could be a key vehicle in supporting REDD in Indonesia. The forestry investments may support sectoral restructuring programs such as re-allocating planned palm oil development from peat land soils to mineral soils, closure of saw mills/plywood mills, developing alternative employment for households depending on timber processing facilities etc.

Table 1.  Summary of REDD Indonesia Strategy (draft May 2009)

| LEVEL / category | Key Strategy Component |
| --- | --- |
| NATIONAL LEVEL |  |
| - Tackling drivers of deforestation and degradation | - Protected area: Develop more effective conservation and management of Protected Areas - Production Forest : i) Develop more effective management of Production Forests, ii) Options for forest harvesting and management to supply the requirements of pulp and paper industry - Oil Palm: Options for supplying the requirements of the oil palm industry - Peat land: Testing strategies for restoration of peat lands |
| - REDD regulation | - Development of technical and institutional guidance to implement REDD - Establishment of National REDD Committee/REDD National Working Group |
| - Methodology | - Establishment of REL at the national level - Establishment of MRV system at national level |
| - Institution | - Establishment of National Registry - Institutional setting to implement REDD - Setting incentive/payment distribution mechanism - Stakeholder communications / coordination/ consultations - Capacity building and institutional strengthening |
| PROVINCIAL LEVEL |  |
| - Methodology | - Establishment of REL at provincial level (shall be consistent with national REL) - Establishment of MRV system at provincial level |
| - Institution | - Stakeholders communication/ coordination/ consultations - Capacity building and institutional strengthening |
| - Demonstration Activities (DA) | - Enhance DA to represent different bio-socio-geographical conditions at 28 provinces (existing at 4 provinces : East Kalimantan, Central Kalimantan, South Sumatera and East Java) - Enhance capacity of local communities, including adat communities to engage in forest management through REDD activities. |
| DISTRICT LEVEL |  |
| - Methodology | - Establishment of REL at district level (shall be consistent with provincial and national REDD) - Establishment of district level MRV system |
| - Institution | - Stakeholder communications/ coordination/ consultations - Capacity building and institutional strengthening |
| - Demonstration Activities (DA) | - Implement Demonstration Activities at district level or management unit (with bundling to district level wherever possible) - Enhance capacity of communities, including adat communities to engage in forest management through REDD activities |
| ALL LEVELS |  |
| Relevant analysis | - Analyze costs of alternative land uses - Analyze environmental and socio-economic impacts of REDD - Evaluate potential additional benefits of REDD - Assess trade-offs and risks of REDD to sustainable development - Assess risks of the REDDI strategy |

Cooperation with Private Sector: Concern on REDD implementation has been given also by some privates and NGOs in a form of developing voluntary based REDD demo activities. Examples for this may be found from the work of Papua Province with an Australia basedvoluntary market company, initiatives of PT Rimba Makmur at Central Kalimantan, PT Global Eco Rescue at Malinau District, East Kalimantan; the work of The Nature Conservancy at Berau District, East Kalimantan, an initiative of North Sulawesi provincial government with Carbon Storage Global PTE Limited, and WWF projects at Kampar Peninsula and Sebangau.

All the above initiatives provide lessons for future REDD interventions in Indonesia. While waiting for results of international negotiation of the REDD mechanism, the government of Indonesia is developing legal aspects to accommodate the above initiatives.

- Needs analysis

To allow UN REDD to properly position itself in its efforts to facilitate technical and financial support for REDD in Indonesia, a Needs Analysis was prepared in December 2008 – January 2009, identifying gaps which would potentially constrain Indonesia to be REDD ready by 2012. This Needs Analysis was based on inputs from key REDD stakeholders and emphasized on issues of the REDD readiness steps criteria as defined by the World Bank forest and carbon facility. The reason to use these readiness criteria is that these are generally accepted by key actors and have been used by countries to design their readiness matrices.

The identified needs were as follows:

- Need to clarify institutional setting .

- There is a need for institutional clarity both vertically and horizontally, the lack of which creates uncertainty in project/demonstration site development.

- There is need for clarity on the regulatory framework, with some institutional mandates overlapping

- There is lack of clarity on the responsibilities of different levels of government (district/province/national) with respect to REDD.

  - Need for standards and database, which necessitates:

- Development of standards with emphasis on baseline methodology, monitoring and verification , what does this entail (with reference to voluntary market projects)

- Development of a register of ongoing projects both through multilateral/bilateral assistance as well as through voluntary market schemes

  - Improved  coordination / communication

- Limited engagement with the non forestry ministries

- Continuing issues such as: forest tenure, forest/wood processing industry restructuring, fires, illegal logging

  - Need for coherent payment scheme(s)

- It is necessary to develop a payment system to streamline activities and bring into one consistent approach. Who is getting what? And who is going to pay?

  - Need for promotion of co-benefits, such as poverty alleviation, biodiversity conservation and water supply

  - Need for analysis of REDD related investment strategies

- Possibilities have been identified for immediate both public and private sector investments between now and 2012

  - Need to anticipate actions beyond Readiness

- purchase credits from demonstration activities

- address permanence and leakage.

- Current Status:

- Rapid expansion of estate crops during the commodity boom in between 1998-2008 led to encroachment upon forest areas. Work conducted by ICRAF showed that this could be reversed through environmental service payments. In Sulawesi the STORMA project showed that agriculture / crops cultivation led to major changes in land use and indigenous tenure arrangements, which led to large scale forest encroachment. These dynamics show that financial returns from REDD need to be able to compete with alternative land uses.

- The Government has taken active and comprehensive steps against illegal logging resulting in significant reduced logging. Top level commitment to combat illegal logging has resulted in more frequent and effective policing action.

- Emerging environmental service payment schemes in Indonesia have shown that this type of mechanism could deliver lasting reduction of threats to natural resources. To date, only a few schemes are being implemented, but interest is increasing and initial results are promising. ICRAF has conducted work on a reverse auction mechanism to deliver environmental services. Results of the work showed that farmers commit to community based forestry schemes (“Hutan Kemasyarakatan”, HKm, Hutan Tanaman Rakyat-HTR, Hutan Rakyat-HR, Pengelolaan Hutan Berbasis Masyarakat-PHBM) where communities have secured access to forest use. Under HKm, forest loss decreases while agroforest areas increase. Deforestation is not completely eliminated, but after 2000 (when HKm was launched) deforestation reached the lowest level since 1973. This is further underlined by experiences in other parts of Indonesia where initial results seem to be promising. Recent revisions in the forestry law allow for environmental services permits to be released.

- The issuance of the first eco-restoration license (Harapan forest) by the Ministry of Forestry to a Birdlife led consortium. This high profile project aims to protect endangered species by setting up an endowment fund. The targeted area is around 104,000 ha.

- Community based carbon monitoring efforts have proven to empower communities to better understand the value of forests. Initial results have led to positive feed back

- A Community peatland monitoring event held in Bogor by KpSHK has shown high awareness of local peatland communities regarding the importance of peatland forest.

- The Proposed Joint Programme:

The proposed National Joint Programme (NJP) aims to support the Government of Indonesia (GoI) to timely develop a REDD architecture that will allow a fair, equitable and transparent REDD implementation significantly contributing to a sustainable reduction of forestry related greenhouse gas emissions. The NJP will be guided by and supportive to the National REDD strategy.

In line with the participating UN Agencies’ mandates, the UN-REDD strategy aims to support development of an Indonesian REDD architecture which is inclusive and addresses the key challenges described above. It will support the Government of Indonesia in developing an equitable and transparent REDD mechanism through:

- Working on strengthening multi-stakeholder involvement at national and sub national levels while aligning sub national process to the national level,

- Work on harmonizing the REDD supply chain with an emphasis on Reference Emission Level setting, Measurement Verification and Reporting (MRV) and principles/standards for payment entitlement and;

- Build capacity within various agencies and stakeholders towards REDD implementation

The Objectives and Outputs of the Programme are laid out in Section 5.

- Project feasibility

During the design of the project, the following two assumptions were deemed critical for the feasibility of the programme:

- GOI political commitment to REDD and a clear need for UN-REDD involvement

- Wide spread stakeholder support for UN-REDD

The above were addressed through numerous meetings with various stakeholders and coordination meetings with multilateral agencies (World Bank, Asian Development Bank) and bilateral agencies.

Apart from the Ministry of Forestry, this programme is supported by various Government agencies including the National Council on Climate Change, which is the focal point for UNFCC negotiations. Indonesia has made key policy commitments to REDD through its high level political support for the Bali roadmap. The Ministry of Forestry has clearly expressed its interests in working on REDD and has identified key issues which require support. This has been cemented at the national level through the IFCA process and other bilateral initiatives. UN-REDD as such is institutionally well embedded and is part of broader effort to develop REDD in Indonesia which is strengthened by high level political support.

The project outcomes, particularly spatial planning, will strengthen Ministry of Forestry capacity. It is in line with the MoFor policy to sustain forests and its management such as the on-going KPH development program.

Furthermore, UN-REDD addresses several key gaps in REDD development in Indonesia which have been defined through multi-stakeholder involvement, including government agencies, donors and civil society organizations. Thus, the Indonesian UN REDD programme is building on strong stakeholder commitment and designed to meet the needs of key actor involved in rolling out REDD.

- Sustainability of Results

Building upon GOI identified needs and well designed implementation, UN-REDD expected results are likely to be sustained The emphasis on broad based stakeholder engagement is a key element of the sustainability strategy.

If COP 15 includes REDD and Indonesia moves towards a national approach with sub-national implementation, then UN-REDD contributes to the development an effective, fair and equitable national REDD architecture. UN-REDD outputs emphasize broadening support for REDD at sub-national levels, harmonizing benefit sharing and ensuring capacity exists to implement REDD by 2012.

# 5. Results Framework

The Objective of the UN-REDD Indonesia Programme is “to support the GoI in attaining REDD-Readiness”

In order to secure this Objective, three Outcomes with respective outputs and activities will be pursued. The outcomes are intended to strengthen stakeholders at national level (outcome 1), provincial level (outcome 2) and district level (outcome 3). The outcomes are designed to strengthen stakeholders at both vertical and horizontal levels, from national to grass root levels and vice versa.  It is designed also to provide linkages between national, provincial and district level for technical implementation of REDD.

Outcome 1: Strengthened multi-stakeholder participation and consensus at national level

This Outcome is particularly focused on securing consensus on key issues related to REDD at the national level, particularly among the governmental stakeholders, but also ensuring participation of civil society organizations. The intended Outputs are as follows:

Output 1.1 (UNDP):  Consensus on key issues for national REDD policy development

The process will be based on the work done by IFCA and will be closely aligned with the DNPI LULUCF Working Group and the MoFor Climate Change Working Group. It will encompass engagement with stakeholders at provincial level. Five provinces are initially targeted which are Aceh, Jambi, Central Kalimantan, Central Sulawesi, and Papua. Indicative activities include:

    - UN REDD Programme Management Unit facilitating multi-stakeholder activities

    - National and sub-national consultations on key-issues

    - Analyze key issues focusing on those related to REL

    - Facilitate inter-ministerial round table discussions on identified issues

    - Prepare policy recommendations & develop roadmap for issuing policies to address these issues

Output 1.2 (UNDP): REDD lessons learned

UN-REDD will support on-going REDD initiatives undertaken by NGO’s, the private sector, and bilateral partners, by establishing a learning mechanism.  Small grants will be mobilized to assist these existing initiatives by IP organizations and CSOs to analyze lessons learned to date, and report them using a harmonized approach to permit further analysis at the national level and reporting to all stakeholders.  These lessons, together with the IFCA studies, will also be used to inform the international negotiation process on REDD. Indicative activities include:

    - Establish national knowledge & learning network

    - Collaborate with relevant projects to stimulate coordination and joint learning (incl Small Grants Programme)

    - Organize joint workshops

    - Prepare publication on lessons learned

Output 1.3 (UNEP): Communications Programme

REDD requires understanding commitment and involvement from a diverse group of stakeholders, ranging from local communities and indigenous groups, the general public, to government officials and parliaments. Currently, the knowledge on REDD is still very limited and the interpretation of what REDD can bring in terms of benefits but also responsibilities is still very diverse. Therefore, a common understanding needs to be built to expedite the process of readiness for REDD and to allow stakeholders to keep abreast of REDD related developments such as new legislation and planned projects.

REDD readiness in Indonesia needs additional investments in creating an enabling environment towards real change in reducing deforestation. This applies to both national political levels where policies such as expansion of oil palm would be competing with objectives of REDD, as well as at local district level where decisions have to be made with regard to changing the status of local forest lands or halting forest exploitation in favor of conserving those carbon resources.

Social marketing will work along the lines of providing strategic information, creating the knowledge and understanding, and as a result the willingness to change, e.g. towards significantly improved national policy decisions. The social marketing envisioned for the UN-REDD would use a range of communications and marketing techniques along with training and education to achieve specific and measurable behavioral changes with decision and policy makers at provincial and national levels, as well as local stakeholder groups at field level. Indicative activities include:

    - Identify on target messages, target groups and national partners

    - Design awareness impact monitoring system, and assessing impact at completion

    - Design social marketing campaign, focusing on high level government decision makers, as well as local resource users in the pilot districts

    - Develop REDD information, education and communication materials

    - Conduct national communications campaign, targeting one or two drivers of deforestation (incl. high-level GoI - UN conference or panel in Jakarta)

    - Conduct training on REDD – with emphasis on local level actors

Outcome 2 Demonstration of establishing a REL, MRV and fair payment systems based on the national REDD architecture

This Outcome will include analytical work on a number of key elements for REDD implementation in Indonesia. The objectives of this outcome are to support Indonesia in being ready to report emission reduction to UNFCCC and to support Indonesia in developing a REDD national implementation system, which Indonesia would like to test at provincial level. Outputs and activities will be based on any systems that have been developed by GoI to contribute to achieving a standardized system. This is important for harmonization and international recognition. Thus the Indonesian MRV system will have two functions, being the essential tool to assess the Indonesian performance in the international mitigation actions and the tool to assess the performances of Indonesian sub-national unit (e.g. provinces).

The criteria used to select the province for demonstration purposes are:

- Deforestation process is ongoing but a significant forest cover has remained.

- Carbon density is relative high

- Local political support is strong

- Local capacity is reasonably strong, in order to generate rapid results

- Drivers can be addressed relatively easily

- REDD can result in significant co benefits within the project site.

- GOI preference and location of other initiatives (based on agreements reached in IFCA on criteria for demonstration site selections, GOI policy on REDD demonstrations and UN-REDD objectives)

Based on these criteria, it is considered that the demonstration province should be selected from among three provinces in northern Sulawesi, namely Central Sulawesi, Gorontalo, and North Sulawesi.

The reasoning for selecting from among these three provinces is presented below:

- The pilot area has significant forest cover and facing significant deforestation. Sulawesi, in particular Central Sulawesi and Gorontalo still have relatively high forest cover, around 60% and higher. For Sulawesi, reanalysed Indonesian forest inventory data showed that of a total land surface, which is around 17.4 million ha, 9.8 million ha is classified as forested. Forest cover is around 60%. Recent analysis of gross forest loss for the island is estimated around 200,000 ha for the period 2000-2005, thus leading to an estimated deforestation rate of around 2%.

- Carbon density is relatively high. Forests are relative carbon dense in particular in above ground biomass. As below ground biomass remains excluded, this makes REDD piloting in Sulawesi increasingly feasible given the relative high carbon density and anticipated deforestation rate. Detailed research for the proposed UN-REDD site by the STORMA (Stabilization Tropical Rainforest Margins) -project, showed a nonlinear relationship between canopy cover in agro-forestry systems with biodiversity and ecosystem functioning. This was based on research in areas which mostly encompassed forests in mountainous regions which are characteristic for remaining forest areas..

- Local political support and capacity:  The governors of these provinces are known to be forward-looking and keen to engage with emerging international carbon markets, while the capacity of local line agencies is relatively good.

- Drivers of deforestation: Smallholder agriculture through the spontaneous spread of cash crops, has been the key driver of deforestation. The drivers for deforestation in Sulawesi are thus significantly different than in Kalimantan and Sumatra, where mechanized logging has already degraded millions of hectares of lowland forest and where now extensive areas of logged-over forest are being cleared for oil palm and pulpwood plantations. Smallholder agriculture has led to major agrarian change over the last two decades. To address drivers of deforestations, community based REDD payment mechanism can be effective alternative to compensate for economic losses due to halted conversion of forests..

- Co-benefits. The proposed project site offers significant potential to realize co-benefits due to the combination of low MDG performance and unique biodiversity..

  - MDG: The targeted parts of Sulawesi are relative poor and faces significant underdevelopment. The proposed project target provinces in Sulawesi (Gorontalo/Central Sulawesi), which despite a wealth of biodiversity has long been among the less developed parts of the country.  In the project areas, poverty levels as high as 60% are reported. In particular, Gorontalo scores low on MDGs progress (second lowest to Papua).  Of the total population in these areas, 31% lives below the poverty line and 44% of all children under five are classified as undernourished, which makes it one the poorest provinces in Indonesia.  Gorontalo for example has the second highest scores (after Papua) on poverty depth and income inequity.  Around 50% of the population has access to a latrine and protected water supply.

  - Biodiversity: Sulawesian biodiversity is unique and under threat by deforestation. Situated at the heart of the Wallacean biogeographical region (named for the 19th century naturalist Alfred Russel Wallace), Sulawesi contains unique biodiversity, with elements of both Asian and Australian fauna and flora, many of which are endemic to the island. For example, with the exception of bats, 98% of the Sulawesian mammals are endemic (notable examples being the babirusa Babyrousa babyrussa, the Anoa Bubalus depressicornis and the Sulawesi giant civet Macrogalidia musschenbroeki) while 89 of the 247 known bird species on Sulawesi are not found anywhere else (e.g. the Red-knobbed hornbill Aceros cassidix and the blue-backed parrot Tanygnathus sumatranus).

- Diversity of pilot project sites: The  MoFor  interest is to have an equal spread of pilot project throughout the country. In so far, REDD demonstration projects are located in Kalimantan and to a lesser extent in Papua and Sumatra. Sulawesi has been poorly covered.  Capacity of government agencies on Sulawesi has assessed as average for Indonesia. Some districts have shown innovation in natural resource management such as the Poso district which has developed a pro-poor land certification program.

Output 2.1 (FAO) Improved capacity and methodology design for forest carbon inventory within a Measurement, Assessment, Reporting and Verification System (MRV), including sub-national pilot implementation

This outcome will work on developing a new methodological approach for the already existing national forest inventory (NFI). The new approach should allow assessing the forest carbon content according to the IPCC LULUCF Guidance and AFOLU Guidelines and should also allow Indonesia to assess and report carbon stock and carbon stock changes at sub-national level (e.g. provincial level). Regarding the methodological design of a MRV system, the UN-REDD Programme will evaluate options that comply with the guidance provided under the UNFCCC and that will allow to assess the national performances and the Indonesian provincial performances. The two levels will be methodologically consistent and will allow Indonesia to support REDD implementation at sub-national level. Indicative activities include:

    - Review on existing standards and methodologies in MRV at national and sub-national levels;

    - Development of measurement protocols and sampling design for a national forest carbon inventory with reporting capability at provincial level, building on the existing Indonesian national forest inventory system;

    - Implementation of the forest carbon inventory in pilot provinces to assess carbon stock and carbon stock changes;

    - Development of methods for Reporting and Verification at sub-national level, consistent with national reporting requirements;

    - Implementation of Reporting and Verification in pilot provinces

    - Workshop: Identification of additional data needs concerning socioeconomic aspect in MRV Training in monitoring and assessment methodology (with AusAid)

Output 2.2 (FAO) Reference emissions level (REL)

The project will develop a methodological approach to set up a workable and verifiable REL against which future efforts to reduce deforestation and forest degradation will be measured.  It will do this at national and the sub-national levels with a REL assessment in a pilot province (likely to be Central Sulawesi).  In order to develop RELs, the following indicative activities are envisaged:

    - Review of methodologies for establishing REL at national and sub-national level

    - Development of methodological options to establish REL at national and sub-national scale

    - Compilation of data to support development of REL

    - Assessment of a provisional REL in a pilot province

    - Scientific peer review of provisional REL

    - Stakeholder consultations on REL methodological approach and provincial provisional REL

    - Scientific peer review of REL methodological approach and provincial provisional REL

Output 2.3 (UNDP) Harmonized fair and equitable payment mechanism at provincial level

There are already examples in Indonesia of payment systems under which funds are transferred from the national level down to local beneficiaries.  One such example is the PNPM Program (The National Community Empowerment Program), which is a programme to generate additional employment and corresponding additional income, primarily for poor unskilled labour.  There are also several pilot PES programmes in different parts of the country.  To the extent possible, a transparent and equitable payment mechanism for REDD should build on existing payment systems, while ensuring that the necessary assurance for international purchasers of carbon credits that their payments are for genuine carbon conservation are met. The project will therefore demonstrate the development of such a system at  provincial level. Indicative activities to achieve this result include:

    - Compilation existing payment systems

    - Analysis/review of benefits and constraints of existing systems

    - Options for modifications to meet requirements of a REDD payment system

    - Stakeholder consultations

    - Integration of modifications to create a REDD payment system

    - Training of local institutions

Output 2.4 (UNEP): Toolkit for priority setting towards maximizing potential Carbon-benefits and incorporating co-benefits, such as biodiversity conservation and poverty alleviation under MDG

Various REDD pilots are under development in Indonesia, of which most are linking carbon markets to biodiversity conservation objectives. Others incorporate watershed protection functions as well as generating co-benefits such as income generation to poor communities, the latter fully meeting MDG objectives. Whilst these are valuable local projects, less clear is whether these have been chosen at the most optimum sites with regards potential carbon gains e.g. through incorporating forested peatlands, high biomass/dense forests, or whether additional co-benefits could possibly have been incorporated, at little additional cost, by targeting a different location whilst maintaining a similar Carbon stock in below- and above-ground biomass. Factors such as maximizing potential carbon gains, water supply & watershed protection, poverty alleviation, as well as selecting biodiversity hotspots and/or sites with higher than average  poverty levels, should be important considerations in site selection for REDD, not least to build a better business case for upscaling of REDD investments nationally.

It is important however to keep the objective of reducing carbon emission high on the agenda, first of all through a standardized but easy to apply site selection process in provinces, whilst incorporating co-benefits should be treated as a secondary objective only.

The UN-REDD programme will develop a priority setting toolkit as well as building capacity in the pilot province and pilot districts on what specific forests or forest zones to target in order to maximize potential carbon gains through a systematic site selection process. This would be conducted in the forests both in the Forest Estate managed by the MoFor as well as in those forests outside the estate. Additionally it will present the methodology to optimize site selection with regards incorporating co-benefits through overlay mapping with data and GIS systems on biodiversity hotspots, high conservation value forests and others such as water resources and watersheds, as well as MDG elements like poverty alleviation.

The mapping component of this tool could build upon the FRIS, whilst the review process of REDD sites through the national registry could make use of the system to optimize for site selection. Indicative activities include:

    - Reach agreement in Indonesia on partner agencies, data sources, GIS development and site selection criteria

    - Development and testing of the Priority Setting Toolkit (including short manual)

    - Mapping of below- & above-ground carbon, inside and outside the Forest Estate, based on existing data sources and linkages to NCAS/FRIS (a. national reconnaissance level; b. detailed pilot province level)

    - Overlay maps and analyze co-benefits (minimally: biodiversity, water resources, pockets of poverty, others)

    - (GIS) Training of provincial staff in use of Priority Setting Tool

    - Workshop on how to translate and integrate the results into local spatial planning process, national REDD policy, and decision taking

Outcome 3: Capacity established to implement REDD at decentralized levels

This outcome will enable Indonesia to demonstrate its commitment to a national approach with sub national implementation through REDD demonstration at district level, based on the REDD architecture developed under outcome 2.  The project will demonstrate legal process of spatial planning in a number of districts in the demonstration province.  Key partners will be the district governments with emphasis on the DPRD, Bappeda, forestry services, agriculture and rural advisory services and Forest Management unit. To achieve the outcome, the following outputs will be pursued:

Output 3.1 (UNDP) Capacity for spatial socio-economic planning incorporating REDD at the district level

This output builds on recent spatial planning law (Law 26/2007) and Forest Law 41/1999 which provide clear guidelines on allocation land to key functions. Agreement on spatial planning is crucial to move forwards on demarking forest area and other land use categories.

The exact location of the demonstration site will be further considered taking into account various factors, including deforestation rates. Criteria to select districts as demo sites will be developed through  stakeholder consultations involving stakeholders from national, province and district levels.

A district REDD mainstreaming tool will be developed and will assist district governments, Forest Management Units (if in existence) and private forest managers to optimize carbon yields and thus generate maximum REDD benefits. Indicative activities include:

    - Develop a comprehensive baseline dataset and identify areas of REDD-eligible forest

    - Analyze opportunity costs of alternative land uses

    - Analyze the potential socio-economic impacts of REDD on communities

    - Mainstream REDD into existing spatial planning and forest utilization planning at provincial and district levels

    - Develop district based consensus on land – and forest use allocation  at district and provincial levels.

    - Approve the REDD mainstreamed spatial plan.

Output 3.2 (UNDP) Empowered local stakeholders are able to benefit from REDD

For REDD to be effective, local stakeholders, consisting both of local communities and local institutions (governmental and non-governmental) need to have the capacity and tools to ensure that they understand their rights and obligations under a REDD regime. This includes, for example, the capacity to verify that payments are consistent with reductions in deforestation and forest degradation achieved locally, and the ability to monitor overall progress in implementation of local REDD initiatives. If, for example, REDD payments are distributed based on performance at a District level, then sub-District REDD management units (for example, Forest Management Units) need to have the capacity to monitor not only their own performance, but also the performance of other management units within the District. Throughout this output, a participatory approach will be applied and stakeholders will be invited to actively participate in the process. Indicative activities to achieve this output include:

    - Capacity needs assessment

    - Design of capacity building & training

    - Training of trainers

    - Conduct of training and other capacity building activities

    - Assessment of follow-up activities required to improve and sustain capacity

Output 3.3 (UNDP) Multi-stakeholder-endorsed District plans for REDD implementation

Within the province of central Sulawesi, interest will be sought from districts to pilot REDD. This will be based on setting initial indicators which emphasis MDGs with emphasis on poverty, forest cover and carbon density of forest (above ground biomass)  through a spatial planning tools which is based on the provincial NCAS-I based on which 5 district will be pre-selected. This process is transparent and guided by a selection committees composed of representatives from MoFor, DNPI (national Climate Change Committee), MoHA (Ministry of Home Affairs) and UN-REDD.

The pre-selected districts will be asked to develop a proposal for REDD implementation which outlines clear commitments in willingness to make change in spatial planning and sufficiently strong track record in management of payment schemes such as PNPM. The district will be asked to present their proposals to a selection committee which will set transparent indicators for selection. After final selections, UNREDD will start engaging and work towards implementation of REDD. Indicative activities include:

    - Assess five districts in which REDD is most feasible

    - Socialize REDD to these districts

    - Invite these districts to present their proposals and ensure political readiness to implement REDD

    - Agree with the selected district on an implementation framework.

A logical framework matrix of the outcomes and outputs are presented in Table 2 below followed by a Summary of Results framework (Table 3).  The logical framework matrix provides the expected results (Objective, Outcomes and Outputs) of the Indonesia UN-REDD programme, together with quantitative indicators, including baseline values and time-bound targets.  It also describes the means of verification and risks and assumptions associated with each result.  The Summary of Results framework (Table 3) identifies the responsible UN agency for each Output and the implementing partner.

Table 2. Logical Framework Matrix. The indicators reflect the indicative activities mentioned above in the results framework. In some cases, two indicators have been identified for one indicative activity.

| Result | Implementing Partner | Related activities | Indicator | Baseline | Proposed target | Means of verification | Risks and assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: Strengthen multi-stakeholder participation and consensus at national and provincial level |  | - IFCA - REDD working group MoFor - DNPI LULUCF coordination program | - Components of REDD architecture and policies in place - REDD pilots running | - Few policies, but not operational yet - Pilots in early stage - Delays in investments | - By end 2009 policy hurdle for REDD demonstration removed - By end 2010 new and effective policies endorsed | Policy documents issued; interviews with key government officials and national NGOs | The REDD policy development is not dramatically interrupted by election and possible change in administration Government and local partner agencies cooperate effectively |
| Outputs: |  |  |  |  |  |  |  |
| 1.1. Consensus on key issues for national REDD policy | - MoFor/GoI | - National working group REDD - Program of DNPI - IFCA process | 1.1.1 UNREDD Programme operational 1.1.2 National and sub-national consultations on key-issues organized 1.1.3 Key issues analyzed 1.1.4 Inter-ministerial round table discussions organized 1.1.5 Policy recommendations on at least 2 key-issues prepared 1.1.5 Roadmap for issuing policies on key-issues developed | - DNPI and MoFor have established REDD related working groups. - Mandates and responsibility of MoFor and DNPI working groups have not been detailed and harmonized yet. - IFCA analysis need further actions/studies.. - Few policies, but not operational yet. - Some demo initiatives are on going. Status of demonstration projects has not been reported yet. - REDDI Strategy - Roadmap to REDD implementation has not been developed. | December 2009 1.1.1 UNREDD Programme operational 1.1.2 Two national consultation on 2 key-issues organized December 2010 1.1.2 Two national and 4 sub-national consultations on 2 key-issues organized 1.1.3 Two key issues analyzed 1.1.4 At least 6 inter-ministerial round table discussions on 2 key issues 1.1.5 Policy recommendations on at least 2 key-issues prepared 1.1.5 Roadmap for issuing policies on 2 key-issues developed | - Progress reports - MoM - Workshop proceedings - Publications - Policy recommenda-tions | Single agencies dominate the process Elections may change the political landscape on REDD Commitment from all partners Institutional relationships strengthened |
| 1.2. REDD lessons learnt | MoFor/GoI | - IFCA process - R-PLAN - Other demonstration activities (AIFCP and GTZ-KfW) - KpSHK, ICRAF, CIFOR | 1.2.1 National knowledge & learning network established 1.2.2 A Small Grants Programme established 1.2.2 Small Grants awarded 1.2.3 Joint workshops organized 1.2.4 A publication on lessons learned prepared 1.2.4 A publication on lessons learned disseminated | - Some NGOs have developed REDD related initiatives. Others are willing to do so but have constraints on funding. - Private sector intends to participate in REDD related activities. - Bilateral REDD initiatives are on going. - Experience and lessons of local communities and CSOs are not widely disseminated | December 2009 1.2.1 Framework for a national knowledge & learning network proposed 1.2.2 Terms of Reference for a Small Grants Programme developed December 2010 1.2.1 National knowledge & learning network established 1.2.2 A Small Grants Programme operational 1.2.2 Five 5 Small Grants awarded 1.2.3 Six joint workshops organized 1.2.4 One publication on lessons learned prepared 1.2.4 One publication on lessons learned disseminated | - Website - Workshop proceedings - Progress reports - Publications - Lessons learned disseminated at at COP15 - Lessons learned disseminated at at COP16 - Small Grant agreements | REDD implementers are unwilling to share experiences/technologies due to commercial or political interests |
| 1.3 Communications Programme | - MoFor/Go | - WB communications program - Green KDP/PNPM (national. community empowerment program) - KpSHK on peatland event | 1.3.1 Agreement on target messages reached 1.3.1 Target groups identified 1.3.2 Awareness impact monitoring system designed 1.3.2 Baseline established 1.3.2 Impact assessed (at completion) 1.3.3 Social marketing campaign designed 1.3.4 REDD information, education and communication materials (IEC) developed 1.3.5 National communications campaign conducted 1.3.5 high-level GoI - UN conference or panel discussion organized 1.3.6 Training on REDD for local level actors conducted | - Awareness on REDD remains limited to few key agencies at central government level. - Various policies endanger prospect and sustainability of REDD, like expansion palm oil on peat and allowing the use of timber from natural forests for pulp and paper - Training on REDD related to sub-national levels are limited. - E-data at MoFor, DNPI, UN are not well updated. | December 2009 1.3.1 Agreement on target messages reached 1.3.1 Target groups identified 1.3.2 Awareness impact monitoring system designed 1.3.2 Awareness baseline established 1.3.3 Framework for social marketing campaign drafted 1.3.4 Outline of REDD information, education and communication (IEC) materials prepared 1.3.6 Training needs on REDD for local level actors identified December 2010 1.3.2 Impact of communication campaign assessed 1.3.3 Social marketing campaign designed 1.3.4 REDD information, education and communication materials developed 1.3.5 National communications campaign conducted 1.3.5 One high-level GoI - UN conference or panel discussion organized 1.3.6 Training on REDD for local level actors conducted | - Awareness baseline study results - Midterm assessment - End-of-project assessment - Media reports - IEC materials | Government supports targeting controversial forestry issues, like oil palm expansion, mining and illegal logging |
| Outcome 2: Successful demonstration of establishing a REL, MRV and fair payment systems based on the national REDD architecture |  | - DGPLAN Province - BAPPEDA province - Centers of Applied Research in Rural Development - Universities - NGOs | - On province has improved MRV system supporting NCAS - Provisional REL successfully demonstrated | - Currently there are no provincial MRV system but it is requirement for sub national implementation - NFI (1989-1997) - FRA (2005) | - By the end of 2010 of provisional REL completed for a province - By 10/2010 NFI system redesigned and MRV demonstrated at the provincial level | Progress reports; Regulations and other documentation; System design documents; | Capital investments and training are delivered in a timely fashion Institutional coordination is effective |
| 2.1 Improved capacity and methodology design for forest carbon inventory within a Monitoring, Assessment, Reporting and Verification System (MRV), including sub-national pilot implementation | MoFor/GoI | - FAO FRA - AIFCP: FRIS, NCAS, FIREWATCH - JICA - KfW/GTZ - EU-FLEGT - National universities - South Dakota State Univ., ITC Netherlands - NGO activities by amongst others TROPENBOS, WRI, SEKALA - ICRAF, CIFOR on REDD ALERT - NCASI and FRIS of AusAID | 2.1.1 Existing standards and methodologies in MRV reviewed 2.1.2 Measurement protocols and sampling design for a national forest carbon inventory developed 2.1.3 forest carbon inventory in pilot provinces implemented 2.1.4 Methods for Reporting and Verification developed 2.1.5 Reporting and Verification in pilot provinces implemented 2.1.6 Workshop on MRV Training methodology organized | - NFI (1989-1997) are outdated and need to be further developed - Baseline for socioeconomic data in NFI does not exists | December 2009 2.1.1 Review of existing standards and methodologies in MRV published 2.1.2 Outline for measurement protocols and sampling design for a national forest carbon inventory prepared 2.1.3 Terms of Reference for forest carbon inventory in pilot provinces prepared 2.1.4 Outline for methods for Reporting and Verification prepared 2.1.6 Workshop on MRV Training methodology organized December 2010 2.1.2 Measurement protocols and sampling design for a national forest carbon inventory developed 2.1.3 forest carbon inventory in pilot provinces implemented 2.1.4 Methods for Reporting and Verification released 2.1.5 Reporting and Verification in pilot provinces implemented | - Progress reports - Regulations - Training materials - Workshop proceedings - Publications | Sufficient staff, equipment and other resources are dedicated to the task Adequate methodology selected for demonstration of MRV There is a need for a clear data management and data sharing policy among information providers and users |
| 2.2 Reference emissions level (REL) proposed at the provincial level | - MoFor/GoI | AIFCP:FRIS & NCAS; ICRAF/DGPLAN ICRAF, CIFOR on REDD ALERT | 2.2.1 REL methodologies reviewed 2.2.2 Methodological options to establish REL at national and sub-national scale developed 2.2.3 Data to support development of REL compiled 2.2.4 Provisional REL in the pilot province assessed 2.2.5 Provisional REL scientifically peer reviewed 2.2.6 Stakeholder consultations on REL methodological approach and provincial provisional REL organized 2.2.7 REL methodological approach and provincial provisional REL scientifically peer reviewed | - Some data analysis exist within DGPLAN but incomplete - No Baseline for Carbon Emission at the national and sub-national level exists - Existing NFI data not calculated for REDD - No scenario exists | December 2009 2.2.1 Review of REL methodologies published 2.2.2 Outline for methodological options to establish REL at national and sub-national scale prepared 2.2.3 Data to support development of REL compiled December 2010 2.2.2 Methodological options to establish REL at national and sub-national scale released 2.2.4 Provisional RELin the pilot province released 2.2.5 Peer review of Provisional REL completed 2.2.6 At least 4 stakeholder consultations on REL methodological approach and provincial provisional REL organized 2.2.7 Peer review of REL methodological approach and provincial provisional REL completed | - Progress reports - Technical reports - Publications - Workshop proceedings | Basic information is available (satellite images, reference data) Authorities are willing to co-operate Implementing partners are capable to allocate skillful staff |
| 2.3. Harmonized fair and equitable payment mechanism at provincial level | - MoFor/GoI | - Voluntary REDD pilots and district governments - PNPM program - PES and BD conservation initiatives | 2.3.1Existing payment systems compiled 2.3.2 Benefits and constraints of existing systems analyzed and reviewed 2.3.3 Options for modifications to meet requirements of a REDD payment system developed 2.3.4 Stakeholder consultations organized 2.3.5 A REDD payment system created 2.3.6 Local institutions trained | - No REDD payment distributions systems for all types of credits - Role of district government unclear | December 2009 2.3.1Information about existing payment systems compiled 2.3.2 Outline for a review on benefits and constraints of existing systems prepared 2.3.3 Terms of Reference for developing options for modifications to meet requirements of a REDD payment system prepared 2.3.4 One stakeholder consultations organized December 2010 2.3.2 Analytical report on benefits and constraints of existing systems published 2.3.3 Options for modifications to meet requirements of a REDD payment system developed 2.3.4 Three stakeholder consultations organized 2.3.5 A REDD payment system created 2.3.6 Local institutions trained | - Progress reports - Publications - Workshop proceedings - MoM - ToRs | No national legislation enabling the payment system(s) Lack up-front payments impacting local commitments |
| 2.4 Toolkit for priority setting towards maximizing potential Carbon-benefits and incorporating co-benefits, at the provincial level | - MoFor/GoI | - AIFCP FRIS & NCAS - Queensland Univ & James Cook University - Global Canopy Program - EU-ICRAF project, - ICRAF, CIFOR, CI, WWF, TNC, WI | 2.4.1 Agreement on agencies, data sources, GIS development and site selection criteria reached 2.4.2 The Priority Setting Toolkit (including short manual) developed 2.4.3 Below- & above-ground carbon, inside and outside the Forest Estate mapped 2.4.4 Co-benefits (minimally: biodiversity, water resources, pockets of poverty, others) mapped 2.4.4 Co-benefits maps analyzed 2.4.5 Provincial staff trained in the use of Priority Setting Tool | - No national nor provincial site selection process, IFCA provides guidelines only - No DSS to make feasible investment decisions - Draft criteria for site selection indicated in IFCA (2007) | December 2009 2.4.1 Agreement on agencies, data sources, GIS development and site selection criteria reached 2.4.2 Outline for the Priority Setting Toolkit developed 2.4.3 Terms of reference for mapping below- & above-ground carbon, inside and outside the Forest Estate prepared 2.4.4 Outline for mapping co-benefits (minimally: biodiversity, water resources, pockets of poverty, others) prepared | - Project reports - Manual of Toolkit translated in Bahasa Indonesia - Maps - MoM | RS coverage pilot province not available or not in time for analysis MoFor departments unwilling to exchange data sets, and share with FORDA Climate Change impacts lead to significant changes in forest ecology. |
|  |  |  | 2.4.6 Workshop organized on co-benefits, local spatial planning, and national REDD policy |  | December 2010 2.4.2 The Priority Setting Toolkit (including short manual) developed and published 2.4.3 Below- & above-ground carbon, inside and outside the Forest Estate mapped 2.4.4 Co-benefits (minimally: biodiversity, water resources, pockets of poverty, others) mapped 2.4.4 Co-benefits maps analyzed and published 2.4.5 Provincial staff trained in the use of Priority Setting Tool 2.4.6 Workshop organized on co-benefits, local spatial planning, and national REDD policy |  |  |
| Outcome 3: Capacity established to implement REDD at decentralized levels |  | - GTZ forest and climate program; - Australian Indonesia Forest & Climate Partnership - FCFP: (Facility for Carbon Forest Partnership) - Voluntary projects - Potential A/R investments | - Local government programs and policies on REDD - Awareness level on REDD with decision makers - # of districts REDD ready | - Weak awareness and understanding pro-contra of REDD - No integrated approach to carbon stock management at district level - Limited understanding on how REDD impacts on local supply level requires A/R investment | - By end of 2010 district spatial plan endorsed by DPRD for 2-3 districts - Awareness levels - One district is REDD ready | Capacity and awareness impact surveys Spatial plan ready + implementation plan | Bupati/DPRD willing to make changes in forest use and status REDD commitment is not dependent on Bupati only but based on stakeholder wide Commitment. |
| 3.1 Capacity for spatial socio-economic planning incorporating REDD at the district level | MoFor/GoI | - TGHK forestry mapping (MoFor); RTRD – spatial planning (PU); Kabupaten Development Program (WB) | 3.1.1 a comprehensive baseline dataset developed 3.1.1 Areas of REDD-eligible forest identified 3.1.2 Opportunity costs of alternative land uses analyzed 3.1.3 Potential socio-economic impacts of REDD on communities analyzed 3.1.4 REDD integrated in existing spatial planning and forest utilization planning 3.1.5 District based consensus on land – and forest use allocation reached 3.1.6 The REDD mainstreamed spatial plan approved | - Ongoing conflicts TGHK with process RTRD - Few district spatial plans endorsed at national level | December 2009 3.1.1 a comprehensive baseline dataset developed 3.1.1 Areas of REDD-eligible forest identified December 2010 3.1.2 Opportunity costs of alternative land uses analyzed and published 3.1.3 Potential socio-economic impacts of REDD on communities analyzed and published 3.1.4 REDD integrated in existing spatial planning and forest utilization planning 3.1.5 District based consensus on land – and forest use allocation reached 3.1.6 The REDD mainstreamed spatial plan approved | - Reports - Minutes of consultations - Maps - draft spatial plan | Forestry authorities willing to participate and go for consensus Priority setting tool ready and applied |
| 3.2 Empowered local stakeholders are able to benefit from REDD | - MoFor/GoI | KDP (WB); various other social development programs pending district chosen | 3.2.1 Capacity needs assessment made 3.2.2 Capacity building & training modules developed 3.2.3 Trainers have been trained 3.2.4 Training and other capacity building activities have been | - Low awareness and high level of misconception REDD at village and district level - All REDD proposals driven by foreign agencies | December 2009 3.2.1 Capacity needs assessment made 3.2.2 Outline for capacity building & training modules prepared December 2010 3.2.2 Capacity building & training modules developed | - Progress reports - Publications - Awareness & capacity impact studies at mid- and end- term | Baseline established at inception |
|  |  |  | Implemented 3.2.5 Follow-up activities required to improve and sustain capacity have been assessed |  | 3.2.3 Trainers have been trained 3.2.4 Training and other capacity building activities have been implemented 3.2.5 Follow-up activities required to improve and sustain capacity have been assessed |  |  |
| 3.3 Multi-stakeholder-endorsed District plans for REDD implementation | - MoFor/GoI | ongoing RTRD (spatial planning at district) | 3.3.1 Five districts in which REDD is most feasible identified 3.3.2 REDD socialized to these districts 3.3.3 Districts developed proposals to implement REDD 3.3.3 Districts show political commitment to implement REDD 3.3.4 For at least one district, agreement on an implementation framework for REDD reached | - Few district spatial plans endorsed at national level | December 2009 3.3.1 Five districts in which REDD is most feasible identified December 2010 3.3.2 REDD socialized to 5 districts 3.3.3 Five districts have developed proposals to implement REDD 3.3.3 Districts show political commitment to implement REDD 3.3.4 For at least one district, agreement on an implementation framework for REDD reached | - Progress reports - MoM - Workshop proceedings - Policies issued - Perda on RTRD | DPRD approves district based spatial plans, |

Table 3: Summary of Results framework

| JP Results | Responsible UN org | Reference to CP | Implementing Partner | Indicative activities for each outputs | Resources allocation |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Y1 | Y2 |
| Outcome 1: Strengthen multi-stakeholder participation and consensus at national and provincial level |  |  |  |  |  |  |
| 1.1 Consensus on key issues for national REDD policy development | UNDP | By 2010 improved environmental living conditions and sustainable use of energy in Indonesia, and establishment of sustainable living conditions in the poorest provinces | MoFor/GoI | - UN REDD Programme Management Unit facilitating multi-stakeholder activities - National and sub-national consultations on key-issues - Analyze key issues focusing on those related to REL - Facilitate inter-ministerial round table discussions on identified issues - Prepare policy recommendations & develop roadmap for issuing policies to address these issues | 190,000 | 310,000 |
| 1.2 REDD lessons learned | UNDP | As above | MoFor/GoI | - Establish national knowledge & learning network - Collaboration with projects to stimulate coordination and joint learning (incl Small Grants Programme) - Organize joint workshops - Prepare publication on lessons learned | 100,000 | 300,000 |
| 1.3 Communications Programme | UNEP | As above | MoFor/GoI | - Agree on target messages, target groups and national partners - Design awareness impact monitoring system, establishing baseline, and assessing impact at completion - Design of social marketing campaign, focus on high level government decision makers, as well as local resource users in the pilot districts - Develop REDD information, education and communication materials - Conduct national communications campaign targeting one or two drivers of deforestation (incl. high-level GoI - UN conference or panel in JKT) Conduct training on REDD -emphasize local level actors | 176,000 | 524,000 |
| Outcome 2: Successful demonstration of establishing a REL, MRV and fair payment systems based on the national REDD architecture | Responsible UN org | Reference to CP | Implementing Partner | Indicative activities for each outputs | Resources allocation |  |
|  |  |  |  |  | Y1 | Y2 |
| 2.1 Improved capacity and methodology design for forest carbon inventory within a Measurement, Reporting and Verification System (MRV), including sub-national pilot implementation | FAO | As above | MoFor/GoI | - Review on existing standards and methodologies in MRV at national and sub-national levels; - Development of measurement protocols and sampling design for a national forest carbon inventory with reporting capability at provincial level, building on the existing Indonesian national forest inventory system; - Implementation of the forest carbon inventory in pilot provinces to assess carbon stock and carbon stock changes; - Development of methods for Reporting and Verification at sub-national level, consistent with national reporting requirements; - Implementation of Reporting and Verification in pilot provinces - Workshop: Identification of additional data needs concerning socioeconomic aspect in MRV Training in monitoring and assessment methodology (with AusAid) | 200,000 | 750,000 |
| 2.2 Reference emissions level (REL) proposed at the provincial level | FAO | As above | MoFor/GoI | - Review of methodologies for establishing REL at national and sub-national level - Development of methodological options to establish REL at national and sub-national scale - Compilation of data to support development of REL - Assessment of a provisional REL in a pilot province - Scientific peer review of provisional REL - Stakeholder consultations on REL methodological approach and provincial provisional REL - Scientific peer review of REL methodological approach and provincial provisional REL | 65,000 | 385,000 |
| 2.3 Harmonized fair and equitable payment mechanism at provincial level | UNDP | As above | MoFor/GoI | - Compilation existing payment systems - Analysis/review of benefits and constraints of existing systems - Options for modifications to meet requirements of a REDD payment system - Stakeholder consultations - Integration of modifications to create a REDD payment system - Training of local institutions | 65,000 | 335,000 |
| 2.4 Toolkit for priority setting towards maximizing potential Carbon-benefits and | UNEP | As above | MoFor/GoI | - Reach agreement in Indonesia on partner agencies, data sources, GIS development and site selection criteria | 145,000 | 230,000 |
|  | Responsible UN org | Reference to CP | Implementing Partner | Indicative activities for each outputs | Resources allocation |  |
|  |  |  |  |  | Y1 | Y2 |
| incorporating co-benefits, at the provincial level |  |  |  | - Development and testing of the Priority Setting Toolkit (including short manual) - Mapping of below- & above-ground carbon, inside and outside the Forest Estate, based on existing data sources and linkages to NCAS/FRIS (a. national reconnaissance level; b. detailed pilot province level) - Overlay mapping and analysis co-benefits (minimally: biodiversity, water resources, pockets of poverty, others) - level a. and b. (one province only) - (GIS) Training of provincial staff in use of Priority Setting Tool Workshop on how to translate and integrate the results into local spatial planning process, national REDD policy, and decision taking |  | Y |
| Outcome 3: Capacity established to implement REDD at decentralized levels |  |  |  |  |  |  |
| 3.1 Capacity for spatial socio-economic planning incorporating REDD at the district level | UNDP | As above | MoFor/GoI | - Develop a comprehensive baseline dataset and identify areas of REDD-eligible forest - Analyze opportunity costs of alternative land uses - Analyze the potential socio-economic impacts of REDD on communities - Mainstream REDD into existing spatial, forest utilization and FMU planning at District level - District based consensus on land – and forest use allocation, - Approve the REDD mainstreamed spatial plan | 40,000 | 610,000 |
| 3.2 Empowered local stakeholders are able to benefit from REDD | UNDP | As above | MoFor/GoI | - Capacity needs assessment - Design of capacity building & training - Training of trainers - Conduct of training and other capacity building activities - Assessment of follow-up activities required to improve and sustain capacity | 50,000 | 500,000 |
| 3.3 Multi-stakeholder-endorsed District plans for REDD implementation | UNDP | As above | MoFor/GoI | - Assess five districts in which REDD is most feasible - Socialize REDD to these districts - Invite these districts to present their proposals and ensure political readiness to implement REDD - Agree with the selected district on an implementation framework. | 50,000 | 250,000 |
| UNDP | Programme Cost ** |  |  |  | 495,000 | 2,305,000 |
|  | Indirect Support Cost** |  |  |  | 34,650 | 161,350 |
| UNEP | Programme Cost |  |  |  | 321,000 | 754,000 |
|  | Indirect Support Cost |  |  |  | 22,470 | 52,780 |
| FAO | Programme Cost |  |  |  | 265,000 | 1,135,000 |
|  | Indirect Support Cost |  |  |  | 18,550 | 79,450 |
| Totals | Programme Cost |  |  |  | 1,081,000 | 4,194,000 |
|  | Indirect Support Cost |  |  |  | 75,670 | 293,580 |
|  | TOTALS |  |  |  | 1,156,670 | 4,487,580 |
|  | GRAND TOTAL |  |  |  | 5,644,250 |  |

Note: Resources allocated to each output are exclusive of programme management costs

# 6. Management and Coordination Arrangements

The Lead Implementing Partner of this Programme will be the Ministry of Forestry. A national implementation management approach of the UN will be used to run the programme / project. A National Project Director (NPD) will be appointed by the GoI. The NPD will direct the programme and carry overall accountability on behalf of the GoI for the programme to the Project Executive Board (PEB; see below). The overall programme and each specific activity will be implemented under the leadership of the GoI, represented by the NPD.

The programme will be managed in accordance with the 2003 UNDG Guidance Note on Joint Programming and executed by several “National Implementing Partners”, including the Ministry of Forestry, Provincial and District agencies, through the participating UN Agencies, i.e. UNEP, FAO, and UNDP. Each of those Implementing Partners is accountable to the Lead Implementing Partner relating to the funds released for the delivery of a specific set of outputs and for management of inputs.

The programme will be run and managed following the UN guidance on programme structure. There will be three main components in the programme structure, namely Programme Executive Board (PEB), Project Management Unit (PMU), and Programme Assurance.

Programme Executive Board (PEB)

A Programme Executive Board will be established by the Ministry of Forestry in consultation with Bappenas, and other key-stakeholders as deemed necessary, as well as the UN Resident Coordinator (UNRC), to guide and oversee the NJP. The PEB will be chaired by the Ministry of Forestry and co-chaired by a designate of UNRC. Members of the PEB will include; representatives of BAPPENAS, FAO, UNDP, UNEP, and the Embassy of Norway. Resources persons from e.g. Indigenous Peoples’ and Civil Society Organizations, and other relevant stakeholders can be invited to attend meetings of the PEB. The PEB will meet at least 3 times per year to ensure effective project implementation. The PEB will provide overall guidance and be responsible for the effective implementation of the programme, the approval of all detailed work plans, budgets, and monitoring and evaluation.  PEB decisions will be reached by consensus. Specific responsibilities include:

  - Provide policy directions to the Programme Management Unit (PMU) on substance, operations, and finance

  - Review and approve Standard Operating Procedures and Mechanisms

  - Approve Annual Work Plan (AWP) including proposed activities as prepared by the PMU

  - Approve draft reports to Global UN-REDD Policy Board prepared by the PMU

  - Coordinate with other REDD related initiatives at policy level

  - Approving the NJP communication strategy and public information plans prepared by the PMU

UN Resident Coordinator (UNRC) and UN Programme Assurance Team

As part of the PEB co-chair role, the UN Resident Coordinator provides leadership, coordination and on-going oversight to the UNREDD Programme, particularly ensuring the participating UN Agencies are meeting their obligations as agreed by the PEB. He/she also facilitates ongoing monitoring and evaluation of UN-REDD activities in conformity with UN standards. The UNRC will be supported by a team of Jakarta based UN Staff for programme assurance. The Programme Assurance Team will i) conduct monthly discussions with their counterparts from the Ministry of Forestry on progress made and issues to be resolved, ii) communicate and coordinate with the regional Centre of FAO, UNDP and UNEP and the respective headquarters, iii) report to the UNREDD Policy Board, iv) support the National Programme Director in working with the UN-agencies. The Programme Assurance Team will be assisted by technical experts from the regional centre of FAO, UNDP and UNEP in Bangkok and the respective headquarters

At the country level, all UN-agencies involved (FAO, UNDP and UNEP) carry equal responsibility. At the project level, the agencies are member of the PEB. Together with the GoI, each agency is responsible for the sound implementation of the outputs and budget allocated  to the respective outputs.

Technical Committee (TC)

A Technical committee consisting of GoI Officials and Jakarta based UN-staff will be established and meet on a monthly basis to provide technical guidance to the project. The TC will also coordinate with other initiatives and agencies on technical matters related to REDD. As per identified needs, other agencies and institutions can be invited to discuss technical issues and share lessons learned.

National Programme Director (NPD)

MoFor will assign a senior government official from MoFor as the National Programme Director. The NPD will work part-time for the project and will be appointed by the Government as in-kind contribution. The NPD will be assisted by Deputy NPDs (if needed). The NPD will manage the programme and carry overall accountability on behalf of the GoI for the programme to the Project Executive Board. She/he will establish (including recruitment of National Project Manager and organizational structure of the Programme Management Unit (PMU; see below). The NPD will furthermore supervise the PMU in implementing the programme. The NPD can appoint Deputy National Programme Director(s) to support him/her in his/her functions and delegate certain tasks if deemed necessary. The NPD is responsible for managing the PMU in developing the relevant SOPs, mechanisms, AWPs, progress reports, M&E framework, to be submitted to the PEB for endorsement. He/she will also be responsible for financial reporting to the Ministry of Finance in accordance with existing regulations. The NPD will furthermore participate in UNREDD Policy Board meetings and reports on behalf of the GoI.

Programme Management Unit (PMU)

At the project management level, MoFor will create a Project Management Unit (PMU) responsible for the overall operational and financial management and reporting of the UNREDD funds in accordance with the rule and regulations for nationally implemented project. The PMU will manage day-to-day operations of the project, and will be based at the MoFor.

The PMU will be responsible for the overall day to day operational and financial activities, developing the relevant SOPs, mechanisms, AWPs, progress reports, M&E framework under supervision of the NPD, in close coordination with the implementing partners and key-stakeholders.

The PMU will also be responsible for preparing a quarterly workplan (QWP) using a unified workplan format and covering activities and inputs under all three Participating UN Agencies and MoFor. Quarterly progress reports will be prepared on activities and detailed expenditures, disaggregated by the responsible participating UN Agency. The QWP will be accompanied by a quarterly budget table, disaggregated by the responsible Participating UN Agency. It will also include the identification of specific procurement and recruitment activities to be undertaken by the Participating UN Agencies. The QWP and budget will be reviewed and agreed by the chair and co-chair of the PEB, in consultation with the members of the PEB.

The PMU will be responsible for the overall operational and financial management in accordance with financial rules and regulations imposed by UN for nationally Implemented Programmes. It will prepare quarterly progress reports, which are to be submitted to UNRC Indonesia. It will hold quarterly meetings with UNRC Indonesia to discuss a quarterly progress report, a quarterly work plan, a quarterly budget and any other relevant issues. It will also produce annual progress reports, which must be submitted to the PEB.  At the end of the Programme, the PMU produces the terminal report, which is to be submitted to the PEB.

Guided by the NPD, the PMU will be comprised of a National Programme Manager (NPM)  a Chief Technical Advisor, three team leaders, a Procurement Specialist, Finance Associate, Administrative Associate, Secretary, experts, national and international consultants, support staff and (if deemed necessary) subcontractors The UNREDD NJP PMU organizational chart is shown  below.

National Programme Manager (NPM)

A professional National Programme Manager will be appointed by the MoFor to ensure smooth implementation of the NJP on a daily basis. The NPM will be accountable for implementation of all activities of the project. This position will require outstanding management skills and experience, and thorough knowledge of both the UN and GoI rules and regulations. Furthermore, the position requires excellent language skills in both English and Bahasa Indonesia (verbally and written). Supervised by the NPD/DNPD and the UNRC, he/she will be responsible for the day-to-day implementation of the project, preparation of progress reports, annual and quarterly workplans, budget approval, and coordination of activities, and compliance with rules and regulations of both the GoI and the UN agencies where applicable.

She/he will be overseeing a team consisting of a Chief Technical Advisor , three team leaders, a Procurement Specialist, Finance Associate, Administrative Associate, Secretary, experts, national and international consultants  support staff., and if needed, sub-contractors.

# UNREDD NJP Programme Structure

Programme Assurance

(UNRC, FAO, UNDP, UNEP)

Global

UN-REDD

Policy Board

National Programme Director & Deputy NPD (GOI)

Programme Management Unit

Technical Committee

Chief Technical Advisor      Administrative Associate

Procurement specialist         Secretary

Finance Associate        Support staff

National Programme Manager

Outcome 2

Team Leader

Experts

Consultants

Outcome 1

Team Leader

Experts

Consultants

Outcome 3

Team Leader

Experts

Consultants

National Programme Executive Board (PEB)

Chair: Ministry of Forestry and UNRC

Members: Bappenas, FAO, UNDP, UNEP, Embassy of Norway

Resource Persons e.g. from CSOs, research agencies and universities.

# 7.  Execution modality and Fund Management Arrangements

The NJP will be executed through the National Implementation Modality (NIM) following all relevant Government regulations. The signed Project Document will serve as the Grant Agreement between the GoI and the UN, supported by the UN-REDD Policy Board decision to allocate the requested funds to the NJP. MoFor will register the programme following the appropriate mechanism and will request MoF to open a project bank account. To expedite the start of the initial activities, MoFor will request the UNRC for country support services from the UN allowing direct payment of goods and services required for undertaking the project activities.

In the case of all three UN Agencies, cash transfers will be according to the UN Harmonized Approach to Cash Transfers (HACT) as agreed at the global level. All Agencies agree that the specific modality of cash transfers will be determined on the basis of a joint micro-assessment to be conducted by the United Nations. The joint Micro-assessment will review the Implementing Partner and the UN agencies involved to identify the appropriate modality for sound financial and administrative management of the NJP.

At the global level, Fund management will use the pass-through modality. UNDP’s Multi-donor Trust Fund Office (MDTF) has been designated as Administrative Agent for UN-REDD. The funds from UN-REDD will be passed through from the Administrative Agent to the Participating UN agencies at headquarters’ level in accordance with the MOU between the Global UN-REDD Programme and the Multi-donor Trust Fund Office.

The disbursed funds from the MDTF to each Participating UN agency will be used by the Programme to carry out the activities for which each UN agency carries responsibility as stated in the NJP. If there is a need to exceed the budgeted amounts, the PEB will submit a supplementary budget request to the UN-REDD Policy Board, through the Technical Secretariat.

The budget includes a 7% General Management Services Costs (indirect costs) of each UN agency. In addition, costs for specialized backstopping support by UN-staff (“Specialized service delivery costs”) can be charged directly to the joint programme. This will be in accordance with the respective Participating UN Agencies’ policies. Backstopping support costs will amount to no more than 6% of the Participating UN Agency’s budget allocation.

At country / project level, fund management will use the government mechanism (PP2/2006).  The on budget off treasury approach will be implemented. All activities will be documented in the DIPA.  Other arrangements not specified in the NJP will be based on applicable rules and regulations of GoI and the relevant UN agency, in consultation with the PEB.

Programme Procurement and Assets

All Programme asset and services shall be procured in line to GoI and UN rules and regulations. All assets shall at all time be in the custody of the PMU throughout the life of the Programme and remains the property of UN which upon closure of the Programme will be handed over to the Implementing Partner. The Programme policy on asset management and transfer of assets upon Programme closure will be decided by the PEB meeting at least 2 quarters before programme closure.

# 8. Monitoring, Evaluation and Reporting

The Indonesia UN-REDD programme is expected to last 20 months, and represents an initial phase in the process of supporting Indonesia to become REDD-ready by 2012. Based on table 2, a monitoring workplan has been prepared for 2009. The monitoring workplan for 2010 will be prepared by the PMU in the fourth quarter of 2009.

Table 4. Monitoring workplan 2009

| Outputs | Indicator December 2009 | Means of Verification |
| --- | --- | --- |
| 1.1 Consensus on key issues for national REDD policy development | 1.1.1 UNREDD Programme operational 1.1.2 Two national consultations on 2 key-issues organized | Reports ToRs Contracts issued MoM Workshop proceedings |
| 1.2 REDD lessons learned | 1.2.1 Framework for a national knowledge & learning network proposed 1.2.2 Terms of Reference for a Small Grants Programme developed | Reports ToR |
| 1.3 Communications Programme | 1.3.1 Agreement on target messages reached 1.3.1 Target groups identified 1.3.2 Awareness impact monitoring system designed 1.3.2 Awareness baseline established 1.3.3 Framework for social marketing campaign drafted 1.3.4 Outline of REDD information, education and communication (IEC) materials prepared 1.3.6 Training needs on REDD for local level actors identified | Reports Interview reports MoM |
| 2.1 Improved capacity and methodology design for forest carbon inventory within a Monitoring, Assessment, Reporting and Verification System (MRV), including sub-national pilot implementation | 2.1.1 Review of existing standards and methodologies in MRV published 2.1.2 Outline for measurement protocols and sampling design for a national forest carbon inventory prepared 2.1.3 Terms of Reference for forest carbon inventory in pilot provinces prepared 2.1.4 Outline for methods for Reporting and Verification prepared 2.1.6 Workshop on MRV Training methodology organized | Reports ToR Workshop proceedings |
| 2.2 Reference emissions level (REL) proposed at the provincial level | 2.2.1 Review of REL methodologies published 2.2.2 Outline for methodological options to establish REL at national and sub-national scale prepared 2.2.3 Data to support development of REL compiled | Reports Publication |
| 2.3 Harmonized fair and equitable payment mechanism at provincial level | 2.3.1Information about existing payment systems compiled 2.3.2 Outline for a review on benefits and constraints of existing systems prepared 2.3.3 Terms of Reference for developing options for modifications to meet requirements of a REDD payment system prepared 2.3.4 One stakeholder consultations organized | Reports Workshop proceedings ToR |
| 2.4 Toolkit for priority setting towards maximizing potential Carbon-benefits and incorporating co-benefits, at the provincial level | 2.4.1 Agreement on agencies, data sources, GIS development and site selection criteria reached 2.4.2 Outline for the Priority Setting Toolkit developed 2.4.3 Terms of reference for mapping below- & above-ground carbon, inside and outside the Forest Estate prepared 2.4.4 Outline for mapping co-benefits (minimally: biodiversity, water resources, pockets of poverty, others) prepared | MoM Reports Maps ToR |
| 3.1 Capacity for spatial socio-economic planning incorporating REDD at the district level | 3.1.1 a comprehensive baseline dataset developed 3.1.1 Areas of REDD-eligible forest identified | Reports MoM Maps |
| 3.2 Empowered local stakeholders are able to benefit from REDD | 3.2.1 Capacity needs assessment made 3.2.2 Outline for capacity building & training modules prepared | Reports MoM |
| 3.3 Multi-stakeholder-endorsed District plans for REDD implementation | 3.3.1 Five districts in which REDD is most feasible identified | Reports Maps MoM |

Monitoring of risk

As part of the project assurance functions, the Risk Log and Issue Log will be reviewed on a quarterly basis (Table 5).  In the case of any changes in risk and issue status, these will be discussed with the PMU for Counter Measures/Management Response.  The revised Risk Log and Issue Log will be sent to the MoFor and all participating UN agencies for their information and if needed, action.

Evaluation, Annual/Regular reviews:

The global UNREDD Technical Secretariat (based in Switzerland) will establish an Evaluation Plan which ensures that all country programmes supported by the UN-REDD Programme will undertake a final evaluation. This will assess the relevance and effectiveness of the intervention, and measure the development impact of the results achieved, on the basis of the initial analysis and indicators described at the time of programme formulation.  Furthermore, the UNREDD Technical Secretariat will lead thematic reviews for all programmes.

Reporting by the participating UN Agencies

Coordinated by the UNRC, the Participating UN Agencies will provide narrative reports on results achieved, lessons learned and the contributions made to the Joint Programme. The information shall be consolidated by the UNRC Office into a narrative report every 6 months, and sent to the PEB for review and endorsement. The NPD or the UNRC will forward the report to the Global UN REDD Technical Secretariat that will use it to provide the Policy Board updates on the implementation progress of the NJP.

At the global level, the Administrative Agent will provide regular updates on the financial status of the MDTF to the Policy Board, for review and action as appropriate.

In consultation with the PEB, participating UN Agencies in receipt of UN-REDD resources will provide the Administrative Agent (see footnote 16) with the following statements and reports:

- Narrative progress reports for each twelve-month period ending 31 December, to be provided no later than two months after the end of the applicable reporting period;

- Annual financial reports as of 31 December each year with respect to the funds disbursed to it from the Joint Programme Account, to be provided no later than three months after the end of the applicable reporting period;

- A final narrative report and financial report, after the completion of all Joint Programme activities financed from the UN-REDD MDTF, to be provided no later than 30 April of the year following the financial closing of Joint Programme activities;

- A final certified financial statement, to be provided no later than 30 June of the year following the financial closing of Project activities.

The Administrative Agent shall prepare consolidated narrative progress and financial reports consisting of the reports referred to above submitted by each Participating UN Agency, and shall provide those consolidated reports to the respective Resident Coordinators and subsequently to the UN-REDD Policy Board through the Technical Secretariat.

Subsequently, in accordance with the MOU and the Standard Administrative Arrangement, the Administrative Agent will submit consolidated narrative and financial reports to all UN-REDD Programme donors. Agreed standard UNDG financial and progress reporting formats will be utilized. The Administrative Agent will also submit to donors a certified annual financial statement (Source and Use of Funds).

Information given to the press, to the beneficiaries of the UN-REDD Programme, all related publicity material, official notices, reports and publications, shall acknowledge the role of the UN-REDD donors, the UN Agencies, and any other relevant parties.

Whenever possible and to the extent that it does not jeopardize the privileges and immunities of UN Agencies, and the safety and security of their staff, UN Agencies will promote donor visibility on information, project materials and at project sites, in accordance with their respective regulations, rules, policies and procedures.

Table 5: RISK LOG: UN-REDD Programme for Indonesia

| # | Description | Date Identified | Type | Probability (P) & Impact (I)* | Counter measures / Management response | Owner | Submitted/updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Commitment of the GoI towards implementing REDD does not remain firm | Programme formulation | Political | Lacking high-level support, progress in programme implementation would be slow, REDD-readiness would not be achieved, and the viability of REDD as an approach to CC mitigation and forest conservation undermined 1 4 4 x = = P x I | Linking the programme to the National Target Programme on CC, which has very strong political support, reduces this risk | UNDP CO will monitor | Programming mission team leader | May 2009 | Stable |
| 2 | Government agencies do not cooperate and coordinate activities effectively | Programme formulation | Organizational | Failure of government agencies, including departments of MoFor, to cooperate would slow, but would not prevent progress towards REDD-readiness. A perception of institutional competition would reduce overall commitment to REDD 3 4 12 □ x = = P x I | Discussions with other agencies, especially the DNPI, took place during formulation. Key partners will be involved in the PEB | Programme manager will be responsible for reporting to UNRC on any early indications of lack of coordination | Programming mission team leader | May 2009 | Stable |
| 3 | Donor coordination (most importantly, with FCPF and AusAID ) is ineffective | Programme formulation | Organizational | Lack of donor coordination would restrict the flow of funds to assist in the progress towards REDD-readiness. As the UN-REDD programme was formulated as part of a larger partnership in developing REDD-readiness, this could limit the benefits of the programme 2 3 6 x = = P x I | The interim working group, which will include donor representatives, will promote coordination. Active exchange of information will be maintained with FCPF, including joint missions whenever possible | UN agencies in-country; UN agency regional coordinators/ advisors | Programming mission team leader | May 2009 | Stable |
| 4 | Sub-national authorities do not share central government’s commitment to REDD | Programme formulation | Political | It is inevitable that there will be variation in the level of commitment among sub-national partners; where commitment is low, developing capacity to implement REDD will be slow. Ultimately, it is to be expected that national implementation of REDD will need to take account of poor progress in some provinces/districts 3 3 9 x = = P x I | Formulation of the programme took this risk into account by selecting a pilot province and pilot Districts where commitment is known to be high | Programme manager will be responsible for reporting to UNRC on any early indications of lack of commitment at pilot sites | Programming mission team leader | May 2009 | Stable |
| 5 | Programme inputs (funds, human resources, etc.) are not mobilized in a timely fashion | Programme formulation | Operational | Most of the outputs in the programme logframe are inter-connected so slow mobilization of inputs to one component will slow down the whole programme 2 2 4 x = = P x I | The PMU includes both a programme manager and technical advisor, whose roles will include management of inputs. Regular communication among UN agencies will reduce probability of risk | Programme manager will be responsible for reporting to UN agencies on apparent or potential delays in mobilizing inputs | Programming mission team leader | May 2009 | Stable |
| 6 | Influential stakeholders who benefit from forest (over)-exploitation undermine REDD | Programme formulation | Political | It is recognized that some stakeholders will hold negative views towards REDD, especially those who benefit from, for example, illegal trade in timber. If these stakeholders exert political pressure to hinder the development of REDD, programme benefits could be compromised 3 4 12 x = = P x I | Engagement both with potential negatively-minded stakeholders and with high-level government officials, supported by awareness campaigns will reduce risk | National Implementing Partner and Programme Manager will be responsible for monitoring | Programming mission team leader | May 2009 | Stable |
| 7 | UN agency partners are unable to coordinate inputs and support to the programme |  | Strategic | The three UN Agency partners in UN-REDD have limited experience in working on joint programmes, and have different approaches to project management, which could impact efficiency of programme implementation 2 3 6 x = = P x I | The UNRC office will, facilitate and coordinate. Regular communication at all levels among the UN agencies will reduce risk | UNRC, UN Agency country offices and regional coordinators | Programming mission team leader | May 2009 | Stable |

* Probability (P) x Impact (I) = risk; P and I are ranked from 1 to 5 (1 = low; 5 = high); low risk is 1, high risk is 25

# 9. Legal Context or Basis of Relationship

The Participating UN Agencies (FAO, UNDP and UNEP) have signed a Memorandum of Understanding (MOU) to implement the UN-REDD Collaborative Programme, which came into effect on 20th June 2008 and ends 20th June 2012.

This Joint Programme document is consistent with the cooperation/assistance agreements signed by the lead UN agencies involved in this programme with the Government of Indonesia.  For the UNDP, this Document is pursuant to the Country Programme Action Plan and arrangements for Non-Standard Basic Assistance Agreement (SBAA) countries (see annex 3 and 4)

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried; and

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan

The UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary.  Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

On the part of the FAO, this document is consistent with the basic agreement with Government of Indonesia as indicated in the exchange of letters between the Government of Indonesia and FAO on 16 October 1978.

The FAO Representative shall represent the Organization in Indonesia, and shall be responsible within the limits of the authority delegated to him/her, for all aspects of the Organization’s activities in the country.  In the effective performance of his/her functions, the FAO representative shall have access to appropriate policy and planning levels of Government in the agriculture, fishery and forestry sectors of the economy, as well as, to central planning authorities. He/she shall maintain close liaison with the Government’s coordinating agency for external assistance and thereby serve to keep all the appropriate Government agencies fully informed on all aspects of the policies and procedures of FAO’s programme in Indonesia.

For UNEP, in line with its position as a non-resident agency with a global mandate for technical cooperation and capacity building, the signed Joint Programme document shall be the legal basis of UNEP’s relation with the Government of Indonesia within the context of this programme.  UNEP will work in close coordination with the programme management team.

The Participating UN Agencies agree to undertake all reasonable efforts to ensure that none of the funds received pursuant to UN-REDD are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by Participating UN Agencies do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this programme document.

10. Title rights, copyrights, patents and other proprietary rights

MoFor and Participating UN Agencies in the UNREDD Programme shall be entitled to all intellectual property and other proprietary rights, including, but not limited to, patents, copyrights and trademarks, with regard to products, processes, inventions, ideas, know-how or documents and other materials which the UNREDD Program and Individual contractor has developed under the NJP Agreement, and which bear a direct relation to or are produced or prepared or collected in consequence of, or during the course of, the performance of the NJP Agreement.

At the request of UNREDD Programme, individuals, institutions, companies and contractors involve in the UNREDD Programme activities shall take all necessary steps, execute all necessary documents and generally assist in securing such proprietary rights and transferring or licensing them to UNREDD Programme in compliance with the requirements of the applicable law and of the Agreement. Subject to the foregoing provisions, all maps, drawings, photographs, mosaics, plans, reports, estimates, recommendations, documents and all other data compiled by or received by the individuals, institutions, companies and contractors involve in the UNREDD Programme activities shall be the property of UNREDD Programme, shall be made available for use or inspection by UNREDD Programme at reasonable times and in reasonable places, shall be treated as confidential and shall be delivered only to UNREDD Programme authorized officials on completion of work under the NJP Agreement.

# 11. Harmonized Annual Work Plan 2009

The Annual Work Plan and budget for 2009 is provided below. Revised work plans and budgets will be produced subsequent to the decisions of the annual/regular reviews. Such revised work plans will be approved in writing by the joint programme Steering Committee.

| NJP Results | Indicative activities | Q1 | Q2 | Q3 | Q4 | Implementing Partner | Source of funding | Budget description | USD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: Strengthen multi-stakeholder participation and consensus at national and provincial level |  |  |  |  |  |  |  |  |  |
| 1.1 Consensus on key issues for national REDD policy development | 1.1.1 UN REDD Programme Management Unit facilitating multi-stakeholder activities | - | - | X | X | MoFor/GoI | MDTF | Personnel | 100,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | 20,000 |
|  |  |  |  |  |  |  |  | Contracts | 30,000 |
|  |  |  |  |  |  |  |  | Other direct costs | 10,000 |
|  | 1.1.2 National and sub-national consultations on key-issues | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 1.1.3 Analyze key issues focusing on those related to REL | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 10,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 1.1.4 Facilitate inter-ministerial round table discussions on identified issues | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 1.1.5 Prepare policy recommendations & develop roadmap for issuing policies to address these issues | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
| NJP Results | Indicative activities | Q1 | Q2 | Q3 | Q4 | Implementing Partner | Source of funding | Budget description | - |
|  |  |  |  |  |  |  |  | Other direct costs |  |
| Outcome 2: Successful demonstration of establishing a REL, MRV and fair payment systems based on the national REDD architecture |  |  |  |  |  |  |  |  |  |
| 1.2 REDD lessons learned | 1.2.1 Establish national knowledge & learning network | - | - | X | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 1.2.2 Collaboration with projects to stimulate coordination and joint learning (incl Small Grants Programme) | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 1.2.3 Organize joint workshops | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | 20,000 |
|  |  |  |  |  |  |  |  | Contracts | 30,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 1.2.4 Prepare publication on lessons learned | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 30,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
| 1.3 Communications Programme | 1.3.1 Agree on target messages, target groups and national partners | - | - | X | - |  |  | Personnel | 3,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 12,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 1.3.2 Design awareness impact monitoring system, establishing baseline, and assessing impact at completion | - | - | X | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 35,000 |
|  |  |  |  |  |  |  |  | Other direct costs | 5,000 |
|  | 1.3.3 Design of social marketing campaign, focus on high level government decision makers, as well as local resource users in the pilot districts | - | - | - | X |  |  | Personnel | 4,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 32,000 |
|  |  |  |  |  |  |  |  | Other direct costs | 5,000 |
|  | 1.3.4 Develop REDD information, education and communication materials | - | - | - | X |  |  | Personnel | 1,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 14,000 |
|  |  |  |  |  |  |  |  | Other direct costs | 40,000 |
|  | 1.3.5 Conduct national communications campaign targeting one or two drivers of deforestation (incl. high-level GoI - UN conference or panel in JKT) | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 1.3.6 Conduct training on REDD -emphasize local level actors | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 25,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
| Outcome 2: Successful demonstration of establishing a REL, MRV and fair payment systems based on the national REDD architecture | Indicative activities | Q1 | Q2 | Q3 | Q4 | Implementing Partner | Source of funding | Budget description |  |
| 2.1 Improved capacity and methodology design for forest carbon inventory within a Monitoring, Assessment, Reporting and Verification System (MRV), including sub-national pilot implementation | 2.1.1 Review on existing standards and methodologies in MRV at national and sub-national levels; | - | - | X | X | MoFor/GoI | MDTF | Personnel | 10,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport |  |
|  |  |  |  |  |  |  |  | Contracts | 10,000 |
|  |  |  |  |  |  |  |  | Other direct costs |  |
|  | 2.1.2 Development of measurement protocols and sampling design for a national forest carbon inventory with reporting capability at provincial level, building on the existing Indonesian national forest inventory system; | - | - | X | X |  |  | Personnel | 25,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport |  |
|  |  |  |  |  |  |  |  | Contracts | 25,000 |
|  |  |  |  |  |  |  |  | Other direct costs |  |
|  | 2.1.3 Implementation of the forest carbon inventory in pilot provinces to assess carbon stock and carbon stock changes; | - | - | - | X |  |  | Personnel |  |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | 60,000 |
|  |  |  |  |  |  |  |  | Contracts |  |
|  |  |  |  |  |  |  |  | Other direct costs | 10,000 |
|  | 2.1.4 Development of methods for Reporting and Verification at sub-national level, consistent with national reporting requirements; | - | - | - | X |  |  | Personnel | 10,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport |  |
|  |  |  |  |  |  |  |  | Contracts | 10,000 |
|  |  |  |  |  |  |  |  | Other direct costs |  |
|  | 2.1.5 Implementation of Reporting and Verification in pilot provinces | - | - | - | - |  |  | Personnel |  |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport |  |
|  |  |  |  |  |  |  |  | Contracts |  |
|  |  |  |  |  |  |  |  | Other direct costs |  |
| Outcome 2: Successful demonstration of establishing a REL, MRV and fair payment systems based on the national REDD architecture | Indicative activities | Q1 | Q2 | Q3 | Q4 | Implementing Partner | Source of funding | Budget description |  |
| Outcome 2: Successful demonstration of establishing a REL, MRV and fair payment systems based on the national REDD architecture | 2.1.6 Workshop: Identification of additional data needs concerning socioeconomic aspect in MRV Training in monitoring and assessment methodology (with AusAid) | - | - | - | X |  |  | Personnel | 10,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | 25,000 |
|  |  |  |  |  |  |  |  | Contracts | 5,000 |
|  |  |  |  |  |  |  |  | Other direct costs | 10,000 |
| 2.2 Reference emissions level (REL) proposed at the provincial level | 2.2.1 Review of methodologies for establishing REL at national and sub-national level | - | - | X | X |  |  | Personnel | 10,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport |  |
|  |  |  |  |  |  |  |  | Contracts | 10,000 |
|  |  |  |  |  |  |  |  | Other direct costs |  |
|  | 2.2.2 Development of methodological options to establish REL at national and sub-national scale | - | - | - | X |  |  | Personnel | 10,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport |  |
|  |  |  |  |  |  |  |  | Contracts | 10,000 |
|  |  |  |  |  |  |  |  | Other direct costs | 5,000 |
|  | 2.2.3 Compilation of data to support development of REL | - | - | - | X |  |  | Personnel | 10,000 |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | 10,000 |
|  |  |  |  |  |  |  |  | Contracts |  |
|  |  |  |  |  |  |  |  | Other direct costs |  |
|  | 2.2.4 Assessment of a provisional REL in a pilot province | - | - | - | - |  |  | Personnel |  |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport |  |
|  |  |  |  |  |  |  |  | Contracts |  |
|  |  |  |  |  |  |  |  | Other direct costs |  |
|  | 2.2.5 Scientific peer review of provisional REL | - | - | - | - |  |  | Personnel |  |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport |  |
|  |  |  |  |  |  |  |  | Contracts |  |
|  |  |  |  |  |  |  |  | Other direct costs |  |
|  | 2.2.6 Stakeholder consultations on REL methodological approach and provincial provisional REL | - | - | - | - |  |  | Personnel |  |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport |  |
|  |  |  |  |  |  |  |  | Contracts |  |
|  |  |  |  |  |  |  |  | Other direct costs |  |
|  | 2.2.7 Scientific peer review of REL methodological approach and provincial provisional REL | - | - | - | - |  |  | Personnel |  |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport |  |
|  |  |  |  |  |  |  |  | Contracts |  |
|  |  |  |  |  |  |  |  | Other direct costs |  |
| 2.3 Harmonized fair and equitable payment mechanism at provincial level | 2.3.1 Compilation existing payment systems | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 2.3.2 Analysis/review of benefits and constraints of existing systems | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 2.3.3 Options for modifications to meet requirements of a REDD payment system | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 10,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 2.3.4 Stakeholder consultations | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 15,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 2.3.5 Integration of modifications to create a REDD payment system | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 2.3.6 Training of local institutions | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
| 2.4 Toolkit for priority setting towards maximizing potential Carbon-benefits and incorporating co-benefits, at the provincial level | 2.4.1 Reach agreement in Indonesia on partner agencies, data sources, GIS development and site selection criteria | - | - | X | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 10,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 2.4.2 Development and testing of the Priority Setting Toolkit (including short manual) | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 30,000 |
|  |  |  |  |  |  |  |  | Other direct costs | 5,000 |
|  | 2.4.3 Mapping of below- & above-ground carbon, inside and outside the Forest Estate, based on existing data sources and linkages to NCAS/FRIS (a. national reconnaissance level; b. detailed pilot province level) (linked to FAO 2.1 & 2.2) | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | 10,000 |
|  |  |  |  |  |  |  |  | Contracts | 35,000 |
|  |  |  |  |  |  |  |  | Other direct costs | 5,000 |
|  | 2.4.4 Overlay mapping and analysis co-benefits (minimally: biodiversity, water resources, pockets of poverty, others) - level a. and b. (one province only) | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | 10,000 |
|  |  |  |  |  |  |  |  | Contracts | 40,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 2.4.5 (GIS) Training of provincial staff in use of Priority Setting Tool | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 2.4.6 Workshop on how to translate and integrate the results into local spatial planning process, national REDD policy, and decision taking | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
| Outcome 3: Capacity established to implement REDD at decentralized levels | Indicative activities | Q1 | Q2 | Q3 | Q4 | Implementing Partner | Source of funding | Budget description |  |
| 3.1 Capacity for spatial socio-economic planning incorporating REDD at the district level | 3.1.1 Develop a comprehensive baseline dataset and identify areas of REDD-eligible forest | - | - | - | X | MoFor/GoI | MDTF | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 40,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.1.2 Analyze opportunity costs of alternative land uses | - | - | - | - | MoFor/GoI | MDTF | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.1.3 Analyze the potential socio-economic impacts of REDD on communities | - | - | - | - | MoFor/GoI | MDTF | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.1.4 Mainstream REDD into existing spatial, forest utilization and FMU planning at District level | - | - | - | - | MoFor/GoI | MDTF | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.1.5 District based consensus on land – and forest use allocation, | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.1.6 Approve the REDD mainstreamed spatial plan | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
| 3.2 Empowered local stakeholders are able to benefit from REDD | 3.2.1 Capacity needs assessment | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 30,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.2.2 Design of capacity building & training | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.2.3 Training of trainers | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.2.4 Conduct of training and other capacity building activities | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.2.5 Assessment of follow-up activities required to improve and sustain capacity | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
| 3.3 Multi-stakeholder-endorsed District plans for REDD implementation | 3.3.1 Assess five districts in which REDD is most feasible | - | - | - | X |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | 50,000 |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.3.2 Socialize REDD to these districts | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.3.3 Invite these districts to present their proposals and ensure political readiness to implement REDD | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  | 3.3.4 Agree with the selected district on an implementation framework. | - | - | - | - |  |  | Personnel | - |
|  |  |  |  |  |  |  |  | Supplies, commodities, equipment and transport | - |
|  |  |  |  |  |  |  |  | Contracts | - |
|  |  |  |  |  |  |  |  | Other direct costs | - |
|  |  |  |  |  |  |  | UNDP | Programme cost | 495,000 |
|  |  |  |  |  |  |  |  | Indirect support cost | 34,650 |
|  |  |  |  |  |  |  | UNEP | Programme cost | 321,000 |
|  |  |  |  |  |  |  |  | Indirect support cost | 22,470 |
|  |  |  |  |  |  |  | FAO | Programme cost | 265,000 |
|  |  |  |  |  |  |  |  | Indirect support cost | 18,550 |
|  |  |  |  |  |  |  | Subtotals | Programme cost | 1,081,000 |
|  |  |  |  |  |  |  |  | Indirect support cost | 75,670 |
|  |  |  |  |  |  |  | Total 2009 |  | 1,156,670 |

# Annex 1 – Response to the UNREDD Secretariat Note

| No. | UNREDD Secretariat Note | Action |
| --- | --- | --- |
| 1. | The Secretariat supports the approval of the budget allocation by the Policy Board. However, it is recommended that additional stakeholder consultation be undertaken before the NJP is signed and funds are released. This could be supported through the Global Joint Programme for International Support Functions. Should the consultation result in changes to the overall budget request, or aggregate allocations to the Participating UN Agencies, the revised NJP should be circulated for an “inter-sessional” decision by the Policy Board. | A consultation meeting with Indigenous People organizations, Civil Society Organisations, local communities and other stakeholders on UNREDD NJP was conducted on May 20, 2009. The workshop was attended by 32 participants including representatives from Government (MoFor, DNPI), IPs (AMAN, Karsa, KpSHK, and Huma), National NGOs and local community (FKKM, FWI, JKPP, ICEL, individual experts), International NGO (CI, WWF Indonesia, Wetland International, CIFOR, ICRAF), and multilateral organizations (WB, FAO, UNDP). The consultation resulted in some revisions to the Prodoc but did not change the overall direction or budget. A report of the consultation meeting is attached. |

# Annex 2 – CSO Consultation

UN-REDD national Joint Programme Consultation with indigenous peoples’ organizations and Civil Society Organizations

Consultation held in Bogor, 20th May 2009

    - OBJECTIVES

The UN-REDD IP/CSO consultation aimed to provide an opportunity for Indigenous Peoples, local communities and related Civil Society Organizations to be fully informed and to be able to provide feedback about the activities of the Government of Indonesia, and especially the Ministry of Forestry, regarding the UN-REDD National Joint Programme in development.

The objectives of the Consultation were:

- To provide an opportunity for Indigenous Peoples, local communities and related Civil Society Organizations to formulate their own informed positions and strategies regarding UN-REDD, including investigating opportunities and challenges;

- To provide an opportunity for Indigenous Peoples, local communities and related Civil Society Organizations to influence the development and implementation of UN-REDD schemes taking into account biological diversity, their traditional knowledge and their rights;

- To ascertain to the current level of involvement of Indigenous Peoples, local communities and related Civil Society Organizations in the national debate on REDD;

- To allow Indigenous Peoples, local communities and related Civil Society Organizations to become familiar with current capacity building tools and opportunities regarding UN-REDD and to ascertain their own capacity

    - Outputs

The objective of the Consultation was to achieve the following outputs:

- Initial consultation with Indigenous Peoples, local communities and related Civil Society Organizations on the proposed UN-REDD National Joint Programme

- Approved meeting minutes, including proposed revisions to the UN-REDD National Programme Document

- Agreement on follow up consultations by all parties

    - IP/CSO Participant Selection Process

- Selection Criteria

The selection criteria for Indigenous Peoples, local communities and related Civil Society Organizations were as follows:

- Demonstrated experience serving as a representative, receiving input from, consulting with, and providing feedback to, a wide scope of civil society/Indigenous Peoples organizations;

- Having national / regional coverage or networks,

- Selected through a  participatory, consultative process,

- Previous experience working constructively with the government and UN system

- Selection Process

The following IP/CSOs were initially identified through discussion with Ministry of Forestry and UNDP staff:

1. 		FKKM (Community Forestry Forum)

2.		KpSHK (Local Community Forest Groups)

3.		WALHI (Friends of the Earth Indonesia)

4.		Forest Watch Indonesia (FWI)

5.		LATIN (Village forest community development)

6.		Kemala (Natural resource management foundation)

7.		LEI (Lembaga Ekolabel Indonesia / Ecolabel SFM)

8.		Telapak-EIA (Investigation and campaign against illegal logging)

9.		NTFP Indonesia (Non timber forest product production and market)

10.	JKPP (Jaringan Kerja Pemetaan Partisipatif/ Participatory mapping development)

11.	IHSA (Institut Hukum Sumberdaya Alam/ National Resource Law)

12.	AMAN (Aliansi Masyarakat Adat Nasional)

13. 	WWF (World Wildlife Fund)

14.	TNC (The Nature Conservancy)

Next, three major organizations (AMAN, TNC and WWF) were asked about their thinking on the above list. All three organizations agreed with the above invitees and further suggested the following:

WWF Suggestions:

- Walhi

- Greenpeace

- AMAN

- CI

- TNC

AMAN Suggestions:

- HuMA

- KARSA

- ICEL

- CSF

TNC Suggestions:

- Carbon and Environmental Researches Indonesia (CER INDONESIA)

All the resulting potential participants were invited either by email or telephone. In addition to IP/CSO representatives, the consultation was attended by stakeholders involved in climate change, forest management, deforestation, forest degradation, and community development, government institutions and field practitioners of sustainable natural and forest resources management. The World Bank was invited in anticipation of synergy between UN-REDD and FCPF, for instance the potential for future joint UN-REDD/FCPF consultations.

- Full list of Consultation Attendees

The actual participants to the consultation were as follows:

- Government:Ministry of Forestry, National Climate Change Council (Dewan Nasional Perubahan Iklim -DNPI);

- Indigenous People Organizations : Indigenous People Alliance of the Archipelago (AMAN-Aliansi Masyarakat Adat Nusantara), Village and Agrarian Reforms Institute (Karsa- Lingkar Pembaruan Pedesaan dan Agraria), Consortium for Supporting Community Based Forest System Management (KpSHK-Kelompok Sistem Hutan Kemasyarakat), HUMA (Community and Ecology Based Legal Reform Organization -Perkumpulan untuk Pembaruan Hukum Berbasis Masyarakat dan Ekologis);

- National Non-government Organizations: Communication Forum on Community Forestry (FKKM-Forum Komunikasi Kehutanan Masyarakat), Forest Watch Indonesia, Participatory Mapping Working Network (JKPP-Jaringan Kerja Pemetaan Partisipatif), Indonesian Center for Environmental Law (ICEL);

- International Non-government Organizations: Conservation International, WWF Indonesia, Wetland International, CIFOR, ICRAF.

- Multilateral Organizations: World Bank, FAO, and UNDP.

    - Agenda and Consultation Method

  - Agenda

The consultation was divided into morning and afternoon sessions. The morning session intended to provide the participants with an overview of UN-REDD and its proposed activities. The afternoon session was designed to allow the participants to debate and discuss the proposed activities at a deeper level. To facilitate this discussion, the participants were separated into two groups, Group 1 covering Outcome 1 and 2 of the UN-REDD Programme Document, and Group 2 covering Outcome 2. The participants could choose the group of their choice. The division was intended to reflect the relative technical aspects of Outcome 2, while Group 1 would deal with the more general socio-economic issues of REDD.

AGENDA FOR UN-REDD JPD CONSULTATION

| Time | Activities | Remarks |
| --- | --- | --- |
| First Session: Registration of participants |  |  |
| 08.00 – 09.00 | Pendaftaran peserta (Registration) |  |
| 09.00 – 09.30 | Opening remarks and keynote speech | Mr. Wandojo S |
| 09.30 – 10.00 | Introduction of UN-REDD | UN |
| 10.00 – 10.30 | Coffee Break |  |
| Second Session: GoI and UN-REDD Scheme |  | Moderator: Dr. Hermawan Indrabudhi |
| 10.30 – 11.00 | Presentation: Overview of UN-REDD National Joint Programme | Mr. Yuyu Rahayu |
| 11.00 – 12:00 | Questions and Discussion | Moderator |
| 12:00 - 12:15 | Grouping participants (see below for details) | Panitia |
| 12.15 – 13.30 | LUNCH |  |
| Third Session: UN-REDD Discussion |  | Facilitators: Dr. Ngaloken Ginting and Dr. Machfudh |
| 13.30 – 13.40 | Explanation of working group discussion format | Facilitators |
| 13.20 – 15.00 | Group Discussion (please see page 2 for details) Group 1 : Outcome 1 and 3 (multi-stakeholder strengthening and capacity building) Group 2 : Outcome 2 (REL, MRV and payment systems) | Facilitators Group1: Dr. Ngaloken Ginting Group2: Dr. Machfudh |
| 15.00 – 15.30 | Coffee Break |  |
| 15.30 – 16.30 | Group Presentations and feedback between groups | Moderator and Facilitators |
| 16:30- 17:00 | Final Discussion: Suggestions for UN-REDD, issues on REDD in general etc. | Moderator |
| 17.00- 17:10 | Closing the Consultation | Ministry of Forestry and UN |
| 17:10 onwards | Dinner and informal discussion, networking |  |

  - Discussion Topics

The following discussion topics were encouraged:

- For each Output, discuss each indicative activity according to the following:

  - Issues and concerns, potential problems

  - Possible solutions

  - Applicability and feasibility of potential solutions

  - Propose solution(s), including baseline situation and target for proposed activity

- General topics

  - What are CSO and local communities’ capacity building needs related to REDD?

    - Consultation Minutes

- UN-REDD should build on existing REDD related activities, and not reinvent the wheel.

- The UN-REDD Programme Document will be updated reflecting inputs from the IPs/CSOs consultation.

- It should be ensured that the Project Management Unit is made up of domestic experts/staff. International experts will be recruited only when necessary to support project implementation. This should be reflected in the Programme Document.

- A paragraph describing roles of IPs, CSOs and local communities as stakeholders of UN-REDD should be inserted in the Executive summary of the Prodoc (page 5). This is to show readers level of ownership of the Prodoc NJP by government of Indonesia.

- National Project Board (NPB) members will consist of representative of government, donors, NGOs, CSOs, universities, etc.  A mechanism of selecting a NPB member to represent his/her organization should be based on their own organization representative selection mechanism.

- Initiatives relevant to UNREDD activities developed by IPs, NGOs, CSOs and local communities are good lesson learnt to support UNREDD activities implementation.  Significant lesson learned from the initiatives will be inserted to the logical framework matrix table in pages 28-31 of the UN-REDD Programme Document. Inclusion of the initiatives in the Programme Document to bring it practical is to increase ownership level of the project by various stakeholders.

- On the consultation process:

  - It was agreed that results from this Consultation will be reflected into the project document, and also that this consultation will serve to discuss the framework for an effective consultation process for future UN-REDD consultations. Consultation with broader stakeholders (including IPs, CSOs, local communities, etc) should be continued during the implementation of the project

  - It was suggested that CSOs or other grass root based institutions should be the focal point in leading IPs, CSOs and other stakeholder consultations at national and sub national levels.

- On demonstration site selection:

  - Location for the exact demonstration project site is still flexible

  - The site should consider levels of degradation (high, average and low degradation). Sulawesi does not have high levels of deforestation

  - The site selection process should be conducted carefully

- On communication:

  - The project is strongly encouraged to strengthen communication among UNREDD stakeholders through various media such as bulletins, websites, mailing list, etc. (page 22). It is suggested that FWI might be one of the node of the communication strengthening activity.

  - Strengthening communication between IPs/NGOs/CSOs and local government / palm plantation companies is strongly encouraged.

- Page 21: Output 1.2 (REDD lessons learned); the project is encouraged to develop a small grant programs following the SGPPTF format, and this should be a top priority activity.

- Page 24: In the activity of a compilation of information on existing payment systems, it should be stated to include existing payment system in Indonesia and abroad.

- Page 24: Process of consultation mentioned in the activity of stakeholder consultations on proposed modifications, should be conducted in various consultation forms including workshops.

- Page 26: Regarding Output 3.1 (Capacity for spatial socio-economic planning incorporating REDD at the district level), the following issues should be analyzed:

  - The baseline of socio-economic situation in the area to develop REDD

  - Impact of implementation of REDD in an area such as on income generation options of local communities.

  - How to include REDD into local spatial plans,

It is suggested that the UNREDD Prodoc to include the following activities: development of baseline related with socio-economic planning for REDD, trainings on spatial planning for REDD, intensifying consultations/meetings with local stakeholders

- Page 27: Output 3.3 (Multi-stakeholder-endorsed District plans for REDD implementation) should include activities:

- Training needs assessment

- Develop guidelines and material for training

- Provide facilitators for local governments at UN-REDD Secretariat

    - Consultation Result Dissemination and Next Steps

The initial consultation minutes were developed by UN-REDD, reviewed and finalized by the UN Agencies and the MoFor, and then distributed by email to the IP/CSO participants for further input. There have been no negative responses to the minutes so far.

Comments from the consultation are being reflected into the National Joint Programme document, and once revised the document will be distributed to the IP/CSO participants for further comment and input.

Adherence to the principles of Free, Prior and Informed Consent of the IP/CSOs have been sought as much as possible, although at this point UN-REDD NJP activities have not been articulated enough to allow issues such as size, pace and reversibility to be debated in a meaningful manner. For instance, the UN-REDD demonstration (pilot) sites are envisaged to be carried out in Sulawesi, but further work needs to be undertaken (taking into account deforestation rates, socio-economic factors, consultations, willingness of local government to cooperate etc.) for exact locations to be specified.

All parties present in the consultation agreed that the UN-REDD consultation process should continue, and therefore this consultation should be ‘one step of a wider consultation and engagement strategy’, as suggested in the UN-REDD Programme IP engagement guidelines. Further steps include dissemination of information on the progress of the UN-REDD NJP shared with the IP/CSOs via email, and further face-to-face consultations regarding detailed UN-REDD activities. Further, reflecting the comments from the consultation, the NJP will prioritize the development of a small scale lessons learned Small Grants Facility for IP/CSOs. This will also serve as a consultation at a more general level.

# Annex 3 – Legal Context UNDP

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document.

(a) The Revised Basic Agreement for Technical Assistance signed 29 October 1954 between the United Nations, the International Labour Organisation, the Food and Agriculture Organisation of the United Nations, the United Nations Educational, Scientific and Cultural Organisation, the International Civil Aviation Organisation, and the World Health Organisation and the Government of the Republic of Indonesia,

(b) The Standard Agreement on Operational Assistance signed 12 June 1969 between the United Nations, the International Labour Organisation, the Food and Agriculture Organisation of the United Nations, the United Nations Educational, Scientific and Cultural Organisation, the International Civil Aviation Organisation, the World Health Organisation, the International Telecommunication Union, the World Meteorological Organisation, the International Atomic Energy Agency, the Universal Postal Union, the Inter-Governmental Maritime Consultative Organisation and the United Nations Industrial Development Organisation and the Government of the Republic of Indonesia,

(c) The Agreement signed 7 October 1960 between the United Nations Special Fund and the Government of the Republic of Indonesia, and

(d) all CPAP provisions apply to this document.

Additionally, this document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together the instrument envisaged in the Supplemental Provisions to the Project Document, attached hereto as Annex __.

Consistent with the above Supplemental Provisions, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

  - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

  - assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document. ”

# Annex 4 –Supplemental Provisions

Standard annex to project documents for use in countries, which are not parties to the Standard Basic Assistance Agreement (SBAA)

Standard Text: Supplemental Provisions to the Project Document

The Legal Context

General responsibilities of the Government, UNDP and the executing agency

- All phases and aspects of UNDP assistance to this project shall be governed by and carried out in accordance with the relevant and applicable resolutions and decisions of the competent United Nations organs and in accordance with UNDP's policies and procedures for such projects, and subject to the requirements of the UNDP Monitoring, Evaluation and Reporting System.

- The Government shall remain responsible for this UNDP-assisted development project and the realization of its objectives as described in this Project Document.

- Assistance under this Project Document being provided for the benefit of the Government and the people of Indonesia, the Government shall bear all risks of operations in respect of this project.

- The Government shall provide to the project the national counterpart personnel, training facilities, land, buildings, equipment and other required services and facilities. It shall designate the Government Co-operating Agency named in the cover page of this document (hereinafter referred to as the "Co-operating Agency"), which shall be directly responsible for the implementation of the Government contribution to the project.

- The UNDP undertakes to complement and supplement the Government participation and will provide through the Executing Agency the required expert services, training, equipment and other services within the funds available to the project.

- Upon commencement of the project the Executing Agency shall assume primary responsibility for project execution and shall have the status of an independent contractor for this purpose. However, that primary responsibility shall be exercised in consultation with UNDP and in agreement with the Co-operating Agency. Arrangements to this effect shall be stipulated in the Project Document as well as for the transfer of this responsibility to the Government or to an entity designated by the Government during the execution of the project.

- Part of the Government's participation may take the form of a cash contribution to UNDP. In such cases, the Executing Agency will provide the related services and facilities and will account annually to the UNDP and to the Government for the expenditure incurred.

(a) Participation of the Government

- The Government shall provide to the project the services, equipment and facilities in the quantities and at the time specified in the Project Document. Budgetary provision, either in kind or in cash, for the Government's participation so specified shall be set forth in the Project Budgets.

- The Co-operating Agency shall, as appropriate and in consultation with the Executing Agency, assign a director for the project on a full-time basis. He shall carry out such responsibilities in the project as are assigned to him by the Co-operating Agency.

- The estimated cost of items included in the Government contribution, as detailed in the Project Budget, shall be based on the best information available at the time of drafting the project proposal. It is understood that price fluctuations during the period of execution of the project may necessitate an adjustment of said contribution in monetary terms; the latter shall at all times be determined by the value of the services, equipment and facilities required for the proper execution of the project.

- Within the given number of man-months of personnel services described in the Project Document, minor adjustments of individual assignments of project personnel provided by the Government may be made by the Government in consultation with the Executing Agency, if this is found to be in the best interest of the project. UNDP shall be so informed in all instances where such minor adjustments involve financial implications.

- The Government shall continue to pay the local salaries and appropriate allowances of national counterpart personnel during the period of their absence from the project while on UNDP fellowships.

- The Government shall defray any customs duties and other charges related to the clearance of project equipment, its transportation, handling, storage and related expenses within the country. It shall be responsible for its installation and maintenance, insurance, and replacement, if necessary, after delivery to the project site.

- The Government shall make available to the project - subject to existing security provisions - any published and unpublished reports, maps, records and other data which are considered necessary to the implementation of the project.

- Patent rights, copyright rights and other similar rights to any discoveries or work resulting from UNDP assistance in respect of this project shall belong to the UNDP. Unless otherwise agreed by the Parties in each case, however, the Government shall have the right to use any such discoveries or work within the country free of royalty and any charge of similar nature.

- The Government shall assist all project personnel in finding suitable housing accommodation at reasonable rents.

- The services and facilities specified in the Project Document which are to be provided to the project by the Government by means of a contribution in cash shall be set forth in the Project Budget. Payment of this amount shall be made to the UNDP in accordance with the Schedule of Payments by the Government.

- Payment of the above-mentioned contribution to the UNDP on or before the dates specified in the Schedule of Payments by the Government is a prerequisite to commencement or continuation of project operations.

(b) Participation of the UNDP and the executing agency

- The UNDP shall provide to the project through the Executing Agency the services, equipment and facilities described in the Project Document. Budgetary provision for the UNDP contribution as specified shall be set forth in the Project Budget.

- The Executing Agency shall consult with the Government and UNDP on the candidature of the Project Manager a/ who, under the direction of the Executing Agency, will be responsible in the country for the Executing Agency's participation in the project. The Project Manager shall supervise the experts and other agency personnel assigned to the project, and the on-the-job training of national counterpart personnel. He shall be responsible for the management and efficient utilization of all UNDP-financed inputs, including equipment provided to the project.

- The Executing Agency, in consultation with the Government and UNDP, shall assign international staff and other personnel to the project as specified in the Project Document, select candidates for fellowships and determine standards for the training of national counterpart personnel.

- Fellowships shall be administered in accordance with the fellowships regulations of the Executing Agency.

- The Executing Agency may, in agreement with the Government and UNDP, execute part or all of the project by subcontract. The selection of subcontractors shall be made, after consultation with the Government and UNDP, in accordance with the Executing Agency's procedures.

- All material, equipment and supplies which are purchased from UNDP resources will be used exclusively for the execution of the project, and will remain the property of the UNDP in whose name it will be held by the Executing Agency. Equipment supplied by the UNDP shall be marked with the insignia of the UNDP and of the Executing Agency.

- Arrangements may be made, if necessary, for a temporary transfer of custody of equipment to local authorities during the life of the project, without prejudice to the final transfer.

- Prior to completion of UNDP assistance to the project, the Government, the UNDP and the Executing Agency shall consult as to the disposition of all project equipment provided by the UNDP. Title to such equipment shall normally be transferred to the Government, or to an entity nominated by the Government, when it is required for continued operation of the project or for activities following directly therefrom. The UNDP may, however, at its discretion, retain title to part or all of such equipment.

- At an agreed time after the completion of UNDP assistance to the project, the Government and the UNDP, and if necessary the Executing Agency, shall review the activities continuing from or consequent upon the project with a view to evaluating its results.

- UNDP may release information relating to any investment oriented project to potential investors, unless and until the Government has requested the UNDP in writing to restrict the release of information relating to such project.

Rights, Facilities, Privileges and Immunities

- In accordance with the Agreement concluded by the United Nations (UNDP) and the Government concerning the provision of assistance by UNDP, the personnel of UNDP and other United Nations organizations associated with the project shall be accorded rights, facilities, privileges and immunities specified in said Agreement.

- The Government shall grant UN volunteers, if such services are requested by the Government, the same rights, facilities, privileges and immunities as are granted to the personnel of UNDP.

- The Executing Agency's contractors and their personnel (except nationals of the host country employed locally) shall:

- Be immune from legal process in respect of all acts performed by them in their official capacity in the execution of the project;

- Be immune from national service obligations;

- Be immune together with their spouses and relatives dependent on them from immigration restrictions;

- Be accorded the privileges of bringing into the country reasonable amounts of foreign currency for the purposes of the project or for personal use of such personnel, and of withdrawing any such amounts brought into the country, or in accordance with the relevant foreign exchange regulations, such amounts as may be earned therein by such personnel in the execution of the project;

- Be accorded together with their spouses and relatives dependent on them the same repatriation facilities in the event of international crisis as diplomatic envoys.

- All personnel of the Executing Agency's contractors shall enjoy inviolability for all papers and documents relating to the project.

- The Government shall either exempt from or bear the cost of any taxes, duties, fees or levies which it may impose on any firm or organization which may be retained by the Executing Agency and on the personnel of any such firm or organization, except for nationals of the host country employed locally, in respect of:

- The salaries or wages earned by such personnel in the execution of the project;

- Any equipment, materials and supplies brought into the country for the purposes of the project or which, after having been brought into the country, may be subsequently withdrawn therefrom;

- Any substantial quantities of equipment, materials and supplies obtained locally for the execution of the project, such as, for example, petrol and spare parts for the operation and maintenance of equipment mentioned under (b), above, with the provision that the types and approximate quantities to be exempted and relevant procedures to be followed shall be agreed upon with the Government and, as appropriate, recorded in the Project Document; and

- As in the case of concessions currently granted to UNDP and Executing Agency's personnel, any property brought, including one privately owned automobile per employee, by the firm or organization or its personnel for their personal use or consumption or which after having been brought into the country, may subsequently be withdrawn there from upon departure of such personnel.

- The Government shall ensure:

- prompt clearance of experts and other persons performing services in respect of this project; and

- the prompt release from customs of:

  - equipment, materials and supplies required in connection with this project; and

  - property belonging to and intended for the personal use or consumption of the personnel of the UNDP, its Executing Agencies, or other persons performing services on their behalf in respect of this project, except for locally recruited personnel.

- The privileges and immunities referred to in the paragraphs above, to which such firm or organization and its personnel may be entitled, may be waived by the Executing Agency where, in its opinion or in the opinion of the UNDP, the immunity would impede the course of justice and can be waived without prejudice to the successful completion of the project or to the interest of the UNDP or the Executing Agency.

- The Executing Agency shall provide the Government through the resident representative with the list of personnel to whom the privileges and immunities enumerated above shall apply.

- Nothing in this Project Document or Annex shall be construed to limit the rights, facilities, privileges or immunities conferred in any other instrument upon any person, natural or juridical, referred to hereunder.

Suspension or termination of assistance

- The UNDP may by written notice to the Government and to the Executing Agency concerned suspend its assistance to any project if in the judgement of the UNDP any circumstance arises which interferes with or threatens to interfere with the successful completion of the project or the accomplishment of its purposes. The UNDP may, in the same or a subsequent written notice, indicate the conditions under which it is prepared to resume its assistance to the project. Any such suspension shall continue until such time as such conditions are accepted by the Government and as the UNDP shall give written notice to the Government and the Executing Agency that it is prepared to resume its assistance.

- If any situation referred to in paragraph 1, above, shall continue for a period of fourteen days after notice thereof and of suspension shall have been given by the UNDP to the Government and the Executing Agency, then at any time thereafter during the continuance thereof, the UNDP may by written notice to the Government and the Executing Agency terminate the project.

- The provisions of this paragraph shall be without prejudice to any other rights or remedies the UNDP may have in the circumstances, whether under general principles of law or otherwise.

Ministry of Forestry. 2008: Reducing Emissions from Deforestation and Forest Degradation. IFCA Consolidation Report. www.forda-mof.org

Kanninen, M. Murdiyarso, D., Seymor, F. Angelsen,A., Wunder, S., and German, L. Do Trees Grow on Money? CIFOR’s INFO BRIEF. No. 14, November 2008.

Pusat Inventarisasi dan Perpetaan Hutan, Departemen Kehutanan. 2008. Perhitungan Deforestasi Indonesia Tahun 2008. Pusat Inventarisasi dan Perpetaan Hutan, Departemen Kehutanan. 2008: Rekalkulasi Penutupan Lahan Indonesia Tahun 2008. Available at http://www.dephut.go.id/.

Departemen Kehutanan. 2005. Rencana Strategis Kementerian Negara/Lembaga Departemen Kehutanan Tahun 2005-2009.

See http://www.greenhouse.gov.au/ncas/ncat for more information on NCAS as developed by the Australia Department of Climate Change

F. Sitorus, 2002 “Revolusi Coklat” Social formation, agrarian structure and forest margins in Upland Sulawesi, STORMA discussion paper 9. 19p

J. Kerr, Suyanto, J. Pender, and B. Leimona, 2008. PROPERTY RIGHTS, ENVIRONMENTAL SERVICES AND POVERTY ALLEVIATION IN INDONESIA. Basic Brief 2008-03

See http://www.birdlife.org/action/ground/sumatra/index.html

Hairiah K and Rahayu S. 2007. Pengukuran karbon tersimpan di berbagai macam penggunaan lahan. Bogor, Indonesia. World Agroforestry Centre - ICRAF, SEA Regional Office. 77 p.

KpSHK, 2009. Indonesia’s Peat Land Community Festival. See http://kajidirilebihdalamlagi.blogspot.com/2009/02/indonesias-peat-land-community-festival.html

Pusat Inventarisasi dan Perpetaan Hutan. 2008.  Rekalkulasi Penutupan Lahan Indonesia Tahun 2008. Badan Planologi Kehutanan, Departemen Kehutanan.

Ingolf Steffan-Dewenter  et al., 2007  Tradeoffs between income, biodiversity, and

ecosystem functioning during tropical rainforest conversion and agroforestry intensification

PNAS  104  (12) p 4973–4978

F. Sitoris, 2002 “Revolusi Coklat” Social formation, agrarian structure and forest margins in Upland Sulawesi, STORMA discussion paper 9. 19p

CARE, 2005. PTF ECML monitor data, Unpublished

http://www.undg.org/docs/2791/3599-Annex_C__Operational_details_for_pass-through_fund_management_for_joint_programmes_-_English_version.pdf

See: www.undg.org/.../4554-Finalized_Guidance_Note_on_Joint_Programming__main_text_only__-_English_version.doc

May also be designated Project Co-ordinator or Chief Technical Adviser, as appropriate.