## Slide 1: Benefit Distribution System Consultation Plan
Sub-technical Working Group on BDS
28 April 2011

## Slide 2: Benefit Distribution for REDD+
There is general consensus in the international REDD+ community that the benefits of REDD+ implementation should largely be for the local population
Providing real benefits from forest protection and enhancement will increase stakeholder participation in better managing the forest
Reduction of poverty in forest-dependent communities helps reduce the pressure on the forest
Stakeholders have to be consulted in order to have a generally acceptable system for all

## Slide 3: Stakeholder consultation plan
Step 1: Seek endorsement for the plan
  All relevant stakeholders should have an option to discuss the consultation plan
  National REDD Network
  Consult with local stakeholders
Step 2: Update the consultation plan
  Involve stakeholders that are interested
Step 3: Contract an NGO for implementation
  NGO should have wide presence in Vietnam and good relationship and experience with local communities

## Slide 4: Stakeholder consultation plan
Step 4: National governmental workshop
  Seek support from various Ministries and State Agencies for the consultation plan and the BDS itself
  Overview of regulatory context and gaps
  Mandates of Government Agencies
Step 5: National NGO workshop
  Current activities on BDS from donors, CSOs and NGOs
  Identification of key organizations and their expertise and potential mandates

## Slide 5: Stakeholder consultation plan
Step 6 and 8: Local consultation in North and South Vietnam
  Consult with villagers on the BDS
  Different types of villages
    Experience with REDD (mainly Lam Dong province)
    Experience with other PES (Lam Dong, Son La)
    No experience with REDD or PES)
Step 7 and 9: Provincial consultation in North and South Vietnam
  Seek the views of the PPC and provincial government agencies
  Integration of BDS into other provincial strategies and funds
  Mandates of the different State Agencies at provincial level

## Slide 6: Stakeholder consultation plan
Step 10: Update the BDS documents
  On the basis of comments received during the entire process
Step 11: National workshop
  For all stakeholders
  Discuss the updated BDS documents
Step 12: Finalization of the BDS documents
  Compile all comments etc into a new set of BDS documents
  Final document will be submitted to the Government
The entire process should be completed by August or September 2011