## Sheet1
Update on national level REDD preparedness activities
| 1. Land use, forest policy and governance quick assessment | 2. Management of Readiness | 3. Design REDD strategy | 4. REDD implementation framework and payment mechanism | 5. Assess the social and environmental impacts of candidate REDD strategy activities | 6.Assess investment and capacity building requirements | 7.Develop a reference scenario of deforestation and degradation | 8.Design and implement a monitoring, reporting and verification system for REDD | 9.Design a system of management, implementation, and evaluation of Readiness preparation activities (optional)
Analysis | 1. IFCA has included an assessment on land use/land use change and forest governance 2. CIFOR has conducted an in depth assessment of drivers of deforestation 3. ICRAF has recently published a study within the framework of ASB which looks at the development of swidden systems and how they impact the landscape | The MOF is taking the lead on Readiness management | 1. IFCA was meant to be the key stakeholder group to work alongside the MOF to develop a REDD strategy 2. Two working groups (MOF and National Climate Change Council) might become engaged in developing a strategy | 1. BAPPENAS and MOF have started to work on REDD implementation and payment mechanism. 2. AUSAID KFCP is working towards implementing a demonstration activity supporting national framework while GTZ/KfW is working on a district approach 3. The Ulu Masen and potentially other voluntary schemes have developed implementation frameworks which are being looked at 4. USAID is looking at improving mechanism for approval of voluntary projects and related payment systems 5. JICA is working on developing pilots on Sumatra (Jambi/South Sumatra/Riau) focussing on fire prevention and peat land management 6. Japan/French $500m climate change program loan has commenced and first disbursement has been made. Second disbursement depends on the government meeting certain milestones derived from the Yellow Book | 1. ICRAF is working on a rights to carbon initiative which looks at whether the poor can make claims to carbon benefits (ALLREDDI which will start in January 2009 and is funded by the EC) 2. KfW/GTZ has identified possible social economic development impacts from a district based REDD approach. 3. AUSAID FIREWATCH is working on improved fire control 4. Work on improved peat land management 5. voluntary project have a strong focus on biodiversity conservation | No comprehensive analysis of readiness cost has been done. | 1 No principal decision yet on future (model based) or historic emissions scenarios. 2. AUSAID NCAS/FRIS to develop monitoring infrastructure. Existing data based on forest resource inventories done every 5 years 3 . Peat land related emissions remain a source of uncertainty and define to a significant the total forestry based emissions 4 No work of defining reference emissions, needed to be backed up by science. Setting ref scenario is a political decision (up to the gov/MOF). 5. Second National Communication done by MOE, however National council on CC will play a key role as UNFCCC focal point 6. JICA is in the process to fund a project with UNPAR on peat land rehab. 7. Investment of district reference emission level | 1. The draft ministerial degree provides an outline 2. The AUSAID NCAS/FRIS project are leading to develop the necessary infrastructure through the development to GHG/carbon monitoring tools. This provides the corner stone to measure reduced GHG at different levels amongst other project and district level. KFCP acts as a demonstration site where the national systems are piloted | no
Multi Stakeholder consultation | IFCA has conducted a consultation with regards to the outcome of the study | 1.Kemitraan has initiated a multi stakeholder process in Kalimantan and Siak, Riau province 2.A workgroup is in the process of being established by MOF and will be official after the REDD regulation is signed 3.Provincial REDD working groups have been set up | 1.IFCA organized initial stakeholder meeting but the strategy is not finalized 2.Accountability and local level initiative to reduce emission from deforestation and degradation in Indonesia (ALLREDDI): EC through ICRAF (will start 2009). | 1.The MOF organized a multi stakeholder meeting on the draft REDD regulation. 2. Draft regulation was presented during REDD meeting in the World Bank 3. Investments in demonstration activities/payment mechanism (for 3-4 districts) | ITTO-MoF: Community based tropical forest conservation to mitigate carbon emission through public-private partnership. | KfW/GTZ consulting services for implementation | AUSAID NCAS and FRIS have been presented and discussed in multi stakeholder workshop in September | see note on draft ministerial degree public consultation process | no
capacity building | IFCA has worked extensively with FORDA The ICRAF work has been developed within the framework of the FORDA | 1.GTZ is working with MOF within the framework of their capacity building project 2.IFCA issued the REDDI report before the COP 13 in Bali which provides an outline towards how to become ready for 2012 3. Finnish aid is assessing possible assistance | No official strategy launched. Candidate activities are underway through pilot projects as well as voluntary market initiatives GTZ/KFW to test different scenarios in different districts to seek most optimal REDD pathways | -KfW/GTZ to provide consultation services to implementation, fund management, tendering etc | ICRAF is in the process of commencing a project of fair and efficient REDD value chains | None | 1 AUSAID NCAS/FRIS 2. GTZ has been working on capacity building within the framework of the Ministry of Forestry Capacity Building project | Insofar none | no