Work plan for the PGA in Vietnam January-June 2014;

towards a PGA report launch by the end of June

| Activity | Date | Place | Responsible |
| --- | --- | --- | --- |
| January - Review process to date and agree on way forward; discuss main governance issues and new PGA organizational structure (introducing an Expert Group) | 7/1 | Lam Dong | Provincial Working Group (PWG) Facilitated by the PGA Coordinator |
| February - Consult Provincial Working Group (PWG) on the proposed new set of governance issues | 21/01 10/02 |  | Provincial Working Group individual (PWG) |
| - Discuss and finalize selection on governance issues based on PWG inputs | 14/02 | Hanoi | Expert Group (EG) meeting (Skype) Facilitated by the PGA coordinator |
| - Draft an indicator set based on agreed governance issues | Available by 18/02 |  | UN-REDD/ FAO supports the EG technically (RECOFTC is recruited to do this task) PGA Coordinator facilitates |
| - PWG consulted on the draft indicator set (deadline for comments is 22/2) | By 22/02 |  | PWG individual |
| - Conclude on indicator set - Discuss and conclude on data collection methods, data collection instrument (detailed ToR for data collectors) and whom should be conducting the data collection - Conclusions/decisions to be communicated to the PWG for their information | 25/02 | Hanoi | Expert Group meeting(with three representatives from PWG) Technical contributions from UN-REDD PGA Coordinator facilitates |
| March - Develop material for training for data collectors | Available 7/03 |  | UN-REDD/ FAO supports |
| - Consulting Provincial Working Group and Expert Group on the training material | 11/03 |  | EG individual PWG individual |
| - Finalizing training material for data collection (deadline to respond is 12/03) | 12/03 | Hanoi | EG/PWG meeting |
| - Training workshop for data collection team | 15-17/03 | Lam Dong | FAO supports/ facilitate |
| April - Collection of data and data entry | 20/04 – 15/05 | Lam Dong | • Data collection team (Consultant and provincial working group) •FAO supports to review data collected/methods |
| - Recruiting an editorial team to analyse findings and draft the report - Drafting of report with main findings and “red flags” | by mid-April 15/05-20/05 |  | PGA Coordinator Editorial team with participation/ overall coordination from the PGA Coordinator |
| - Present the early draft to Expert Group - New draft based on inputs from | By 24/05 |  | Editorial team With inputs from EG members |
| May - Discuss findings agree on key recommendations for the draft report | 28/05 | Hanoi | EG meeting |
| - Updating the first draft | By 02/06 |  | Editorial team |
| - Validation workshop - Agree on next steps, additional sources if information is lacking, and major edits for the final report | 10/06 | Lam Dong | Expert Group and Provincial Working Group members participate Facilitated by PGA coordinator and with technical contributions from UN-REDD |
| - Revise report according to input from validation workshop - Provide a response matrix and circulate to stakeholders | By 16/06 |  | Editorial team with involvement from the PGA Coordinator |
| - Final approval of the report by Expert Panel | By 20/06 |  | Expert Group - Individual basis |
| June Official launch(es) of the PGA report in Vietnam (Lam Dong and Hanoi) - Expert Group to discuss and agree on further road map for the PGA in Vietnam - Communication of road map to stakeholders in Lam Dong | 24-30/06 |  | Facilitated by the PGA Coordinator in close collaboration with Expert Group members Expert Group members join the meeting – alongside a representative delegation of the PWG |