Teleconference Notes

1 March, 2010

Attendance:

Secretariat: Yemi, Linda, Reem, Cheryl, Clea, Onye

UNDP: Charles, Asako, Nina, Tim C, Estelle

UNEP: Julie, Niklas

FAO: Alberto, Jose Antonio Prado

Agenda

- Update on preparation of national programme documents to be presented at PB4  (15 min)

Progress on status on preparation of documentation:  no completed country yet

  - Bolivia

    - Still waiting for independent technical review (ITR), and still waiting for budget allocation per agency table

  - DRC

    - We have ITR, validation meeting minutes and budget

    - Lack official submission from resident coordinator

    - Waiting for the cover section of the harmonized report

  - Zambia

    - Waiting for ITR, expected COB today

    - Have validation meeting minutes

    - Waiting for official submission from resident coordinator

Overall, key pieces missing in each. If resident coordinator does not submit by March 4th, it will be a problem. Might have to go to inter-sessional decision or ask board to allow late submissions.

Comment: In the case of Bolivia: documentation prepared by Secretariat needs to make that a national forest inventory isn’t expected to be completed with only $700K in funding

Re: Allowing for more time to session 5 (budget allocation) on Policy Board agenda:

Decision: Secretariat will look into spending $3,000 to extend the window on interpretation, so that day one can end an hour later and day two can start an hour earlier.

- PB4 Meeting (30 min)

  - Update on field visit

    - Dry run done, very promising, positive responses.

  - Document mailing

    - First batch of docs to be emailed out today.

  - Confirmation of accommodation

    - Room block is being release between today and tomorrow; won’t be reserved after tomorrow

  - Seminar for new countries

    - Happening Tues, 16 March 6-8.30 pm in Tribe hotel. Objective to meet new countries and present the Programme and hear their expectations, and manage their expectations.

    - All countries are already arriving by Tues afternoon, so budgetary implications are quite small.

    - Alberto and Tim C available have confirmed their participation. Still need to hear from Ravi

Decision: Linda will organize a separate call to discuss a united message for this new countries seminar.

- E-mail from Henning (UNFCCC) regarding perceptions of the UN-REDD Programme by certain countries.

How to proceed?

Decision:

- Alberto will try to get minutes and list of participants from the meeting and will share list with Clea so she can follow up with her contacts in Latin America

- Clea to help gather information, and Yemi will work with Clea to draft a response to Henning

- Update on Year in Review and Next issue of newsletter (5 min)

  - Proposal that next newsletter combine March-April

Decision: The next newsletter will be a march-April issue with results from Policy Board, Paris meeting etc.

  - Year in Review update

- Both FAO and UNDP will push to have agency quotes in by Wednesday deadline.

- Any Other Business

  - Strategy paper feedback: Document is too long to be presented to Policy Board. Needs to be reduced.

Decision: Nicklas (UNEP) will post suggestions on how to cut the document on the workspace COB tomorrow morning.  Other agencies will get their suggested cuts in by Wednesday.

  - Start to think about UN-REDD’s involvement in the formal UNFCCC meeting on April 9th in Bonn.