Teleconference

31 August 2009

- Strategy Paper

Yemi posted updated version on work space for feedback. Issues of phases remained, but were now closer to understanding.

Agreed Action:

- Add national REDD strategy development

- Add summary of products at beginning of chapter on products

- Send to Norway before meetings in New York and Washington by end of this week (either 1st or 2nd of September)

- III Policy Board Meeting

Key issues:

  - There was concern about the unwillingness of FCPF to accommodate the UN-REDD Programme so that it can hold its Policy Board Meeting on October 29 and 30. The optics of the meeting were wrong /need Norway to weigh in to convince Benoit to be more flexible and considerate.

  - Agenda should include run-up to Copenhagen and how UN-REDD board could be more productive, lead-up to Copenhagen, take stock of the first lessons, and order of agenda needs to be strategized

  - Informal consultations should be held with Policy Board members to get support for agenda

  - Many countries once again expressed their desire to join the UN-REDD Programme

  - Policy Board members should have a list of countries interested

  - Particular focus should be given to countries like Ecuador/ The Philippines as they add legitimacy, are not part of FCPF, can be supported in the quick phase, and fits with new strategy

Agreed Action:

  - Yemi to discuss optics of meeting with Benoit to get response

  - Yemi to contact Norway to put pressure on World Bank

  - One option to put to the FCPF is that the UN-REDD Policy Board meets on Monday and Tuesday October 26 and 27.

  - Amock to send list of key decisions from II meeting to Max for review

  - Working Group on National Programmes to meet and report back the week of September 7th on draft letter to be sent to countries interested in joining UN-REDD

  - We should make a strong case to the board regarding the demand to join UN-REDD and that we have not been able to respond positively due to a lack of funding. The PB should be asked to endorse the requests and to further request the secretariat to seek the additional funding.

- Business and Strategic Meeting at GA in NY

Agreed Action:

  - Date for meeting will be September 24-25, 2009

  - Only a couple key players from each agency will be present

  - UNDP to provide meeting room

  - Agenda will focus on Policy Board meeting agenda as a priority, strategic thinking for COP15, and team building exercise to follow Policy Board meeting in October

- Second Newsletter

Positive feedback received on first issue of UN-REDD newsletter, but there is still room for improvement

Key issues:

  - Producing and editing content for website and newsletter, and distribution

Agreed Action:

  - Second newsletter deadline to be pushed back a week from 16 September to after the 23  September

  - Anna helping with editing and finalizing content

- Other Business

  - SG Office to request draft opening remarks from agencies for GA High-Level Event by 4 September