[image: image1.jpg]UN-REDD

PROGRAMME




	Semi-Annual

Report Zambia
National Programme

	21 July 2011

	


Semi-Annual Report Template for the National Programmes
The Semi-Annual Report for the National Programmes, for each six months period ending 31 June (1 January-31 June), should be submitted to the UN-REDD Programme Secretariat no later than one month (31 July) after the end of the applicable reporting period. Prior to submitting the report to the UN-REDD Programme Secretariat (un-redd@un-redd.org), the report should be co-signed by the selected focal point for each participating UN organization, as well as the Government Counterpart. For more background information, roles and responsibilities please refer to the UN-REDD Planning, Monitoring and Reporting Framework Document.
The National Programme semi-annual report draws information from your usual management tools (financial and technical) at the programme and national level to minimize the workload for programme teams. The report is divided into three sections: 1) National Programme Status, 2) National Programme Progress and 3) Government Counterpart Information.

1. National Programme Status
1.1 National Programme Identification
Please identify the National Programme by completing the information requested below. The Government Counterpart and the designated National Programme focal points of the participating UN organisations will also provide their electronic signature below, prior to submission to the UN-REDD Secretariat.
	Date of submission:
Submitted by: 
	
	Country: Republic of Zambia
Title of programme: UN-REDD Programme – Zambia Quick Start Initiative

	
	
	


	Implementing partners
:

Forestry Department of Ministry of Tourism, Environment and Natural Resources
	
	Reporting period: 1st January – 30th  June 2011
Programme duration: 3 years 
Official starting date: September 2009

	
	
	


The financial information reported should include overhead, M&E and other associated costs.
	Financial summary

	Budget

	Total approved National Programme budget

(This information is available on the MDTF Office GATEWAY www.mdtf.undp.org)
	FAO:    US$ 2,180,000
UNDP: US$ 1,995,000

UNEP:  US$ 315,000
Total:   US$4,490,000

	Total amount transferred to date
(This information is available on the MDTF Office GATEWAY www.mdtf.undp.org)
	FAO:US$ 900,192
UNDP:US$ 664,996
UNEP: US$ 120,005
Total: US$ 1,685,193

	Expenditure

	Commitment  to date
(Amount for which legally binding contracts have been signed, including multi-year commitments which may be disbursed in future years)
	FAO:    US$ 72,647

UNDP: US$ 43,997
UNEP:  US$ 0
Total:   US$116,644

	Disbursement to date
(Amount paid to a vendor or entity for goods received, work completed, and/or services rendered (does not include un-liquidated obligations)
	FAO: US$ 7,759
UNDP: US$ 52,854
UNEP: US$ 0
Total: US$ 60,613


	Electronic signatures by the designated UN organization focal points

	Electronic signature by the Government Counterpart

	FAO
	UNDP
	UNEP
	

	
	
	
	


1.2 Monitoring Framework
In the table below, please report on progress to date based on the Monitoring Framework included in the signed National Programme Document. Please input cumulative data and input quantitative/qualitative values for the indicators. If indicators or other data was modified, please explain in the comments column. If there is no data to be reported in the reporting period, please mark N/A. Please add additional rows as needed.
	Expected Results (Outcomes)
	Indicators
	Baseline
	Overall  National Programme Expected Target
	Achievement of Target to Date
	Means of Verification
	Responsibilities
	Risks and Assumptions
	Comments

	From Results Framework
	From Results Framework
	Baselines are a measure of the indicator at the start of the National Programme

Baseline for all indicators:
	The desired level of improvement to be reached at the end of the National Programme
	The actual level of performance reached at the end of the reporting period. Please provide a substantive assessment of the achievement of target to date, no more than 300 words per outcome.
	From identified data and information sources
	Specific responsibilities of participating UN organizations (including in case of shared results)
	Summary of assumptions and risks for each result
	

	Outcome 1: Capacity to manage REDD+

Readiness

strengthened.
	Institutional framework

to manage REDD+ Readiness

adopted.

 Proportion of

stakeholders perceiving the

REDD+ coordination unit as

effective in implementing and

coordinating the REDD+

readiness process.
	No
	Yes 
	The programme has started recently and therefore the basic capacity building and stakeholder engagement process is ongoing.
	  Progress reports

 Workshop Reports

 Evaluation Reports
	UNDP/UNEP
	
	The REDD+ team is being constituted and this is at the roots of delays. However, there are prospects of catching up with delays in the coming months.

	Output 1.1. REDD+ Readiness coordination and management bodies established and functioning.
	1.1.1 National REDD+ Readiness

institutional arrangements

in place and functioning.

1.1.2 Proportion of identified

capacity gaps that are

addressed.
	‘1 No
‘2 No


	‘1 Yes

‘2 Yes

	‘1. REDD+ readiness institutional arrangements not fully in place yet, but ongoing.

The establishment of the REDD+ National Office is ongoing. Synergy between UN-REDD and ILUA-II programmes is advancing solidly, and this will provide a stronger basis for forest resource management and REDD+ readiness. A number of goods and services have been delivered.
National REDD+ Coordinator  attended the UN-REDD Policy Board meeting in Vietnam.

Formalization of the Steering Committee and Multi-sectoral committee has been a slow process and not yet finalized, but almost. The nomination letters from the Permanent Secretary on new REDD+ team members are still pending.
‘2. No. Harmonisation of the different ongoing initiatives (UN-REDD, ILUA II, CCFU, ENRMMP) is needed in order to avoid duplication of activities and to optimise the different work plans and outcomes. The concept paper of integrating these programmes haven’t been made by the relevant Governmental units. 
	 Progress reports.

 Workshop proceedings.

 Capacity needs report. 
	UNDP
	‘- Delays in

appointment &

recruitment of staff.

‘- Inadequate 
understanding and capacity in REDD+ initiative among stakeholders beyond MTENR.

 ‘- Sudden change of a actocg PS
	The workplan  and the total budget were revised 6/11. Because of realistic implementation of some activities, funds from other activities were removed to Output 1.1. Original budget for this Output was 289,720USD, after revision it is 304,720USD

	Output 1.2. National REDD+ Readiness process

integrated into the national

development planning process.
	1.2.1 National Climate Change

Response Strategy with

REDD+ Readiness Process in

place and implemented.

1.2.2 Plans to integrate UNREDD+

mechanisms into

National Development Plans

in Place.
	‘1 No

‘2 No


	‘1 Yes

‘2 Yes


	Both activities have not started since the programme has been starting implementation in the current semester.

	Progress reports.

 Copy of Drafts and final

Strategy documents.

 Minutes of the Climate

Change strategy consultative

meetings.
	UNDP
	1.2 Delays in

reaching consensus on content and design 
on the climate change

response strategy. 
	 The different environmental, forest and climate initiatives are a bit fragmented, but recent efforts from government and with UN-REDD mission support are allowing a smoother concertation and a better policy coherence.

	Output 1.3.  
Communication and advocacy strategy as input

in overall climate change strategy developed and implemented.
	1.3.1 REDD+ Communication

Strategy developed.

1.3.2 Climate Change

Communication and

Advocacy Strategy with

REDD readiness

communication in place and

implemented.
	
	
	 N/A
	 Progress reports.

 Copies of Strategy

Documents.

 Workshop Reports.

 Technical Reports.
	UNEP
	
	

	Output 1.4. Mapping and gap analysis of relevant initiatives undertaken.
	1.4.1 Report on gaps, ongoing and

planned initiatives relevant

to REDD+ available.

1.4.2 Lessons pertinent to

implementing REDD+

shared.
	
	
	N/A
	 Progress reports.

 Copy of Study report and

Lesson learnt document.
	UNDP
	
	

	Outcome 2: Broad-based

stakeholder

support for

REDD+

established.
	 Information sharing and

coordination platform

between UN-REDD+

process and stakeholders

(NGOs, Other

government

departments, private

sector and bilateral

partners) established.
	No
	Yes
	The work has started. A major training event was planned and conducted (see below). 
	 Progress reports

 Workshop Reports.

 Minutes of meetings

 Evaluation Reports

 Survey reports
	UNDP
	
	Stakeholder engagement was stronger at project design and somehow declined. This is being revived during the 2nd half of 2011.

	Output 2.1. Stakeholders engagement process functioning.
	2.1.1 Report on the review of the

stakeholder engagement

process (including gaps

identified) is completed and

disseminated.

2.1.2 UN-REDD+ stakeholders

advisory group established

and functional.

2.1.3 A framework and guideline

for stakeholder engagement

at national, provincial,

district and community

levels is in place.

2.1.4 Number of joint planning,

consultative and review

meetings held between UNREDD+

and stakeholders

(Other government

departments, NGOs, Private

Sector and bilateral

partners) held.

2.1.5 Number of civil society

participants in joint

planning, consultative, and

review meetings.

2.1.6 Proportion of female

participants in stakeholder in

joint planning, consultative

and review meetings.
	‘1. No
‘2. No

‘3. No

‘4. 

‘5.

‘6.
	‘1. Yes

‘2. yes

‘3. Yes

‘4. 

‘5.

‘6.
	‘1. Ongoing. 
 ‘-Participated in the World Environmental Day function on the 5th June in Lusaka and  International Trade Fair in Ndola 

‘2. Not accomplished. This will be a result from the upcoming consultancy
‘3. Not conducted. This will be a result from the consultancy under item
‘4. 5
‘- stakeholder review meeting when finalizing the workplan 2011

‘- Stakeholder orientation training workshop  for raising awareness on REDD+ was held from 27th to 29th June 2011. A total of 75 participants from various stakeholder groups attended the training. Out of these 36 participants represented the 9 provinces, with 4 from each province.
-‘ meetings with donors and NGOs for possible pilot projects
‘5. 25% 
‘6. 25%
	 Progress reports

 Workshop reports

 Minutes of meetings
	UNDP
	
	The workplan  and the total budget were revised 6/11. Because of realistic implementation, funds from Output 2.1 were reduced and transferred to next  year. Original budget for this Output was 84,112USD, after revision it is 82,612USD

	Output 2.2. Conflict resolution and redress mechanism

reviewed.
	2.2.1 Report on the review of

existing conflict resolution

mechanisms is completed

and disseminated, and its

recommendations

implemented.

2.2.2 New conflict and arbitration

mechanisms developed and

in place.
	
	
	N/A
	 Reports

 Progress reports

 Conflict resolution or

arbitration

manuals/Guidelines
	UNDP
	
	The workplan and the total budget were revised 6/11. Because of realistic implementation, activities for output 2.2. were postponed to coming year. Original budget for this Output was 28,037USD, after revision it is 0USD

	Outcome 3: National

governance

framework and

institutional

capacities for the

implementation

of REDD+ strengthened.
	Outcome 3:

National

governance

framework and

institutional

capacities for the

implementation of

REDD+

strengthened
	
	
	N/A
	 Progress reports

 Reports

 Evaluation Reports
	UNDP
	
	The slow start of the programme may result in delayed policy review on identified gaps.

	Output 3.1. Institutional capacity to implement REDD+ framework developed.
	3.1.1 Report on human and

financial capacity needs to

address longer term

institutional requirements to

implement REDD+

completed and

disseminated.

3.1.2 Partnership strategy to

facilitate sourcing of

additional financial resources

for capacity building in

place.

3.1.3 Number of agreements and

MOUs for accessing

additional financial resources

in place.

3.1.4 Number of South_South

cooperation learning tours
	
	
	N/A – No activities for 2011
	 Progress reports

 Reports

 Copy of partnership

strategy.

 Copies of Agreements

and MOUs.

 Mission reports.
	UNDP
	
	

	Output 3.2. National REDD+ Strategy process integrated into the national development planning process.
	3.2.1 National REDD+ Strategy

developed through

consultative process.

3.2.2 % of districts with

development plans that

have integrated REDD+

readiness mechanisms.

3.2.3 Monitoring framework for

governance, social,

economic and

environmental impacts

pertinent to REDD+

implementation is in place.
	
	
	N/A – Some activities postponed to next year. Others not yet started
	 Progress reports.

 Reports.

 Copy of monitoring

framework.

 Minutes of REDD advisory

groups.
	UNDP
	
	The workplan and the total budget were revised 6/11. Because of realistic implementation, some activities for output 3.2. were postponed to coming year. Original budget for this Output was 37,383USD, after revision it is 29,883USD

	Out 3.3. Legislative framework to facilitate implementation of  REDD+ strengthened.
	3.3.1 Report on the review of

existing legislation in terms

of applicability and gaps in

relation to REDD+ is

available and its

recommendations have

been addressed.

3.3.2 Report on legal review to

establish the ownership of

carbon in different land

tenure systems completedand disseminated.

3.3.3 Report on the appropriate

regulatory process for

developing, managing and

monitoring carbon trading

agreements completed and

disseminated.

3.3.4 Report on necessary

changes to policies and

legislation for optimising

REDD+ implementation

completed and

disseminated.

3.3.5Action plan for Legal

changes required to channel

REDD+ finances in place.

3.3.6 Number of policies, laws,

Acts and by-laws revised to

incorporate REDD+

requirements.
	
	
	N/A – Some activities postponed to next year. Others not yet started
	 Progress reports

 Reports

 Copy of draft bills, laws,

policy documents, Acts

and Bi-laws revised.

 Law enactment records at

the National Assembly of

Zambia
	UNDP
	
	The workplan and the total budget were revised 6/11. Because of realistic implementation, some activities for output 3.3. were postponed to coming year. Original budget for this Output was 70,093USD, after revision it is 30,000USD

	Output 3.4. Mechanism to administrate and channel REDD+ finance established.
	3.4.1 Report on options for

channelling REDD+ finance,

including the national

budget and special fund

mechanisms completed and

disseminated.

3.4.2 Number of consultative

meetings held

3.4.3 System for managing

REDD+ finance established.
	
	
	N/A  Activities postponed to next year. 
	 Progress reports

 Reports

 National budget

documents

 Forum reports and policy

briefs

 Review of systems at

MFNP and other

implementing ministries.
	UNDP
	
	The workplan and the total budget were revised 6/11. Because of realistic implementation,  activities for output 3.4. were postponed to coming year. Original budget for this Output was 9,345USD, after revision it is 0USD

	Output 3.5. Benefit sharing model approved.
	3.5.1 Number of benefit

distribution options and

payment mechanisms

assessed.

3.5.2 Report on the assessment of

different proposed benefitsharing

approaches through

demonstration projects

completed and

disseminated.

3.5.3 Number of benefitdistribution options and

payment mechanisms

developed.

3.5.4 Mechanisms for delivering

REDD+ benefits determined

through broad-based

consultations with

landowners and other

stakeholders.

3.5.4 Report on tax implications

for all REDD+ beneficiaries

completed and

implemented.

3.5.5 Criteria and guidelines for

sharing the benefits for

activities under the REDD+

mechanism are in place.
	
	
	N/A  Activities postponed to next year.
	 Progress reports

 Reports

 Consultative meeting

reports

 Copies of leaflets,

brochures and

newsletters on benefit

sharing mechanisms

developed.

 Review of systems at MFNP and other

implementing ministries.
	UNDP
	
	The workplan and the total budget were revised 6/11. Because of realistic implementation, activities for output 3.4. were postponed to coming year. Original budget for this Output was 46,728USD, after revision it is 0USD

	Outcome 4: National REDD+

strategies

identified.
	
	
	
	
	
	
	
	

	Outcome 4.1: Drivers of deforestation and forest degradation assessed 
	4.1.1 Report on drivers of deforestation and forest degradation completed and disseminated

4.1.2 Key national, provincial, district and community level agencies responsible for addressing the drivers of deforestation and forest degradation identified and oriented
	no
	yes
	N/A
	Progress report

Workshop report

Final report
	UNEP/FAO


	
	

	Outcome 4.2: Candidate activities for REDD+ identified
	4.2.1 Identify global best practices and benchmarking for forest management and REDD+ activities, and tailor practices to Zambia suitable activities are identified

4.2.2 Multiple benefits of REDD+ implementation identified and mapped

4.2.4 Expert consultations on development of a framework addressing opportunity costs for key stakeholders as well as cost abatement curves and follow up actions completed

4.2.5 Relevant global level initiatives are incorporated into national REDD+ strategy and national Development planning process
	no
	yes
	N/A
	Progress report

Workshop report

Final report
	UNEP
	
	

	Outcome 5: MRV capacity to implement REDD+ strengthened.

	5.1 REDD+ integrated with forestry inventory system (ILUA)
	5.1.1 Full fungibility with the ILUA data base and information system provided

5.1.2 Environmental data are integrated with socio economic data

5.1.3 ILUA data management improved
	
	
	The process of recruiting an MRV advisor  to lead the MRV technical work in Zambia has been finalized and the candidate will start soon in the coming weeks.
The integration with ILUA-II coordination has been carefully studied and a joint workplan FAO MRV and ILUAII has been made in order to allow a smooth implementation.

The ILUA II data is being studied to see where gaps are and which data can be used for carbon calculations in the REDD+ process.

The leaflet to raise awareness concerning MRV has been finalized and are printed for distribution. 
	Workplan
Leaflets
	FAO
	
	Need to harmonize coordination of  ILUAII and UN-REDD programmes for better monitoring.
After the REDD+ MRV seminars in the REDD+ orientation workshop, major efforts will be put in the awareness raising also for MRV semantics and process.

	5.2 Operational Forest Management institutionalized
	5.2.1 A cell for geographical information analysis and personnel training is established

5.2.2 A geographical explicit database for all types of of land use information is established and populated

5.2.3 An end user interface for database management and queries is designed and implemented

5.2.4 Support tools for REDD+ policies and measurements is selected

5.2.5 Linkages with regional geographical information systems are established.
	
	
	The FRA sampling tiles from FAO have been analyzed for Zambia in order to have a first estimate of carbon stocks and stock changes.
FAO HQ is setting up a pilot portal for the national monitoring system, so Zambia can decide which system to use.
In the meanwhile refurbishments are done at the FD to accommodate the RS unit.

FAO HQ is working on a methodology with INPE in order to allow a smooth training and set-up for the Zambian national forest monitoring system.
	
	FAO
	
	RS capacity is weak and will require a lot of capacity building.
An intensive training in RS both in-country and in Brazil through INPE is foreseen.



	5.3: Green house gas emissions and removals from forest lands estimated and accurately reported
	5.3.1 A fully compliant UNFCCC/IPCC greenhouse gas inventory is developed.

5.3.2 Training courses on greenhouse gas inventory methodology and IPCC Good practice Guidelines is developed and delivered
	
	
	Two technical officers from Zambia attended the intensive Training on Green House Gases (GHG) inventory in FAO HQ in January 2011. The workshop allowed a broad overview of the necessary steps for the national GHG inventory.
.


	
	FAO

	
	The workshop  provided information and training on setting national systems for greenhouse gas (GHG) inventories, including technical requirements and institutional actions needed to establish a national GHG inventory. 



	Outcome 6: Assessment of REL and RL undertaken.

	Outcome 6.1: Historical rates of forest are and carbon stock changes reviewed
	6.1.1 Report on historical forest area changes at national level developed

6.1.2 Historical greenhouse gas emissions and removal rates at national level assessed


	
	
	A methodological framework document has been developed for RL and REL in Zambia in FAO HQ.
	 Progress reports

 Reports

 Publications

	FAO
	
	

	6.2> National circumstances assessed
	6.2.1 The opportunity cost of land providing REDD + benefits in relation to  other land uses

6.2.2 National socio economic condition assessed

6.2.3 Needs and resources for sustainable development assessed

6.2.4 Report on expected trends on forest area changes completed

6.2.5 Assessment of economic data on other sectors relevant to deforestation completed

6.2.6 The most threatened forests identified and mapped

6.2.7 Other forest co benefits assessed and mapped
	
	
	N/A  - Activities postponed to next year.
	 Progress reports

 Reports

 Publications

	FAO
	
	


1.3 Financial Information
In the table below, please provide up-to-date information on activities completed based on the Results Framework included in the signed National Programme Document; as well as financial data on planned, committed and disbursed funds. The table requests information on the cumulative financial progress of the National Programme implementation at the end of the reporting period (including all cumulative yearly disbursements). Please add additional rows as needed. Definitions of financial categories:
· Budget: Amount transferred from the MDTF to date for the programme

· Commitments: Includes all amount committed
 to date

· Disbursement: Amount paid to a vendor or entity for goods received, work completed, and/or services rendered (does not include un-liquidated obligations)
· Expenditures: Total of commitments plus disbursements
· Percentage delivery: Cumulative expenditure over funds transferred to date
	PROGRAMME OUTCOMES
	UN ORGANISATION
	IMPLEMENTATION PROGRESS

	
	
	BUDGET
	CUMULATIVE EXPENDITURES
	DELIVERY (%)

	
	
	
	Commitments
	Disbursements
	Total Expenditures
	Expenditure as percentage of the budget

	Outcome 1: Capacity to manage REDD+ Readiness strengthened.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	56,075
	0
	0
	0
	0%

	
	UNDP
	370,000
	43,997
	14,811
	58,807
	16 %

	Outcome 2: Broad-based stakeholder support for REDD+ established.
	FAO
	-
	

-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	120,000
	-
	38,043
	38,043
	32 %

	Outcome 3: National governance framework and institutional capacities for the implementation

of REDD+ strengthened.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	174,996
	0
	0
	0
	0%

	Outcome 4: National REDD+ strategies identified.
	FAO
	37,383
	0
	0
	0
	0%

	
	UNEP
	63,930
	0
	0
	0
	0%

	
	UNDP
	-
	-
	-
	-
	-

	Outcome 5: MRV capacity to implement REDD+ strengthened.
	FAO
	512,809
	72,647
	7,759
	80,406
	16%

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	-
	-
	-
	-
	-

	Outcome 6: Assessment of REL and RL undertaken.
	FAO
	350,000
	0
	0
	0
	0%

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	-
	-
	-
	-
	-

	TOTAL: 
	1,685,193
	116,644
	60,613
	177,256
	11%

	Figures are inclusive of 7% indirect support costs
	
	
	
	
	


2. National Programme Progress
The questions in section two are intended to capture advancements and challenges that the National Programme has faced during the reporting period. It also aims to collect information on inter-agency coordination, ownership and development effectiveness, and communication. Please provide your answers after each question.
2.1 Narrative on Progress, Difficulties and Contingency Measures
The questions below ask for a brief narrative describing progress on the implementation of activities, generation of outputs and attainment of outcomes. It also asks for a description of internal and external challenges to National Programme implementation, as well as the contingency actions planned to overcome them.
2.1.1 Please provide a brief overall assessment of the extent to which the National Programme is progressing in relation to expected outcomes and outputs. Please provide examples if relevant (600 words).
The project is in real terms starting implementation in the current semester. The three staff attached to the programme from the Forestry Department were awaiting their revised attachment letters that spell out revised TORs facilitating these officers to work fully on the programme. The nomination letters were finally submitted in August 2011. The slow start of implementation was due to lack of dedicated staff to start implementing the project. 
While a Joint Steering Committee and Technical Committee already exist, there is need to expand the mandate and incorporate other stakeholders at the core of REDD+ implementation. The establishment of a steering committee and a multi-sectoral committee including the development of the TORs need to be expedited for the programme to benefit from the policy guidance and sectoral issues that have the bearing on the REDD process. 

The agreed UN-REDD annual workplan for 2011 was signed as late as March 2011. In the quarterly review Q1 (May 2011) it was considered to have become too ambitious given the local constraints, as well as the fact that it was almost mid-2011 the planned activities hadn’t truly started. As a result, a more realistic workplan was created jointly with the Government and UN-REDD support team. That interim workplan, which will cover the period May-September 2011, was elaborated with leaders and members of the different environmental programmes (UN-REDD, ILUA II, CCFU and ENRMMP – the Environment and Natural Resources Management and Mainstreaming programme), as well as donors. This method of planning was considered particularly enriching and the UN-REDD support team recommended it to become regular practice for planning efforts, review of key documents and missions within the MTENR.

It is also noted that harmonisation of the different ongoing initiatives (UN-REDD, ILUA II, CCFU, ENRMMP) is needed, and already ongoing, in order to avoid duplication of activities and to optimise the different work plans and outcomes.

Stakeholder engagement is an important challenge for implementation. The diversity of stakeholder engagement during the UN-REDD programme’s design needs to be revitalized, and that started to be achieved through the REDD+ Orientation Workshop that took place in late June 2011. At the same time, there is need for basic REDD+ training, targeting a multi-stakeholder audience, in order to create the basic understanding and to broaden the REDD+ process. This collaboration has started by the successful 3 day REDD+ Orientation workshop in the end of June.

2.1.2 Please provide a brief overall assessment of any measures taken to ensure the sustainability of the National Programme results during the reporting period. Please provide examples if relevant. (250 words)
The delivery rate against the original wokplan for year 2011 is very low and, as it was explained, this is due to the fact that the programme is just starting and the national REDD+ team is being established.
2.1.3 If there are difficulties in the implementation of the National Programme, what are the main causes of these difficulties? Please check the most suitable option.
 FORMCHECKBOX 
 UN agency Coordination

 FORMCHECKBOX 
 Coordination with Government 

 FORMCHECKBOX 
 Coordination within the Government 

 FORMCHECKBOX 
 Administrative (Procurement, etc) /Financial (management of funds, availability, budget revision, etc)

 FORMCHECKBOX 
 Management: 1. Activity and output management 
 FORMCHECKBOX 
 Management: 2. Governance/Decision making (PMC/NSC) 
 FORMCHECKBOX 
 Accountability
 FORMCHECKBOX 
 Transparency
 FORMCHECKBOX 
 National Programme design
 FORMCHECKBOX 
 External to the National Programme (risks and assumptions, elections, natural disaster, social unrest)
2.1.4 If boxes are checked under 2.1.3, please briefly describe any current internal difficulties
 the National Programme is facing in relation to the implementation of the activities outlined in the National Programme Document. (200 words)
Although there has been an improvement in the delivery of the project, the rate is still relatively low. Within the reporting period the three staff attached to the programme were still awaiting revised attachment letters that spell out revised TORs facilitating these officers to work 100% on the programme. The Zambia REDD+ team is being established.
During the Mission visit in May 2011, the Ministry provided a position on how programmes and projects will be implemented in the Ministry in order to enhance coordination, avoid duplication, optimize the different work plans and outcomes and reduce on transactions costs. The Ministry was to come up with a concept paper of integrating these programmes, which has not been presented yet. The delay in developing and implementing the strategy may contribute to the duplication of efforts among the projects. 
The procurement process took longer than planned for the effective setup of the REDD+ Coordination unit.
2.1.5 If boxes are checked under 2.1.3, please briefly describe any current external difficulties
 (not caused by the National Programme) that delay or impede the quality of implementation. (200 words)
The Permanent Secretary of Ministry of Tourism, Environment and Natural Resources was suddenly changed (6/11). Zambia is facing election period in September 2011 and it has been influencing the programme throughout the year by occupying Governmental staff also on other matters than agreed.  
2.1.6 Please, briefly explain the actions that are or will be taken to eliminate or manage the difficulties (internal and external referred to in question 2.1.3 and 2.1.4) described in the previous sections. (250 words)
The RC has taken the issues on the table in the high level quarterly review Q1 in May 2011. These have been also discussed with the new PS by UNDP. The weekly progress meetings  between local UN-REDD team and the REDD+ Team will give follow ups what is ongoing.
2.2 Inter-Agency Coordination
The aim of the questions below is to collect relevant information on how the National Programme is contributing to inter-agency work and “Delivering as One”.

2.2.1 Is the National Programme in coherence with the UN Country Programme or other donor assistance framework approved by the Government?
 FORMCHECKBOX 
 Yes
 FORMCHECKBOX 
No
If not, does the National Programme fit into the national strategies?
 FORMCHECKBOX 
 Yes
 FORMCHECKBOX 
No
If not, please explain:
2.2.2 What types of coordination mechanisms and decisions have been taken to ensure joint delivery? Please reflect on the questions above and add any other relevant comments and examples if you consider it necessary:
The HACT assessment was finalized in Jan 2011 to ensure good implementation within the UN Agencies.
2.2.3 Is HACT being applied in the implementation of the National Programme by the three participating UN organisation?
 FORMCHECKBOX 
Yes

 FORMCHECKBOX 
No
If not, please explain:

2.3 Ownership
 and Development Effectiveness

The questions below seeks to gather relevant information on how the National Programme is putting into practice the principles of aid effectiveness through strong national ownership, alignment and harmonization of procedures and mutual accountability.
2.3.1 Do government and other national implementation partners have ownership of the implementation of activities and the delivery of outputs?
 FORMCHECKBOX 
 No

 FORMCHECKBOX 
Some 
 FORMCHECKBOX 
 Yes
Please explain:
Government is on board with implementation, but relies on the strong support by the UN Agencies.
2.3.2 Are the UN-REDD Programme’s Guidelines for Stakeholder Engagement and Operational Guidance Engagement of Indigenous Peoples and Other Forest Dependent Communities been applied in the National Programme process?
 FORMCHECKBOX 
 No

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
 Fully 

Please explain, including if level of consultation varies between non-government stakeholders:
The stakeholder assessment and engagement plan has not yet been started to identify all the key stakohelders. The non governmental stakeholders have been included in the planning process and to review the progress.
2.3.3 What kind of decisions and activities are non-government stakeholders involved in?
 FORMCHECKBOX 
 Policy/decision making

 FORMCHECKBOX 
 Management:  FORMCHECKBOX 
 Budget  FORMCHECKBOX 
 Procurement  FORMCHECKBOX 
 Service provision 
 FORMCHECKBOX 
 Other, please specify
Please explain, including if level of involvement varies between non-government stakeholders:
There is non-governmental involvement in dialogue and information sharing on climate, forest and REDD matters. For other aspects of REDD+ readiness, there is still much to progress, yet there is awareness on all side of the challenge ahead, and commitment to tackle this weakness.

2.3.4 Based on your previous answers, briefly describe the current situation of the government and non-government stakeholders in relation to ownership and accountability
 of the National Programme. Please provide some examples. 
3. Government Counterpart Information
The aim of this section is to allow the Government Counterpart to provide their assessment, as well as additional and complimentary information to Section 1-3 which are filled out by the three participating UN organizations.

	Comments by the Government Counterpart:
The implementation of the REDD+ Readiness Process in Zambia has been based on consensus with stakeholders on the approach in development the national strategy. In general the start up was slow due to administrative procedures, however, the 3 staff attached to the Programme finally received their official letters and this will enhance the process of implementation. The common understanding of the potential of REDD+ in Zambia is yet to be developed and there is need, therefore, for awareness raising and capacity development in order to facilitate a stakeholder based national REDD+ strategy.


	løkløk









� Please list all the partners working on implementing the National Programme


� Total budget for entire duration of  the Programme, as specified in the signed National Programme Document


� Each UN organisation is to nominate one or more focal points to sign the report. Please refer to the UN-REDD Programme Planning, Monitoring and Reporting Framework document for further guidance


� Commitment is the amount for which legally binding contracts have been signed, including multi-year commitments which may be disbursed in future years


� Difficulties confronted by the team directly involved in the implementation of the National Programme


� Difficulties confronted by the team caused by factors outside of the National Programme


� Ownership refers to countries exercising effective leadership over their REDD+ policies and strategies, and co-ordination of actions.


� Accountability: Acknowledgment and assumption of responsibility for actions, � HYPERLINK "http://en.wikipedia.org/wiki/Product_%28business%29" \o "Product (business)" �products�, decisions, and policies and encompassing the obligation to report, explain and be answerable for resulting consequences.





2

