[image: image1.jpg]UN-REDD

PROGRAMME




	
Zambia
National Programme

2011 Annual Report


	31st January 2012 (final draft)

	


1. National Programme Status
1.1 National Programme Identification
	Country: Republic of Zambia
Title of programme: UN-REDD Programme – Zambia quick start initiative
Date of submission: March 2010
	
	Date of signature
: 26th September 2010
Date of first transfer of funds
: 22nd October 2010
End date: August 2013
No-cost extension requested
:

	
	
	


	Implementing partners
: 
Forestry Department of the Ministry of Mines and Natural Resources

	


The financial information reported should include overhead, M&E and other associated costs.
	Financial Summary (USD)

	UN Agency
	Approved Programme Budget

	Amount transferred to date

	Cummulative Expenditures up to 31 December 2011


	FAO
	2.180,000
	900,182
	184,643

	UNDP
	1,995,000
	664,996
	310,415.90

	UNEP
	315,000
	120,005
	0

	Total
	4,490,000
	
	


	Electronic signatures by the designated UN organization

	Electronic signature by the Government Counterpart

	FAO
	UNDP
	UNEP
	

	
	
	
	

	Type the name of signatories in full:

	
	
	
	


1.2 Monitoring Framework
In the table below, please report on progress to date based on the Monitoring Framework included in the signed National Programme Document. Please input cumulative data and input quantitative/qualitative values for the indicators. If indicators or other data was modified, please explain in the comments column. If there is no data to be reported in the reporting period, please mark N/A. Please add additional rows as needed.
	Expected Results (Outcomes)
	Indicators
	Baseline
	Overall  National Programme Expected Target
	Achievement of Target to Date
	Means of Verification
	Responsibilities
	Risks and Assumptions
	Comments

	From Results Framework
	From Results Framework
	Baselines are a measure of the indicator at the start of the National Programme

Baseline for all indicators:
	The desired level of improvement to be reached at the end of the National Programme
	The actual level of performance reached at the end of the reporting period. Please provide a substantive assessment of the achievement of target to date, no more than 300 words per outcome.
NOTE; The Zambia UN-REDD Programme started implementation in 2011 and hence the progress reporting is the progress so far.
	From identified data and information sources
	Specific responsibilities of participating UN organizations (including in case of shared results)
	Summary of assumptions and risks for each result
	

	Outcome 1: Capacity to manage REDD+

Readiness

strengthened.
	Institutional framework

to manage REDD+ Readiness

adopted.

 Proportion of

stakeholders perceiving the

REDD+ coordination unit as

effective in implementing and

coordinating the REDD+

readiness process.
	No
	Yes 
	The National REDD+ Coordination Unit was set up during the year, with staff officially assigned to the implementation of the UN-REDD Programme.  The Coordination unit is working with other stakeholders in the implementation of activities.

1. 
Zambia also attended the Convention on Biological Diversity (CBD) and REDD+ Capacity building Workshop in Cape Town, South Africa, which aimed at supporting parties’ efforts to address reducing emissions from deforestation and forest degradation in developing countries in the frame work of the United Nations framework convention on climate change in a way that contributes to the implementation of the CBD programme of work on forest biodiversity; and (iii) A Zambian delegation attended a training workshop on the national systems for Green House Gas (GHG) organized by FAO and CRfN in January 2011 at FAO Headquarters in Rome.
2. 


	  Progress reports

 Workshop Reports

 Evaluation Reports
	UNDP/UNEP
	
	With new Government in place and the definitive take of of the Zambia REDD+ process, a new coordination team and arrangements are being built up and early 2012 will experience a progress in this component.

	Output 1.1. REDD+ Readiness coordination and management bodies established and functioning.
	1.1.1 National REDD+ Readiness

institutional arrangements

in place and functioning.

1.1.2 Proportion of identified

capacity gaps that are

addressed.
	‘1 No

‘2 No


	‘1 Yes

‘2 Yes


	1. The REDD+ readiness institutional arrangements are still being developed and will be based on stakeholder consensus (for which a first period of basic training and multi-stakeholder was needed). Appointment of the focal point persons from key Ministries was done during the year under review. 
2. In order to enhance collaborative approach between two major UN programmes related to the forest (namely ILUA-II and UN-REDD), it was discussed and agreed that the Technical committees for the REDD+ readiness process will be based on the already established structures of ILUA Project.

3. The National REDD+ Coordinator  attended the UN-REDD Policy Board meetings in Vietnam and Germany.

4. In spite of the Steering Committee under the ENRMMP being established, the formalization of the Terms of References to include REDD+ was not concluded during the year. However this is expected to be achieved in the first quarter of 2012. 
5. Increased collaboration among Programme initiated at different times in the former Ministry (MTENR) was recognized as important to avoid duplication and optimize work plans. The Ministry (MTENR) then developed a concept on the collaborative approach to UN-REDD, ILUA II, CCFU, and ENRMMP. The concept was to be approved by the senior management in the Ministry. However, the Ministry was dissolved before this could happen. However, ILUA and UN-REDD are currently collaborating more on various activities, and a new, broader framework of cooperation will be defined with the Government.
6. Several international-level specialised trainings served to enhance the capacities of national-level actors in REDD+.
	 Progress reports.

 Workshop proceedings.

 Capacity needs report. 
	UNDP
	
	Changes in Ministries resulted new orientation of various staff in the new Ministry. However, since most of them had been attend the consultative meetings, this was not a major problem.

	Output 1.2. National REDD+ Readiness process

integrated into the national

development planning process.
	1.2.1 National Climate Change

Response Strategy with

REDD+ Readiness Process in

place and implemented.

1.2.2 Plans to integrate UNREDD+

mechanisms into

National Development Plans

in Place.
	‘1 No

‘2 No


	‘1 Yes

‘2 Yes


	N/A: This output will be addressed once the REDD+ readiness process is more solidly on track.

	a. Progress reports.

b. Copy of Drafts and final Strategy documents.
c. Minutes of the Climate

Change strategy consultative
meetings.
	UNDP
	Delays in

reaching consensus on content and design 

on the climate change

response strategy. 
	 The Government was in the process of assessing the proposed climate change response framework with the aim of creating an integrated approach. 

	Output 1.3.  
Communication and advocacy strategy as input

in overall climate change strategy developed and implemented.
	1.3.1 REDD+ Communication

Strategy developed.

1.3.2 Climate Change

Communication and

Advocacy Strategy with

REDD readiness

communication in place and

implemented.
	
	
	A stakeholder Assessment and Engagement Plan (under Outcome 2) has been conducted, and it will definitively become the basis of the development of the Communication and Advocacy Strategy. The mentioned assignment was conducted in each of the 9 provinces of Zambia
	 Progress reports.

 Copies of Strategy

Documents.

 Workshop Reports.

 Technical Reports.
	UNEP
	
	

	Output 1.4. Mapping and gap analysis of relevant initiatives undertaken.
	1.4.1 Report on gaps, ongoing and

planned initiatives relevant

to REDD+ available.

1.4.2 Lessons pertinent to

implementing REDD+

shared.
	
	
	A study was conducted on Best forest Practices relevant to REDD+ in Zambia (under outcome 4). The results of the study were expected to be ready in the first quarter of 2012, then given opportunities to multi-stakeholder review and decision on actions concerning REDD+.
	 Progress reports.

 Copy of Study report and

Lesson learnt document.
	UNDP
	
	

	Outcome 2 Broad-based

stakeholder

support for

REDD+

established.
	 Information sharing and

coordination platform

between UN-REDD+

process and stakeholders

(NGOs, Other

government

departments, private

sector and bilateral

partners) established.
	No
	Yes
	The REDD+ Coordination Unit has been working with various stakeholders (including NGOs and the private sector) to enhanance their understanding about REDD+ and contribution to the process of developing a national strategy. Various stakeholder Consultative meetings were held during the year. A REDD+ training workshop was held, becoming the first major, multi-stakeholder event for joint learning and dialogue around REDD+, including a solid representation of field practitioners from the provinces. In addition, the mentioned stakeholder assessment and engagement plan will provide guidance to advance towards the achievement of this outcome.
	 Progress reports

 Workshop Reports.

 Minutes of meetings

 Evaluation Reports

 Survey reports
	UNDP
	 Unclear roles and responsibilities for REDD+ implementation among stakeholders may result in uncoordinated efforts 

	Stakeholder engagement has been the core of the Zambian process and continue to be strong.

	Output 2.1. Stakeholders engagement process functioning.
	2.1.1 Report on the review of the

stakeholder engagement

process (including gaps

identified) is completed and

disseminated.

2.1.2 UN-REDD+ stakeholders

advisory group established

and functional.

2.1.3 A framework and guideline

for stakeholder engagement

at national, provincial,

district and community

levels is in place.

2.1.4 Number of joint planning,

consultative and review

meetings held between UNREDD+

and stakeholders

(Other government

departments, NGOs, Private

Sector and bilateral

partners) held.

2.1.5 Number of civil society

participants in joint

planning, consultative, and

review meetings.

2.1.6 Proportion of female

participants in stakeholder in

joint planning, consultative

and review meetings.
	‘1. No

‘2. No

‘3. No

‘4. 

‘5.

‘6.
	‘1. Yes

‘2. yes

‘3. Yes

‘4. 

‘5.

‘6.
	1. During the year under review, a large team of specialists undertook an assignment on "Stakeholder Assessments and Engagement Plan", with field surveys in each of the 9 provinces of Zambia. The final results are expected in the first quarter of 2012, and will be submitted to a stakeholder review process.
2. The stakeholder advisory group was not established during the year as it was important to understand the roles and responsibilities of various stakeholders through the stakeholder assessment task (as above). The Advisory group will be established in collaboration with ILUA II Project in the first quarter of 2012. 


3. A Stakeholder REDD+ orientation training workshop was conducted for raising awareness on REDD+  in June  2011. A total of 75 participants from various stakeholder groups attended the training. Out of these, half (36 participants) represented the 9 provinces.
4. A number of civil society organization serving various stakeholders continued to attend the meetings organized by the REDD+ Coordination Unit. The civil societies that cover a wide range of specialization including land, environment and natural resource management, Gender, Youths, Media. A fluid communication and collaboration between governmental and non-governmental stakeholders around REDD+ has been crafted during 2011.
5. The UNZA university student Environmental Association held a meeting that aimed at enhancing students’ understanding about REDD+ and related matters, and the potential role of student organisations in facilitating information flow. The meeting helped the students to understand the basic scope of REDD+ and has added to their consideration of potential internships into government institutions, such as the Forestry Department during the industrial break for Universities 

6. Community Based Natural resource Management Forum (CBNRMF), at their annual review meeting, hosted a presentation on the status of REDD+ readiness process and the potential role of CBNRM  experiences in adding value to the REDD+ process in Zambia
7. The Zambia National Climate Change Network (ZCCN), in collaboration with the national REDD+ team, conducted presentations and discussions aimed at enhancing the understanding of the Environmental and Social Safeguards as outlined in the Cancun Agreements of 2010. The aim was to facilitate Civil Society contribution towards identification of important actions that may be required to put in place safeguards

8. The REDD+ project team presented a paper on REDD-plus Co-benefits-Experience for Zambia at a meeting on REDD-plus after Cancun: Moving from Negotiation to Implementation Building REDD-plus Policy Capacity for Developing Country Negotiators and Land Managers, 10-12 May 2011 in Douala, Cameroon which was organized by IISD and ASB-ICRAF 

9. A Civil Society consultative meeting was held on the 5th October at Kingfisher Hotel, aiming at identifying civil society representatives to participate in the REDD+ readiness process.  Civil Society have identified which institutions/representatives will form a core contact group with the UNREDD+ Programme.


	 Progress reports

 Workshop reports

 Minutes of meetings
	UNDP
	
	

	Output 2.2. Conflict resolution and redress mechanism

reviewed.
	2.2.1 Report on the review of

existing conflict resolution

mechanisms is completed

and disseminated, and its

recommendations

implemented.

2.2.2 New conflict and arbitration

mechanisms developed and

in place.
	
	
	N/A  - Activities will start in the following year.
	 Reports

 Progress reports

 Conflict resolution or

arbitration

manuals/Guidelines
	UNDP
	
	

	Outcome 3: National

governance

framework and

institutional

capacities for the

implementation

of REDD+ strengthened.
	Outcome 3:

National

governance

framework and

institutional

capacities for the

implementation of

REDD+

strengthened
	
	
	N/A  - Activities will start in the following year since this requires preliminary work..
	 Progress reports

 Reports

 Evaluation Reports
	UNDP
	Slow pace of policy review process  may affect level of REDD+ implementation
	

	Output 3.1. Institutional capacity to implement REDD+ framework developed.
	3.1.1 Report on human and

financial capacity needs to

address longer term

institutional requirements to

implement REDD+

completed and

disseminated.

3.1.2 Partnership strategy to

facilitate sourcing of

additional financial resources

for capacity building in

place.

3.1.3 Number of agreements and

MOUs for accessing

additional financial resources

in place.

3.1.4 Number of South_South

cooperation learning tours
	
	
	N/A  - Activities postponed to next year.
	 Progress reports

 Reports

 Copy of partnership

strategy.

 Copies of Agreements

and MOUs.

 Mission reports.
	UNDP
	
	

	Output 3.2. National REDD+ Strategy process integrated into the national development planning process.
	3.2.1 National REDD+ Strategy

developed through

consultative process.

3.2.2 % of districts with

development plans that

have integrated REDD+

readiness mechanisms.

3.2.3 Monitoring framework for

governance, social,

economic and

environmental impacts

pertinent to REDD+

implementation is in place.
	
	
	
FAO’s Global UN-REDD team conducted a study ‘Legal Preparedness for REDD+’ in Zambia. The project aimed to identify legal challenges, gaps and needs for the implementation of REDD+ and make recommendations to help strengthen legal and institutional capacity in 3 REDD+ countries, where Zambia represented Africa. This study can be used as a baseline when assessing the needs of strengthening the legislative framework to facilitate implementation of REDD+ 

	 Progress reports.

 Reports.

 Copy of monitoring

framework.

 Minutes of REDD advisory

groups.
	UNDP
	
	

	Out 3.3. Legislative framework to facilitate implementation of  REDD+ strengthened.
	3.3.1 Report on the review of

existing legislation in terms

of applicability and gaps in

relation to REDD+ is

available and its

recommendations have

been addressed.

3.3.2 Report on legal review to

establish the ownership of

carbon in different land

tenure systems completedand disseminated.

3.3.3 Report on the appropriate

regulatory process for

developing, managing and

monitoring carbon trading

agreements completed and

disseminated.

3.3.4 Report on necessary

changes to policies and

legislation for optimising

REDD+ implementation

completed and

disseminated.

3.3.5Action plan for Legal

changes required to channel

REDD+ finances in place.

3.3.6 Number of policies, laws,

Acts and by-laws revised to

incorporate REDD+

requirements.
	
	
	
	 Progress reports

 Reports

 Copy of draft bills, laws,

policy documents, Acts

and Bi-laws revised.

 Law enactment records at

the National Assembly of

Zambia
	UNDP
	
	

	Output 3.4. Mechanism to administrate and channel REDD+ finance established.
	3.4.1 Report on options for

channelling REDD+ finance,

including the national

budget and special fund

mechanisms completed and

disseminated.

3.4.2 Number of consultative

meetings held

3.4.3 System for managing

REDD+ finance established.
	
	
	N/A  - Activities postponed until the basis of REDD+ are unfolded.
	 Progress reports

 Reports

 National budget

documents

 Forum reports and policy

briefs

 Review of systems at

MFNP and other

implementing ministries.
	UNDP
	
	

	Output 3.5. Benefit sharing model approved.
	3.5.1 Number of benefit

distribution options and

payment mechanisms

assessed.

3.5.2 Report on the assessment of

different proposed benefitsharing

approaches through

demonstration projects

completed and

disseminated.

3.5.3 Number of benefitdistribution options and

payment mechanisms

developed.

3.5.4 Mechanisms for delivering

REDD+ benefits determined

through broad-based

consultations with

landowners and other

stakeholders.

3.5.4 Report on tax implications

for all REDD+ beneficiaries

completed and

implemented.

3.5.5 Criteria and guidelines for

sharing the benefits for

activities under the REDD+

mechanism are in place.
	
	
	Idem as above
	 Progress reports

 Reports

 Consultative meeting

reports

 Copies of leaflets,

brochures and

newsletters on benefit

sharing mechanisms

developed.

 Review of systems at MFNP and other

implementing ministries.
	UNDP
	
	

	Outcome 4: National REDD+

strategies

identified.
	
	
	
	A number of assessments, data collection and analytical work have started to provide the basis to identify the REDD+ strategic options.
	
	
	Poor coordination among implementing and executing institutions  may affect  deliverables.
	

	Outcome 4.1: Drivers of deforestation and forest degradation assessed 
	4.1.1 Report on drivers of deforestation and forest degradation completed and disseminated

4.1.2 Key national, provincial, district and community level agencies responsible for addressing the drivers of deforestation and forest degradation identified and oriented
	no
	yes
	A study conducted by Copperbelt University is currently ongoing and its final report is presented at the end of January 2012. A consultative process will be used to validate the report. This will ground the efforts to identify and evaluate the drivers of deforestation under a REDD+ perspective.
	Progress report

Workshop report

Final report
	UNEP/FAO


	
	

	Outcome 4.2: Candidate activities for REDD+ identified
	4.2.1 Identify global best practices and benchmarking for forest management and REDD+ activities, and tailor practices to Zambia suitable activities are identified

4.2.2 Multiple benefits of REDD+ implementation identified and mapped

4.2.4 Expert consultations on development of a framework addressing opportunity costs for key stakeholders as well as cost abatement curves and follow up actions completed

4.2.5 Relevant global level initiatives are incorporated into national REDD+ strategy and national Development planning process
	no
	yes
	A study was conducted by NIRAS consulting firm. The report is expected at the end of January 2012. Validation will be through stakeholder consultation.  
The programme undertook an assignment to collect information from different sources and compile it in  digital form to enhance the database for the REDD+ Readiness process (some examples are mentioned in the "observations" section on the right. This 
exercise will enhance the database for the programme and also enable the REDD coordination office act as a resource center where different important information on REDD related issues can be found

	Progress report

Workshop report

Final report
Final report

CD containing information compiles
	UNEP/ FAO
	
	The current status and  development of Biofuel industry in Zambia, 2011; Institutional and Policy Analysis for Protected Areas under the Reclassification of Zambia’s Protected Areas Systems project;  The Roles of Traditional Leadership and Communities in Community Based Natural Resource Management in Zambia;   Resettlement Programs – Zambia; Baseline Study of the Socio‐economic Patterns of Charcoal, Wood and Stove use in greater Lusaka, Zambia; Wildlife Protected Areas Status



	Outcome 5: MRV capacity to implement REDD+ strengthened.
	
	
	
	A Technical Advisor for Measurements, Reporting and Verification (MRV) was recruited during the period under review and will start soon (end of January 2012).


	
	FAO
	Delays in the release of funds could impede progress and prevent deliverables being achieved on time.
	

	5.1 REDD+ integrated with forestry inventory system (ILUA)
	5.1.1 Full fungibility with the ILUA data base and information system provided

5.1.2 Environmental data are integrated with socio economic data

5.1.3 ILUA data management improved
	
	
	
ILUA and UN-REDD Programme worked jointly on various activities that are common of have common goals. It is expected that in 2012 most of the activities will be harmonized.

Communication materials on MRV were prepared during the year and distributed during various meetings and functions. 

	Workplan

Leaflets
	FAO
	
	

	5.2 Operational Forest Management institutionalized
	5.2.1 A cell for geographical information analysis and personnel training is established

5.2.2 A geographical explicit database for all types of of land use information is established and populated

5.2.3 An end user interface for database management and queries is designed and implemented

5.2.4 Support tools for REDD+ policies and measurements is selected

5.2.5 Linkages with regional geographical information systems are established.
	
	
	Some of the Coordination Unit offices were  refurbished during  year under review to accommodate the RS unit.
A needs assessment for the establishment of a fully equipped GIS Unit at National and Provincial levels of Forestry Department in Zambia was carried out. 

The equipment (Computers, printers, scanners) and software (Arc GIS 9.3) that is required for the monitoring system to be fully operational. were indentified and procurement included in the 2012 work plan.

Staff capacities were also assessed and trainings to improve capacities included in the 2012 work plan.
	Final report
	FAO
	
	

	5.3: Green house gas emissions and removals from forest lands estimated and accurately reported
	5.3.1 A fully compliant UNFCCC/IPCC greenhouse gas inventory is developed.

5.3.2 Training courses on greenhouse gas inventory methodology and IPCC Good practice Guidelines is developed and delivered
	
	
	Two technical officers from Zambia attended the intensive Training on Green House Gases (GHG) inventory in FAO HQ in January 2011. The workshop allowed a broad overview of the necessary steps for the set-up of a national GHG inventory in compliance with the UNFCCC reporting requirements.

A consultant was recruited to provide a framework and roadmap for the estimation and reporting of GHG emissions and removals from forest lands Zambia. 

	Inception report
	FAO


	
	The workshop  provided information and training on setting national systems for greenhouse gas (GHG) inventories, including technical requirements and institutional actions needed to establish a national GHG inventory. 



	Outcome 6: Assessment of REL and RL undertaken.
	
	
	
	
	
	
	Limited human resources in the country may limit project implementation.

	

	Outcome 6.1: Historical rates of forest are and carbon stock changes reviewed
	6.1.1 Report on historical forest area changes at national level developed

6.1.2 Historical greenhouse gas emissions and removal rates at national level assessed


	
	
	A methodological framework document was been developed for RL and REL in Zambia in FAO HQ.
A consultant was recruited to provide a framework for the assessment/ review of historical rates of forest area and carbon stock changes in Zambia. 

	 Progress reports

 Reports

 Publications
Inception report
	FAO
	
	Zambia will define one national Reference Emissions Level (REL) and one national Reference Level (RL), but to support REDD+ implementation, the country will also define RELs and RLs at sub-national levels. The sub-national RELs and RLs will be defined at provincial level or at project level which will depend on decisions made by the Zambian authorities on REDD+ implementation.

	6.2National circumstances assessed
	6.2.1 The opportunity cost of land providing REDD + benefits in relation to  other land uses

6.2.2 National socio economic condition assessed

6.2.3 Needs and resources for sustainable development assessed

6.2.4 Report on expected trends on forest area changes completed

6.2.5 Assessment of economic data on other sectors relevant to deforestation completed

6.2.6 The most threatened forests identified and mapped

6.2.7 Other forest co benefits assessed and mapped
	
	
	N/A  - Activities postponed to next year.
	 Progress reports

 Reports

 Publications

	FAO
	
	


1.3 

· 
· 
· 
· 
· 
1.4 Financial Information
In the table below, please provide up-to-date information on activities completed based on the Results Framework included in the signed National Programme Document; as well as financial data on planned, committed and disbursed funds. The table requests information on the cumulative financial progress of the National Programme implementation at the end of the reporting period (including all cumulative yearly disbursements). Please add additional rows as needed. Definitions of financial categories:
· Amount transferred: From the MPTF to date for the programme

· Commitments: Includes all amount committed to date. Commitment is the amount for which legally binding contracts have been signed and entered into the Agencies’ financial systems, including multi-year commitments which may be disbursed in future years.
· Disbursement: Amount paid to a vendor or entity for goods received, work completed, and/or services rendered (does not include un-liquidated obligations)
· Expenditures: Total of commitments plus disbursements
· Percentage delivery: Cumulative expenditure over funds transferred to date
	PROGRAMME OUTPUTS
	UN ORGANISATION
	IMPLEMENTATION PROGRESS

	
	
	Amount Transferred
	CUMULATIVE EXPENDITURES
	DELIVERY (%)

	
	
	
	Commitments
	Disbursements
	Total Expenditures
	Expenditure as percentage of the budget

	Output 1.1 REDD+ Readiness coordination and management bodies established and functioning.
	FAO
	-
	-
	-
	--
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	289,720
	2,840.93
	232,227.34
	229,386.41
	79 %

	Output 1.2 National REDD+ Readiness process integrated into the national development planning process.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	28,037
	0
	0
	0
	0 %

	Output 1.3 Communication and advocacy strategy as input in overall climate change strategy developed and implemented.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	54,500
	0
	0
	0
	0 %

	
	UNDP
	-
	-
	-
	-
	-

	Output 1.4 Mapping and gap analysis of relevant initiatives undertaken.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	28,037
	0
	0
	0
	0 %


	Output 2.1Stakeholders engagement process functioning.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	84,112
	-
	75,347.63
	75,347.63
	89%


	Output 2.2 Conflict resolution and redress mechanism reviewed.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	28,037
	0
	0
	0
	0 %

	Output 3.1 Institutional capacity to implement REDD+ framework developed.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	0
	0
	0
	0
	0 %

	Output 3.2   National REDD+ Strategy process integrated into the national development planning process.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	--

	
	UNDP
	37,383
	0
	0
	0
	0 %

	Output 3.3 Legislative framework to facilitate implementation of  REDD+ strengthened.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	70,093
	0
	0
	0
	0 %

	Output 3.4 Mechanism to administrate and channel REDD+ finance established.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	9,345
	0
	0
	0
	0 %

	Output 3.5 Benefit sharing model approved.
	FAO
	-
	-
	-
	-
	-

	
	UNEP
	-
	-
	-
	-
	-

	
	UNDP
	46,729
	0
	0
	0
	0 %

	Output 4.1 Drivers of deforestation and forest degradation assessed.
	FAO
	37383
	14,022
	20,698
	34,720
	92.9%

	
	UNEP
	36,000
	0
	0
	
	0%

	
	UNDP
	-
	-
	-
	-
	

	Output 4.2 Candidate activities for REDD+ identified.
	FAO
	40199
	14,900
	19214
	-
	84.9%

	
	UNEP
	37,000
	0
	0
	
	0%

	
	UNDP
	-
	-
	-
	-
	

	Output 5.1 REDD+ integrated with forestry inventory system (ILUA).
	FAO
	93458
	5,040
	28,737
	
	36.1%

	
	UNEP
	-
	-
	-
	-
	

	
	UNDP
	-
	-
	-
	-
	

	Output 5.2 Operational Forest Monitoring System established and institutionalized.
	FAO
	261,862
	
	104,023
	
	39.7%

	
	UNEP
	-
	-
	-
	-
	

	
	UNDP
	-
	-
	-
	-
	

	Output 5.3  Greenhouse gas emissions and removals from forest lands estimated and reported
	FAO
	140,187
	8,000
	11,971
	
	14.2%

	
	UNEP
	-
	-
	-
	-
	

	
	UNDP
	-
	-
	-
	-
	

	Output 6.1 Historical rates of forest area and carbon stock changes reviewed.
	FAO
	140,187
	9,000
	
	
	6.4%

	
	UNEP
	-
	-
	-
	-
	

	
	UNDP
	-
	-
	-
	-
	

	Output 6.2 National circumstances assessed.
	FAO
	186,916
	
	
	
	0

	
	UNEP
	-
	-
	-
	-
	

	
	UNDP
	-
	-
	-
	-
	

	Total FAO
	900,192
	50,962
	184,643
	235,605
	26.2%

	TOTAL :    
	
	
	
	
	


1.4.1 Co-financing

If additional resources (direct co-financing) are provided to the UN-REDD National Programme, please fill in the table below: 
	Sources of co-financing

	Name of co-financer
	Type of co-financing

	Amount (US$)

	N/A
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	


2. National Programme Progress
The questions in section two are intended to capture advancements and challenges that the National Programme has faced during the reporting period. It also aims to collect information on inter-agency coordination, ownership and development effectiveness, and communication. Please provide your answers after each question.
2.1 Narrative on Progress, Difficulties and Contingency Measures
The questions below ask for a brief narrative describing progress on the implementation of activities, generation of outputs and attainment of outcomes. It also asks for a description of internal and external challenges to National Programme implementation, as well as the contingency actions planned to overcome them.
2.1.1 Please provide a brief overall assessment of the extent to which the National Programme is progressing in relation to expected outcomes and outputs. Please provide examples if relevant (600 words).
The National Joint Programme was officially launched on the 23rd November 2010, and the Annual Workplan and Budget was signed on the 17th March 2011. The actual implementation started in June 2011.  The slow start was mostly due to administrative and basic coordination matters, slowed down by the fact that the second semester of 2011 was an intense electoral period for the country which resulted in a change of Government
Despite the initial slow start of the Programme, significant progress was done in terms of the initial studies that were agreed upon during the UN-REDD Mission visit at the time of the review in May 2011. The Joint Steering Committee and Technical Committee already existed, but there was need of expanding their mandate and incorporate adequate stakeholders. 

During the reporting period,  the Ministry of Tourism, Environment and Natural resources was abolished, after the elections.  The Forestry Department is now under the Ministry of Mines and Natural Resources.
The REDD+ readiness process in Zambia has put an emphasis on developing local-level structures for awareness raising, capacity development and dialogue. As a result, most of the review meeting and trainings conducted during the year had representatives from all the 9 provinces of Zambia, which requires more complex logistics. During the 2012 period the activities will extend as one more province has been created.

In summary the main activities conducted during the period under review were as follows:

a. Set up of REDD+ Coordination Unit
b. 
c. Recruitment of MRV TA and Administrative Assistant
d. 7 specific studies were conducted aimed at generating more information for the readiness process. These were:
i. Drivers of Deforestation and potential for REDD+
ii. Stakeholder Assessment and Engagement Plan
iii. Forest best practices related to REDD+
iv. Legal Preparedness for REDD+
v. Needs assessment for GIS 
vi. Consolidation of research reports
vii. Digital data in agriculture, lands, forestry, energy
e. Awareness raising and training for various stakeholders, including Provincial representatives, were conducted
2.1.2 Please provide a brief overall assessment of any measures taken to ensure the sustainability of the National Programme results during the reporting period. Please provide examples if relevant. (250 words)
The REDD+ readiness process in Zambia is based on developing capacity of the stakeholders and on solid coordination. This has been a core activity in this first year of implementation, and will remain as such in the next year. UN-REDD technical and policy advisory missions proved useful in providing such guidance..

2.1.3 If there are difficulties in the implementation of the National Programme, what are the main causes of these difficulties? Please check the most suitable option.
 FORMCHECKBOX 
 UN agency Coordination

 FORMCHECKBOX 
 Coordination with Government 

 FORMCHECKBOX 
 Coordination within the Government 

 FORMCHECKBOX 
 Administrative (Procurement, etc) /Financial (management of funds, availability, budget revision, etc)

 FORMCHECKBOX 
 Management: 1. Activity and output management 
 FORMCHECKBOX 
 Management: 2. Governance/Decision making (PMC/NSC) 
 FORMCHECKBOX 
 Accountability
 FORMCHECKBOX 
 Transparency
 FORMCHECKBOX 
 National Programme design
 FORMCHECKBOX 
 External to the National Programme (risks and assumptions, elections, natural disaster, social unrest)
2.1.4 If boxes are checked under 2.1.3, please briefly describe any current internal difficulties
 the National Programme is facing in relation to the implementation of the activities outlined in the National Programme Document. (200 words)
There has been various factors, some inter-acting among them, that have slowed down the start of implementation and its progress. Yet these factors are not important and rather related to the start of a new policy process of certain technical complexity and a need of stakeholder engagement, as REDD+ entails.

Coordination arrangements for the programme took time to be consolidated and this caused for some delays in the beginning of the Programme
There follows next a description of some of these factors.

a. Establishment of the Steering Committee and Multi-sectoral committee.
The process of formalization of the Joint Steering Committee took time and is still underway. The cross-sectorial dimension that REDD+ requires is not easy to achieve because most government structures are used to a thematic focus.. However, appointments of Focal point persons from key institutions like Agriculture, Energy, Finance, local government, Local Government and Community Development were been processed. It is expected that formalization of the Technical Committee will be concluded in the first quarter in 2012.

b. Linkages and coordination among UN-REDD, ILUA, CCFU and ENRMMP: 
It has been observed that there was need for the 4 programmes to work together to avoid duplication of work. The abolished Ministry (MTENR) prepared a concept of to enhance the linkages of the 4 programmes. The REDD+ and ILUA programmes are being coordinated from within Forestry Department while CCFU and ENRMMP are in the Ministry of Local Government and Housing, Early Child Education and Environmental Protection. This process of coordination has required discussions and dialogue among the parties, which required time.
c. Abolition and Establishment of new Ministries: It must be noted that there has been reorganization and realignment of the Ministry. The functions have been split among Ministry of Information, Broadcasting and Tourism, Ministry of Mines and Natural Resources and that of Ministry of Local Government and Housing, Early Education, and Environmental Protection. This may result in some adjustments in administration of programmes in the former Ministry (MTENR).

d. Start of Implementation: The programme was launched on the 23rd November 2010 and the Workplan and Budget was signed in March 2011 and the actual implementation started in June 2011. In addition, Outcome 5 of the programme is dependant more of the progress of ILUA Project while Outcome 6 was postponed to 2012. The Forestry Department continued to provide office supplies, fuel and vehicle 

to the Programme during the period under review to lessen the Programme administrative challenges of the REDD+ Coordination Unit.

e. Procurements: The procurement process with UNDP was initially slow but picked up at the end of the year when the Local Purchase Order Books were procured and the Administrative Assistant recruited in November 2011. 

2.1.5 If boxes are checked under 2.1.3, please briefly describe any current external difficulties
 (not caused by the National Programme) that delay or impede the quality of implementation. (200 words)
Year 2011 was an electoral year with resulted in a new President and a new Government from a different political party. This caused some delays in the implementation of the programme, as well as disruptions due to a restructuration of the public administration..

2.1.6 Please, briefly explain the actions that are or will be taken to eliminate or manage the difficulties (internal and external referred to in question 2.1.3 and 2.1.4) described in the previous sections. (250 words)
The Coordination arrangements has been concluded and the required staff have been attached to the programme. In addition, towards the end of 2011, the Director of Forestry recognized the need to discuss with the Permanent secretary for an addition staff to the programme from the research division. This is further expected to enhance the delivery of the programme. An international-level technical advisor will be recruited in early 2012 and this will enhance advisory support to the programme implementation..
2.2 Inter-Agency Coordination

The aim of the questions below is to collect relevant information on how the National Programme is contributing to inter-agency work and “Delivering as One”.

2.2.1 Is the National Programme in coherence with the UN Country Programme or other donor assistance framework approved by the Government?
 FORMCHECKBOX 
 Yes
 FORMCHECKBOX 
No
If not, does the National Programme fit into the national strategies?
 FORMCHECKBOX 
 Yes
 FORMCHECKBOX 
No
If not, please explain:
2.2.2 What types of coordination mechanisms and decisions have been taken to ensure joint delivery? Please reflect on the questions above and add any other relevant comments and examples if you consider it necessary:
The HACT assessment was finalized in Jan 2011 to ensure good implementation within the UN Agencies.
2.2.3 Is HACT being applied in the implementation of the National Programme by the three participating UN organisation?
 FORMCHECKBOX 
Yes

 FORMCHECKBOX 
No
If not, please explain:

2.3 Ownership
 and Development Effectiveness

The questions below seeks to gather relevant information on how the National Programme is putting into practice the principles of aid effectiveness through strong national ownership, alignment and harmonization of procedures and mutual accountability.
2.3.1 Do government and other national implementation partners have ownership of the implementation of activities and the delivery of outputs?
 FORMCHECKBOX 
 No

 FORMCHECKBOX 
Some 
 FORMCHECKBOX 
 Yes
Please explain:
Government is implementing the Programme with support from civil society. Government has so far provided enough guidance on how the REDD+ readiness process is to be implemented in Zambia. So far the government has provided leadership on the direction of implementation. As in any new initiaitves the programme has faced challenges and this is forms part of the capacity building process of the programme itself.
2.3.2 Are the UN-REDD Programme’s Guidelines for Stakeholder Engagement and Operational Guidance Engagement of Indigenous Peoples and Other Forest Dependent Communities been applied in the National Programme process?

 FORMCHECKBOX 
 No

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
 Fully 

Please explain, including if level of consultation varies between non-government stakeholders:
The government has effectively engaged various stakeholders from the design to the implementation of the NJP readiness process. The Stakeholder analysis has just been completed and it is expected that more engagement platforms and levels will be identified and enhance the engagement further. And local consultants have been used in the studies so far providing room for ownership of the outputs. The national REDD+ team cooperates closely with the UN-REDD team, following UN-REDD policies and using UN-REDD tools and experiences.
2.3.3 What kind of decisions and activities are non-government stakeholders involved in?

 FORMCHECKBOX 
 Policy/decision making

 FORMCHECKBOX 
 Management:  FORMCHECKBOX 
 Budget  FORMCHECKBOX 
 Procurement  FORMCHECKBOX 
 Service provision 

 FORMCHECKBOX 
 Other, please specify

Please explain, including if level of involvement varies between non-government stakeholders:
Decision of Policy is made by government through a consultative process. The non-governmental organization have been involved in the design of the NJP and are the ones that made the proposal to have Forestry Department lead the process of the REDD+ readiness. They continue to be part of the overall implementation. They have been involved in awareness raising on the general climate change issues including REDD+ 

2.3.4 Based on your previous answers, briefly describe the current situation of the government and non-government stakeholders in relation to ownership and accountability
 of the National Programme. Please provide some examples. 
The government and Non-Governmental Organizations have worked closely. They have contributed considerably to shaping the approach of implementation of the NJP.

3. General Programme Indicators
This section aims to aggregate information on results for the six work areas of the UN-REDD Programme defined in the Programme’s Strategy (2011-2015), delivered through the Global and National Programmes. Information is to be provided cumulatively. If the information requested is not available at this stage of Programme implementation, check the “does not apply” box.
1.4.2 Number of MRV and monitoring related focal personnel with increased capacities:
 FORMCHECKBOX 
  Women

Total No   …….

 FORMCHECKBOX 
  Men


Total No   …….  
Comments: information not applicable yet.

Does not apply as this component as not yet been implemented
1.4.3 Does the country have a functional MRV and monitoring system in place?
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
  Not applicable at this stage

Comments:
1.4.4 Does the country have nationally owned governance indicators, developed through a participatory governance assessment?
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
Not applicable at this stage

Comments:

1.4.5 Was a participatory governance assessment supported by the UN-REDD Programme and incorporated into the National REDD+ Strategy?
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
 Not applicable at this stage

Comments, including if the assessment was supported by another initiative:
1.4.6 Does the National REDD+ Strategy include anti-corruption measures, such as a code of conduct, conflict of interest prohibitions, links to existing anti-corruption frameworks, protection for whistleblowers or application of social standards?
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
 Not applicable at this stage

Comments:
1.4.7 Number  of Indigenous Peoples/civil society stakeholders represented in REDD+ decision making, strategy development and implementation of REDD+ at the national  level:
 FORMCHECKBOX 
  Women    
Total No. …….
 

 FORMCHECKBOX 
  Men

Total No. …….

Comments: Information not yet applicable as no major REDD+ decision making is taking place; nevertheless, a fluid information exchange and dialogue is under way between government and civil society stakeholders.

N/A
1.4.8 Number  of consultation processes (Meetings, workshops etc.) underway for national readiness and REDD+ activities:
Total No.  around 4 major processes (Dialogue with national REDD+ team; REDD+ Orientation workshops; stakeholder assessment exercise; and consultations for the ongoing studies and technical tasks).
Comments:

A number of consultation processes were conducted involving national and provincial stakeholders.
1.4.9 Grievance mechanism established in order to address grievances of people alleging an adverse effect related to the implementation of the UN-REDD national programme:
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
 Not applicable at this stage

Comments:

1.4.10 Country has undertaken to operationalize Free Prior and Informed Consent for the implementation of readiness or REDD+ activities that impact Indigenous Peoples’ and local communities’ territories, resources, livelihoods and cultural identity:
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
  Not applicable at this stage

Comments:

1.4.11 Country applying safeguards for ecosystem services and livelihood risks and benefits:
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
  Not applicable at this stage

Comments:

1.4.12 Application of the UN-REDD Programme social principles and criteria: 
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
  Not applicable at this stage

Comments:

1.4.13 REDD+ benefit distribution system contributes to inclusive development
, with specific reference to pro-poor
 policies and gender mainstreaming
:
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
  Not applicable at this stage

Comments:
1.4.14 Country adopting multiple benefit decision tool kit:
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
  Not applicable at this stage

Comments:

1.4.15 National or sub-national development strategies incorporate REDD+ based investments as means of transformation of relevant sectors
:
 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
  Not applicable at this stage

Comments:
1.4.16 Investment agreements supported or influenced so that they take advantage of the REDD+ as a catalyst to a green economy:

 FORMCHECKBOX 
  Yes 

 FORMCHECKBOX 
 Partially
 FORMCHECKBOX 
  No

 FORMCHECKBOX 
  Not applicable at this stage

Comments:
4. Government Counterpart Information
The aim of this section is to allow the Government Counterpart to provide their assessment, as well as additional and complimentary information to Section 1-3 which are filled out by the three participating UN organizations.

	Comments by the Government Counterpart:
The REDD+ initiative is providing an avenue for sustainable forest/land management. While the start of the Programme was slow due to some administrative matters, a number of activities were conducted mainly consultative meetings and studies were carried out, providing a basis for future planned activities in the coming year, 2012. There was an improvement in the understanding and appreciation of REDD+ among the various stakeholders. Provincial and District capacity development is required as a foundation for REDD+.     


	


� Last signature on the National Programme Document


� As reflected on the MPTF Office Gateway � HYPERLINK "http://www.mdtf.undp.org" �www.mdtf.undp.org� 


� If yes, please provide new end date


� Those organizations either sub-contracted by the Project Management Unit or those organizations officially identified in the National Programme Document as responsible for implementing a defined aspect of the project


� The total budget for the entire duration of the Programme, as specified in the signed Submission Form and National Programme Document. This information is available on the MPTF Office GATEWAY � HYPERLINK "http://www.mdtf.undp.org" �www.mdtf.undp.org�


� This information is available on the MPTF Office GATEWAY � HYPERLINK "http://www.mdtf.undp.org" �www.mdtf.undp.org�


� Disbursement and commitments combined


� Each UN organisation is to nominate one or more focal points to sign the report. Please refer to the UN-REDD Programme Planning, Monitoring and Reporting Framework document for further guidance


� Commitment is the amount for which legally binding contracts have been signed, including multi-year commitments which may be disbursed in future years


� Indicate if the source of co-financing is from: Bilateral aid agency, foundation, local government, national government, civil society organizations, other multilateral agency, private sector, or others.


� Indicate if co-financing is in-kind or cash.


� Difficulties confronted by the team directly involved in the implementation of the National Programme


� Difficulties confronted by the team caused by factors outside of the National Programme


� Ownership refers to countries exercising effective leadership over their REDD+ policies and strategies, and co-ordination of actions.


� Accountability: Acknowledgment and assumption of responsibility for actions, � HYPERLINK "http://en.wikipedia.org/wiki/Product_%28business%29" \o "Product (business)" �products�, decisions, and policies and encompassing the obligation to report, explain and be answerable for resulting consequences.


� Inclusive development is development that marginalized groups take part in and benefit from, regardless of their gender, ethnicity, age, sexual orientation, disability or poverty. Inclusive growth implies participation and benefit-sharing.  On the one hand, it ensures that everyone can participate in the growth process, both in terms of decision-making for organizing the growth progression as well as in participating in the growth itself. On the other hand, it makes sure that everyone shares equitably the benefits of growth.


� Pro-poor policies are those that directly target poor people (i.e. benefit the poor more than the non-poor), or that are more generally aimed at reducing poverty. There is also a general consensus that pro-poor policy processes are those that allow poor people to be directly involved in the policy process, or that by their nature and structure lead to pro-poor outcomes. For some, the aim of pro-poor policies is to improve the assets and capabilities of the poor.


� The overall intention of gender mainstreaming with regard to environment and energy is to ensure the inclusion of gender equality considerations in planning systems at all levels, and to expand both the access of women to finance mechanisms and the direction of that finance to areas that will benefit women.  Gender mainstreaming tools include gender analysis, sex-disaggregated data and participatory approaches that explicitly consider women.


� Relevant sectors denote those that are related to forests and land use, e.g. including energy, agriculture, mining, transport and land use planning.





�The perceived slow process is caused by pre-determined direction of how REDD+ readiness process should be implemented by the UN-System as can be seen from the continued administrative challenges (behind the scene maneuvers) concerning Coordination, role of Technical ADVISOR, limited support to the REDD+ Coordination Unit. There are so many interested parties in REDD+ who want to have controls of the REDD+ in Zambia. This has created an impression that GRZ is not appropriately leading the process. This requires to be addressed very soon if we have to see reasonable progress in 2012. I have therefore deleted the comment.  


�This is not a risk at the moment because we are designing the REDD+ implementation and the roles and responsibilities of each stakeholders will be understood once the various studies are completed and the implementation arrangements agreed upon. So I have modified the text.


�This may not be correct that the country may not have human resource!!!! This Programme aims at building the capacity of stakeholders and this will have to be addressed.


�UNDP note:


There is no request (RDP) from the FD to pay for fuel.


 Two vehicles (1 in garage though) have been waiting for transfer to UN-REDD from a previous project.


�The 2 vehicles referred to under comment U1 above are vehicles procured in in late 2008 and arrived in early 2009 under a different Programme called “Utilization of Environmental Assets and Climate Change.” A request for fuel was made and we were told to justify use of fuel by requesting that the vehicles be transferred to the UN-REDD Programme. The REDD+ Coordination Unit and Indeed the Ministry is not in a position to make such a request.





2

